Annex 2: TEMPLATE – MONITORING, EVALUATION AND RESEARCH PLAN 20xx-20XX

NOTE: Examples have been included below to illustrate how to complete each column; they are not meant to be accurate to real life activities.

Monitoring and Research Plan 2015

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount |
| MONITORING |  |  |  |  |
| Impact 1: Women lead and participate in decision making at all levels |  |  |  |  |
| Quarterly progress reports and Biannual/Annual Progress reports from Partners | To be added | TBC |  |  |
| Baseline Report of the second phase of the RNE supported Programme conducted in India, Bhutan and Sri Lanka | Government, CSOs, NGOs in India, Bhutan and Sri Lanka | TBC |  |  |
| Training Needs Assessment and pre and post evaluations of capacity building of Parliamentarians and women in Political participation in Maldives | Parliamentarians, UN Agencies, CSOs in Maldives | TBC |  |  |
| Reports to Donor |  |  |  |  |
| Biannual/Annual Progress Reports to RNE |  |  |  |  |
| Impact 2: Women from excluded communities in MCO countries realise their right to sustainable livelihoods, decent work and social protection. |  |  |  |  |
| Reports from Partners |  |  |  |  |
| End line and final progress reports for project on “Making women's voices and votes count- An ICT based intervention in India" | IT for Change and KMVS | End line Report – May Final Progress Report - May | Non-Core (FGE) |  |
| Six monthly narrative Progress reports, End line and final progress report for project on “Dignity Campaign- Action for Liberation of Dalit Manual Scavenger women in India” | Jan Sahas | Jan-Jun – Report due in July Final Progress Report – Jan 2016 Endline- Jan 2016 | Non-Core (FGE) |  |
| End line and final progress reports for the projects on “Economic empowerment of women in low income groups and the realization of their economic rights and gender equality” ( SriLanka) | CENWOR | Endline- July Final Progress Report- July | Non-Core (FGE) |  |
| End line and final progress reports for the projects on “Facilitating women in four endemic poverty states of India to access, actualize and sustain provisions on women empowerment” | PRADAN | Endline- July Final Progress Report- July | Non-Core (FGE) |  |
| Training Capacity Assessments, Quarterly progress reports and annual progress report for project regarding training and accompaniment to MORD, MWCD, MOLE for gender responsive design, implementation and monitoring of laws and flagship programmes for women workers and farmers | ANANDI/ Mahila Samakhya/ Women's Rights organizations | Training Capacity Assessment Report- June, Sep QPR- April, July, Oct, Jan 2016 Annual Progress Report- Jan 2016 | Non-Core ( RNE+ ADB) | 176504 (Part of the WEE Budget) |
| Quarterly progress reports and annual progress report for project on setting up of a national level alliance for undertaking research, training and advocacy on rights on women farmers | MAKAAM/Women's Rights Organizations | QPR- April, July, Oct, Jan 2016 Annual Progress Report- Jan 2016 | Core | 40000 (Part of the WEE Budget) |
| Reports to Donors |  |  |  |  |
| Six Monthly progress reports and annual progress report for project regarding training and accompaniment to MORD, MWCD, MOLE for gender responsive design, implementation and monitoring of laws and flagship programmes for women workers and farmers | RNE + ADB | As per contractual agreement with donors |  |  |
| Action research on implementation of laws, policies and programmes for rights of women workers | RNE | As per contractual agreement with donor |  |  |
| Monitoring Missions |  |  |  |  |
| Monitoring Missions to FGE and WEE Core projects | Jan Sahas, ANANDI, CSO partners | Jan- Dec | Non-Core (FGE and ADB) and Core | 20000 (Part of the WEE Budget) |
| Impact 3: Women and girls in four South Asian countries live a life free from Violence |  |  |  |  |
| Reports from Partners |  |  |  |  |
| Quarterly Progress Report of “Delhi Safe City Program Free of Violence Against Women and Girls” | Jagori | April, July, October | Non-Core |  |
| Quarterly Progress Reports of “Empowerment of Widows and their Coalition” | Astha (support subject to fund availability) |  | Non-Core |  |
| Final Report of UNTF Project on “Community Initiative to Address Violence against Women in Sex Workers in Karnataka, India”(Project Extension granted till June 2015) | KHPT | June | Non-Core |  |
| Six Monthly Report of UNTF Project on “Preventing Violence: Change Starts Now” | Breakthrough | June, December | Non-Core |  |
| Final Report of UNTF Project on “Anti-harassment committee’s and violence prevention system in export-oriented garment factories” | Fairwear Foundation | April | Non-Core |  |
| Training Needs Assessment and pre and post evaluations of Gender Training and Consultation reports in Sri Lanka | Government of Sri Lanka | July | Non core |  |
| Training Needs Assessment and pre and post evaluations of Gender Training and GBV into magistrates and judges induction training modules in Maldives | Magistrates/Judges in Maldives | TBC | Core |  |
| Reports to Donors |  |  |  |  |
| Annual Report “Delhi Safe City Program Free of Violence Against Women and Girls” | USAID | December | Non-Core |  |
| Six monthly Report “Delhi Safe City Program Free of Violence Against Women and Girls” | Japan | July , December | Non-Core |  |
| Monitoring Missions |  |  |  |  |
| Monitoring visit Delhi Safe City “Delhi Safe City Program Free of Violence Against Women and Girls” | Jagori/Pravah | April/October | Non-core | (Part of the EVAW Budget) |
| UNTF Project on “Anti-harassment committee’s and violence prevention system in export-oriented garment factories” | Fairwear | January | UNTF | 3,000 (Part of the EVAW Budget) |
| UNTF Project on “Community Initiative to Address Violence against Women in Sex Workers in Karnataka, India” ”(Project closes in June 2015) | KHPT | January/June | UNTF | 3,000(Part of the EVAW Budget) |
| UNTF Project on “Anti-harassment committee’s and violence prevention system in export-oriented garment factories” | Dhaka, Bangladesh | February | UNTF | 3,600(Part of the EVAW Budget) |
| Safe City Program Free of Violence Against Women and Girls” and Shaurya Dal Program with Government of Madhya Pradesh | Bhopal | March/August | Non-core | (Part of the EVAW Budget) |
| Project on “Safe City Program Free of Violence Against Women and Girls” | Mumbai | June/November | Non-core | (Part of the EVAW Budget) |
| Project on “Empowerment of Widows and their Coalition” | Udaipur | March/September | Non-core | (Part of the EVAW Budget) |
| Work on Ending Violence against Women in Maldives | RCO | March | Core | (Part of the EVAW Budget) |
| Work on Ending Violence against Women in Srilanka | RCO | April | Core | (Part of the EVAW Budget) |
| Work on Ending Violence against Women in Bhutan through engaging Men and Boys as champions of gender equality | NCWC | March | Core | (Part of the EVAW Budget) |
| Impact 4: Peace building and humanitarian action are shaped by women leadership and participation in four countries in South Asia. |  |  |  |  |
| Reports from Partners |  |  |  |  |
| Quarterly and Annual progress reports and Donor reports for the projects on "Capacity building of peacekeeping institutions to integrate gender perspectives into policies and pre-deployment trainings " | Ministry of Defence Ministry of Home Affairs Department of Peace Keeping Operations(DPKO)- UNW HQ | December 2014 Quarterly 2015 Annual Report - 2015 |  |  |
| Impact 5: Macroeconomics framework and national development plans and budgets fully reflect accountability for GE commitments and priorities |  |  |  |  |
| Reports from Partners |  |  |  |  |
| Quarterly/Annual Progress Report from NFI project on Building Partnerships with Civil Society Budget work organizations on GRB | National Foundation for India & partners in 6 states | Quarterly - September 2014 to February 2016) Annual Report - | Core | $70,000(Part of the GRB Budget) |
| Technical Support to select line departments and state governments Baseline/Endline Assessment of GRB trainings conducted Final Annual Progress Report | Ford Foundation; Officials from Relevant Ministries | January 2015 to December 2015 December 2015- Annual Report to Donor | Core | $60,000(Part of the GRB Budget) |
| Trainings and capacity development of Audit Officials on GRB Final Progress Report including Baseline/Endline Assessment of GRB trainings conducted | Audit Officials (national/state level), audit training institutes, Fiscal Policy Institute | March 2015 to December 2015 Final Report – December 2015 | Core | $20,000(Part of the GRB Budget) |
| Pilot test of CEDAW practitioners guide and capacity Development of CSO Final Progress Report | CSOs and women’s rights organizations | March 2015 to December 2015 Final Report – December 2015 | Core | 10,000(Part of the GRB Budget) |
| Reports to Donors |  |  |  |  |
| Interim and Project Completion Report to Ford Foundation (TBC) | Ford Foundation; Officials from Relevant Ministries | January – December 2015 | Non core | 100,000 (Part of the GRB Budget) |
| Monitoring Missions |  |  |  |  |
| Monitoring visits to select states under NFI project on Building Partnerships with Civil Society Budget work organizations on GRB | National Foundation of India, State budget groups Odisha, Gujarat, MP, Maharashtra, Rajasthan, AP | March to December 2015 | Core | (Part of the GRB Budget) |
| Impact 6: Coordination and inter-governmental processes : A comprehensive and dynamic set of global norms, policies and standards on gender equality and women’s empowerment is in place and is applied through action by the national Governments and other stakeholders at all levels. |  |  |  |  |
| Quarterly Progress Reports from SAARC Gender Specialist and SARRC Gender Policy Advisory Group (GPAG) Technical meetings | SAARC, GPAG | Quarterly | Core | 72000 (Part of Coordination Unit’s Budget) |
| Quarterly Progress Report to ROPA | ROPA, UN Women | Every Quarter | Core |  |
| Mission Reports from CSO Delegates to Intergovernmental processes | CSO Delegates | Periodic Mission Report | Core/RNE | 50,000 (Part of Coordination Unit’s Budget) |
| Pre Briefing and Post Briefing CSO Consultation Reports for Inter-governmental processes | CSOs/UN Women | Periodic Consultation Report | RNE | 35000(Part of Coordination Unit’s Budget) |
| Technical Reports on Tracking Implementation of CEDAW and Beijing Platform for Action | Technical Consultant | Quarterly | RNE | 40,000 (Part of Coordination Unit’s Budget) |
| Monthly Progress Reports from Consultant at MWCD | Technical Consultant | Monthly | Core/RNE | 26,000 (Part of Coordination Unit’s Budget) |
| OEE output cluster 2: To institutionalize a strong culture of results-based management, reporting, knowledge management and evaluation |  |  |  |  |
| 14 Monitoring/Evaluation visits under 5 Impact areas | M&E Unit/Partners/ Programme Units | Biannual | Core/Non-Core | 10,000 (Part of M&E Budget) |
| Complete Mid-term review of UN Women, MCO India Strategic Plan 2014-2017. | M&E Unit/Partners/UN Women Office | Q2 of 2015 | Core | 15,000 |
| RESEARCH |  |  |  |  |
| Impact 1: Women lead and participate in decision making at all levels |  |  |  |  |
| Situational Analysis for Sri Lanka, Bhutan and Maldives supported | Government, CSOs, Academicians | January March | Core | (Part of Governance Budget) |
| Conduct research on the impact of the 50 per cent reservation for women in Panchayati Raj Institutions (PRIs) | Government, CSOs, Academicians | March - Dec | RNE | (Part of Governance Budget) |
| Asses the national and state structures (NIRD/SIRD) and methods of capacity development for elected representatives mapped from gender lens | Government, CSOs, Academicians | Feb - Dec | RNE | (Part of Governance Budget) |
| Mapping the journey of the elected women representative provided training under the first phase and the impact of the training on decision making | Government, CSOs, Academicians | Jan - June | RNE | (Part of Governance Budget) |
| Impact 2: Women from excluded communities in MCO countries realise their right to sustainable livelihoods, decent work and social protection. |  |  |  |  |
| Action research on implementation of laws, policies and programmes for rights of women workers | CSO | Jan-Dec | Core + Non Core | 30000 + 25000 (Part of the WEE Budget) |
| Research to map women's unpaid work across sectors/flagship schemes - NRLM, NREGA, NFSA, NSDC | CSO | Jan- Dec | Core | 25000 (Part of the WEE Budget) |
| Undertaking research on rights of women farmers | CSO | Jan- Dec | Core | 40000 (Part of the WEE Budget) |
| Action research to assess the utilization of remittance sent by women migrant workers receiving households for creating sustainable livelihoods and building social capital | CSOs | tbc | tbc | tbc |
| Impact 3: Women and girls in four South Asian countries live a life free from violence |  |  |  |  |
| Handbook on Sexual Harassment | TBD | December 2014-March 2015 | Core | 15,000(Part of the EVAW Budget) |
| National Research on trafficking | NHRC and TISS | January 2015 for two years | Core | 40,000(Part of the EVAW Budget) |
| Research on Sex selection | HLC , CWDS, UNFPA | December 2014-June 2015 |  | 30,000(Part of the EVAW Budget) |
| Research on VA against transgender community | TBD | March 2015-October 2015 |  | 25,000(Part of the EVAW Budget) |
| Impact 4: Peace building and humanitarian action are shaped by women leadership and participation in four countries in South Asia. |  |  |  |  |
| Longitudinal study on perceptions and reflection of UN police and military commanders on (pre-post) pre-deployment training on gender and sexual violence in armed conflict | Government | Tbc | Tbc | Tbc |
| Impact 5: Macroeconomics framework and national development plans and budgets fully reflect accountability for GE commitments and priorities |  |  |  |  |
| Research on Impact of Budget on Time Use | Feminist Researchers | 2/2015 to 12/2015 | Core | $25000(Part of the GRB Budget) |
| Research on GRB and Intersectionality | CSO/women’s rights groups | September 2014 to March 2015 | Core | $10000(Part of the GRB Budget) |
| Research on Gender and Macroeconomics | Feminist Researchers | September 2014 to March 2015 | Core | $20000(Part of the GRB Budget) |

Evaluation Plan 20xx-20xx

| Evaluation name | Mandatory? (Y/N) |  | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ MCO/ RO AWP Output | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |  |
| Impact 1: Women lead and participate in decision making at all levels |  |  |  |  |  |  |  |  |  |  |  |  |
| Impact 2: Women from excluded communities in MCO countries realise their right to sustainable livelihoods, decent work and social protection. |  |  |  |  |  |  |  |  |  |  |  |  |
| Impact 3: Women and girls in four South Asian countries live a life free from violence |  |  |  |  |  |  |  |  |  |  |  |  |
| Final Evaluation of the project on "Empowerment of Widows and their Coalitions programme" | Y |  |  |  | India | MCO/India, Nepal and Sri Lanka |  | WHR, WERC | Q1 2015 | 15,000 | Initiated | Carry - Over |
| Impact 4: Peace building and humanitarian action are shaped by women leadership and participation in four countries in South Asia. |  |  |  |  |  |  |  |  |  |  |  |  |
| Impact 5: Macroeconomics framework and national development plans and budgets fully reflect accountability for GE commitments and priorities |  |  |  |  |  |  |  |  |  |  |  |  |
| Final Evaluation of the Ford funded Programme on "Partnership with civil society and the Comptroller and Auditor General (CAG) of India to promote gender responsive planning, budgeting and auditing in select States" | Y |  |  |  | India | India |  | Swadhikar, Social Watch, NEN, Fiscal Policy Institute and Independent Researchers | Q1 2015 | 10,000 | Initiated | Carry- Over |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |  |
| Impact 2: Women from excluded communities in MCO countries realise their right to sustainable livelihoods, decent work and social protection. |  |  |  |  |  |  |  |  |  |  |  |  |
| Final Evaluation: “Making women's voices and votes count- An ICT based intervention in India" | Y |  | Goal: 1 Outcome 1.1 Women from excluded communities have increased political representation and voice at levels of the government | Output 1.1.1: Enhanced political participation by women from excluded communities in the election process at the national and sub-national levels. | India MCO | India | N | NGO- IT for Change, KMVS | Jan-Mar 2015 | Non-Core (FGE) $ 14,700 + $ 10,000 | To be initiated |  |
| Final Evaluation “Facilitating women in four endemic poverty states of India to access, actualize and sustain provisions on women empowerment” | Y |  | Outcome 2.1 National and state policies, strategies and flagship programmes become gender responsive and women have increased access to and control over income and resources. | Output 2.1.2 Women from excluded communities, especially those working in agricultural and informal sectors, have increased access to income generation opportunities, social protection and decent work conditions | India MCO | India | N | NGOs - PRADAN and Jagori | Apr- Jun 2015 | Non-Core- FGE $15,000 | To be initiated |  |
| Impact 3: Women and girls in four South Asian countries live a life free from violence |  |  |  |  |  |  |  |  |  |  |  |  |
| Final Evaluation of the Trust Fund Project | Y |  |  |  | India | MCO/India and Bangladesh |  | India MCO and Fairware Foundation India MCO and Breakthrough Trust India MCO and KHPT | Q1 2015 Q4 2016 Q1 2015 | 10,598.65 39,389 9,524 | To be initiated To be initiated To be initiated |  |
| Impact 5: Macroeconomics framework and national development plans and budgets fully reflect accountability for GE commitments and priorities |  |  |  |  |  |  |  |  |  |  |  |  |

Please fill out a separate row for each evaluation.