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Monitoring and Research Plan 2014-2015

	Activity 
	Partners and stakeholders 
	Planned Dates (Month and year of start and end)
	Budget

	
	
	
	Source
	Amount

	MONITORING

	Monitoring visits to various project sites 
	Ministry of Social Welfare, Gender and Children’s Affairs (MSWGCA), UN Agencies, CSO partners 
	1/14-12/15
	N/Core TBM
	$10,000

	RESEARCH

	Research on Urban Women Poverty
	FAO, Key government ministries, Department and Agencies
	3/14-12/15
	N/Core TBM
	$10,000

	Research on Gender Interventions in 10 Ministries, Department and Agencies
	Key Government Ministries, Departments and Agencies
	1/14-12/15
	Non-core: PBF
	$ 35,000

	Collection of all missing baseline data for the SN and AWP as well as for all programmes.
	Central Statistics, key government ministries, agencies and departments.
	1/14-12/15
	N/core TBM
	$10,000


Evaluation Plan 2014-2016[footnoteRef:2] [2:  Please fill out a separate row for each evaluation. ] 

	Evaluation name
	Mandatory?
(Yes)
	UNDAF Outcome/ UN Women SP Goal, Outcome  
	Country/ MCO/ RO AWP Output
	Office in charge
	Region/ country
	Joint activity 
(Yes indicate partners)
	Key Stakeholders
	Planned Dates 
(start-end)
	Budget (US$) / Sources of Funding
	Status (pending/ initiated/ ongoing/ completed)
	Remarks

	Evaluations in which the office participates
	

	Evaluation 1:
Evaluation of UN Women Sierra Leone’s contribution to EVD Response

	

Y

	UNW SP Goal 4 Outcome 4

	Sierra Leone -AWP Output 4
	
	Sierra Leone
	N
	RCO/UNCT/GTT
MSWGCA
Donor Gender Reference Group
NERC
UNMEER
	July-Sept 2015
	US$30,000
Core Funds
	Pending
	

	Evaluation 2:
Mid-Term Evaluation of SLE programme on Women, leadership and political participation
	Y




	UNW SP Goal 1 Outcome 1


	 Sierra Leone -AWP Output 1

Sierra Leone 
	Sierra Leone 
CO


	

Sierra Leone 
	

Y
	GNWP-SL
MSWGCA
WISSL
MLGRD-
ONS
UN Women
	


May to July 2016
	US$30,000
Core Funds
	


Pending
	

	Evaluation 3:
1325 NAP assessment/evaluation-2010-2014
	
Y 
	
Goal 4, Outcome  4
	Sierra Leone -AWP
Output 4
	MSWGCA
CO
	Sierra Leone
	Y
	SLEFPAC 
CRC 
CSO
APPWA
MLGRD 

	Sept –November 2015
	
US$30,000
Core Funds

	
Pending
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