MONITORING, EVALUATION AND RESEARCH PLAN 2014-2016

Monitoring and Research Plan 2014-2015

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount |
| MONITORING |  |  |  |  |
| Monitoring visits to various project sites | Ministry of Social Welfare, Gender and Children’s Affairs (MSWGCA), UN Agencies, CSO partners | 1/14-12/15 | N/Core TBM | $10,000 |
| RESEARCH |  |  |  |  |
| Research on Urban Women Poverty | FAO, Key government ministries, Department and Agencies | 3/14-12/15 | N/Core TBM | $10,000 |
| Research on Gender Interventions in 10 Ministries, Department and Agencies | Key Government Ministries, Departments and Agencies | 1/14-12/15 | Non-core: PBF | $ 35,000 |
| Collection of all missing baseline data for the SN and AWP as well as for all programmes. | Central Statistics, key government ministries, agencies and departments. | 1/14-12/15 | N/core TBM | $10,000 |

Evaluation Plan 2014-2016

| Evaluation name | Mandatory? (Yes) | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ MCO/ RO AWP Output | Office in charge | Region/ country | Joint activity (Yes indicate partners) | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |
| Evaluation 1: Evaluation of UN Women Sierra Leone’s contribution to EVD Response | Y | UNW SP Goal 4 Outcome 4 | Sierra Leone -AWP Output 4 |  | Sierra Leone | N | RCO/UNCT/GTT MSWGCA Donor Gender Reference Group NERC UNMEER | July-Sept 2015 | US$30,000 Core Funds | Pending |  |
| Evaluation 2: Mid-Term Evaluation of SLE programme on Women, leadership and political participation | Y | UNW SP Goal 1 Outcome 1 | Sierra Leone -AWP Output 1 Sierra Leone | Sierra Leone CO | Sierra Leone | Y | GNWP-SL MSWGCA WISSL MLGRD- ONS UN Women | May to July 2016 | US$30,000 Core Funds | Pending |  |
| Evaluation 3: 1325 NAP assessment/evaluation-2010-2014 | Y | Goal 4, Outcome 4 | Sierra Leone -AWP Output 4 | MSWGCA CO | Sierra Leone | Y | SLEFPAC CRC CSO APPWA MLGRD | Sept –November 2015 | US$30,000 Core Funds | Pending |  |

Please fill out a separate row for each evaluation.