MONITORING, EVALUATION AND RESEARCH PLAN 2021 - 2025

UN Women Bosnia and Herzegovina

- Monitoring and Research Plan 2021 - 2025

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount (USD) |
| MONITORING |  |  |  |  |
| DRF and OEEF – Quarterly monitoring of the AWP implementation in the RMS | IPs and other partners involved in the AWP implementation | Quarterly | Core and non-core | Staff input |
| Annual Reports | IPs and other partners involved in the AWP implementation | Annually – end year | Core and non-core | Staff input |
| UNSDCF 2021-2025 Annual Reports | UNCT, PMT, Gender Theme Group | Annually – end year | Core and non-core | Staff input |
| SN 2021 – 2025 Indicators Review and data collection | IPs and other partners involved in the SN 2021-2025 implementation | Bi-annually | Core and non-core | Staff input |
| RESEARCH |  |  |  |  |
| Gender Mainstreaming Guidance for line ministries (6 sectors to be determined) | Agency for Gender Equality, FBiH and RS Gender Centre, selected line ministries | January 2021 – June 2021 January 2022 – June 2022 | EU (non-core) | 100,000 |
| Behavioral insights: Women and Girls in STEM | UNICEF, UNDP, BiT Alliance, Ministries of Education, selected IT companies | Q1 2021 | Non-core | 40,000 |
| Country Gender Assessment: GENDER, AGRICULTURE AND RURAL DEVELOPMENT IN BOSNIA AND HERZEGOVINA | FAO, gender institutional mechanisms, Ministries of Agriculture | Q3 2019 – Q2 2021 | Core | 10,000 |
| System overview of the VAW protection and prevention in Bosnia and Herzegovina with focus on measurement and evaluation of results and recommendations for programming | Gender institutional mechanisms, Ministries of Interior, Ministries of Labor and Social Protection, Ministries of Justice, UNFPA, UK, USAID, SWE, EUD | Q3, Q4 2022 – Q1, Q2 2023 | Non-core | 41,000 |
| Assessment of available services and gaps, and prevention of VAW initiatives in BiH with focus on new area of work (e.g justice, women with disability) | Agency for Gender Equality, FBiH and RS Gender Centre, selected line ministries and CSOs | Q1, Q2, Q3 2023 | SWEDEN (non-core) | 20,000 |
| Country Gender Equality Profile | UNCT, government and CSO partners | First publication end 2020, annual review in the subsequent years | Non-core | 15,000 |
| Socio-economic position of Women in BiH | Economics Institute, Agency for Gender Equality, Ministry of Foreign Trade and Economic relations, CSOs | Q1 2021 | Non-core | 25,000 |
| Study on the resilience of women owned businesses | Economics Institute, Chambers of Commerce, Agency for Gender Equality, Ministry of Foreign Trade and Economic relations, CSOs, Women entrepreneurs associations | Q1 2021 | Non-core | 30,000 |
| Baseline Study on Care Economy | Economics Institute, Agency for Gender Equality | Q4 2021 – Q1 2022 | Non-core | 25,000 |
| Focus on Gender, a serial publication highlighting the work of UN Women BiH in various policy areas | N/A | Quarterly publishing | Non-core | 3.700 USD per year |

- Evaluation Plan 2021-2025

| Evaluation name | Mandatory? (Y/N) | UNSDCF Outcome/ UN Women SP Outcome and relevant SDGs | SN Output/Relevant flagship program | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Planned Dates (start-end) |  | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| GEF EU Final Evaluation | Y | Outcome 4 UNSDCF / Outcome 2 UN Women SP | BiH DRF Output 2.1 | BiH CO | BiH | N | Q1 2023 |  | 20,000 non-core | Pending |  |  |
| SWE Support to SN 2019-2022 Final Evaluation | Y | Across SN 2021 - 2025 | Across SN 2021 - 2025 | BiH CO | BiH | N | Q3 2023 |  | 30,000 non-core | Pending | Prerequisite for the continuation of the Sweden SN financing |  |
| SDG Financing Joint Programme Final Evaluation | Y | Goal 5, Outcome 2 | BiH DRF Output 2.1 | UNDP BiH | BiH | Y, UNDP, UNW, ILO, WHO, UNICEF, UNESCO | Q3 and Q4 2022 |  | 40,000 non-core | Pending |  |  |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |  |  |
| GRB Regional Project Final Evaluation | Y | Goal 5, Outcome 2 | BiH DRF Output 2.1 | ECA RO | ECA RO | N | October 2023 April 2024 |  | 40,000 non-core | Pending |  |  |
| EU EVAW regional program Final evaluation | Not for EC | Goal 5, Outcome 4 | RO AWP Outcome 3.1 | ECA RO | ECA + Albania, BiH, North Macedonia Montenegro, Kosovo, Serbia and Turkey | No | Q3 2023 |  | 80,000 non-core | Pending |  |  |
| UNSDCF 2021 – 2025 Final Evaluation | Y | All outcomes | n/a | RCO BIH | BIH | Y | Q1 and Q2 2025 |  | TBD | Pending |  |  |

UN Sustainable Development Cooperation Framework (UNSDCF), formerly known as UNDAF.

Outcomes contributing to the SDGs as per the Strategic Plan