MONITORING, EVALUATION AND RESEARCH PLAN (MERP) 2017-2021

Monitoring 2017-2021

| SN Impact/Outcome | Activity | Responsible staff member | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Source | Amount In USD |
| MONITORING |  |  |  |  |  |  |
| Mid-year reviews and annual reporting of UNDAF | PoC and RBM / Outcome Working Group review meeting | UNW staff | UNCT, Government Authorities | 2017-2012 (Annually) | no funding implications |  |
| Quarterly programme reviews and quarterly monitoring | Quarterly programme reviews conducted, quarterly monitoring exercise conducted of AWP in RMS to ensure substantive outputs are on track. | Focal point per Outputs in RMS | Internal staff | 2017 – 2021 (quarterly) | no funding implications |  |
| Programme monitoring visits | Programme monitoring visits are conducted routinely (includes UNTF and FGE monitoring) | UNW staff | as often as possible with partners; | 2017 – 2021 (bi-monthly) 2017-2019 2017-2019 2017 2018-2020 | Core Non-core Non-core – ADA EVAW – EU IPA Non-core FGE – ExB Non-core Social Inclusion | $10,000 $2,000 $3.700 $5,800 $4,000 $1,000 |
| Mid-term Review of the Strategic Note and preparation of new Strategic Note (late 2020) | Desk review, Interviews, Workshop | M&E Focal Point (support from RO Planning & Coordination Specialist) | Office staff, key donors, key partners, UNCT | 9/2019-12/2019 | Core | $7,500 |
| SN Impact area 2, Outcome 5.1 | CEDAW 5th periodic report | Programme Officer | MoFA, Council of Ministers, MHSP, line Ministries | 1/2019-7/2019 | non-core | $15,000 |

Research Plan 2017-2021

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount In USD |
| RESEARCH |  |  |  |  |
| Contribution to the Common Country Assessment | UNCT Albania | 2020 | Core | $15,000 |
| Gender Brief Albania | MHSP, INSTAT, line ministries | 6/2017-12/2017 | Non-core tbm | $35,000 |
| Public education financial survey | MoF, MHSP, | 1/2018-6/2018 | Non-core tbm | $40,000 |
| Annual Statistical Bulletins – Women and Men | INSTAT, MHSP, line Ministries | 10/2017 - 2019 | Non-core tbm | $15,000 |
| Technical papers on gender mainstreaming and EU acquis (ERP, NSDI, Tourism) | PMO, MHSP, Ministry of Economy, Finance and Labor and other line ministries l | 2017-2018 | EU and IPA funds | $8,000 |
| Baseline and end-line study for Albania under the regional EVAW project - Assessment of perceptions and attitudes in targeted communities before and after the implementation of the GenderLab | MHSP, Local CSO, MHSP, MoI, Local Government Units | 2017-2018 | EC funds | $30,000 |
| Baseline report on gender-responsive planning at local level in Albania “Planning for Equality at the local level” | Local Government Units, MOSWY | 2018 | ADA Funds | 3600 |
| Assessment of key international standards, including the Istanbul Convention as well as the existing normative standards in the Albanian legislation relevant to specialist services/centers for victims of sexual violence; | Ministry of Justice, Ministry of Health and Social Protection, Ministry of Interior, Albanian State Police | 2017-2018 | Non-core | 6000 |
| Follow-up study on availability and accessibility of support services for women and girls subjected to GBV | Local CSO, MHSP, MI, Local Government Units MHSP | 2019 | EC funds | $8,400 |
| Publication and dissemination of the National Study on Rural Women and Economic Diversification in Rural Areas | WEE | 2017 | Non-Core | $ 22,000 |
| National Study “Women in boards and Senior Positions in Albania” | NGO, private companies, Ministry of Economy and Finance | 2017 | Non-Core | 23,400 |
| Perception on Women Participation in Elections Index | National and International Experts | 2017 | Non-core | 19,500 |
| Political Parties financing and transparency and women career development opportunities Political Parties Statuses and Candidate Recruitment Processes | NGOs, national and international experts | 2017 | Non-Core | $25,600 |
| Women Empowerment Principles: National Gender Equality Index in Albanian Companies | NGO, private companies, Tirana Municipality | 2017 | Non-core | 12,800 |
| Study on freedom to vote and family voting | NGO, CEC, political parties, MPs | 2017-2018 | Non-core | 28,000 |

Evaluation Plan 2017-2021

| Evaluation name | Mandatory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ MCO/ RO AWP Output | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-end) | Budget (in US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |
| Thematic evaluation of Women’s Political Empowerment (SN Outcome 1) | N | SP Outcome 2 | Albania | Albania CO | ECA | N | CEC, MPs, CSOs, media | 2018 | $10,000 core | pending |  |
| Evaluating of the SN 2017-2021 | N | Impact Area 1, 2, 3, 5 | Albania | CO Albania | Albania | Involving stake-holders of impact areas | Government Civil society UNCT, Donors | 2020-2021 | $30,000 Core | pending |  |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |
| UNDAF (2017-2021) evaluation | Y | All Impact areas | ALB CO – OEEF Output 2.3 | Albania CO | Albania | Y (RCO, UN Agencies) | RCO, UNCT, Government, Donors, CSOs | 2020 | 30,000 core | Pending |  |
| Evaluation of the FGE project | Y | SP Outcome 1 | Albania | Albania – FGE grantee | ECA | N | FGE | 2018-2019 | $10,000 FGE | pending | Evaluation to be managed by the grantee |
| Evaluation of the GRB Regional project | Y | SP Outcome 2 | Albania | ECA RO | ECA | N | Government, donors, CSOs | 2018-2019 | $33,180 (ADA funds) | pending | Evaluation involves four countries in the region, under the GRB Regional project |
| Final evaluation of the regional EVAW Project | Y | SP Outcome 4 | RO | ECA RO | ECA | Y | Government, donors, CSOs | 2019 | $184,493 (EU funds) | Pending | Evaluation to be commissioned by the RO. The planned budget is not part of Albania CO budget. |
| Evaluation of Swedish Support to One UN in Albania for gender equality work 2012-2017 | N | UNDAF Outcome 2,3,4 | Albania | Albania CO | ECA | Y (Sida, RCO, UNDO, UNFPA, UNICEF, GTG) | UN Agencies, government, CSOs | 2017 | No funding implications | Completed | Evaluation commissioned by Sweden |

Please see Guidance on Decentralized Evaluations, link.

Please fill out a separate row for each evaluation.