UN WOMEN TURKEY OFFICE

- Evaluation Plan 2019-2022

| Evaluation name | Mandatory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome | SN Output /Relevant flagship program | Office in charge | Region/ country | Joint activity (Y/ N, indicate partner/s entities if YES) | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ complete) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by CO |  |  |  |  |  |  |  |  |  |  |  |
| Final evaluation of the programme “Gender Equality in Political Leadership and Participation in Turkey”. | Y | UNW SP IRRF Outcome 1 | SN Output 1 | Turkey PP | Turkey | N | Key partners in the implementation | 3rdQ 2020 | US$ 60,000 Non-core | Pending |  |
| Country Portfolio Evaluation | N | NA | NA | Turkey PP/ECARO | Turkey | NA | Implementing partners | 1st Q 2022 | TBD (estimated US$ 60,000 core) | Pending |  |
| Final evaluation of the programme “Implementing Gender - Responsive Planning and Budgeting in Turkey” | Y | UNW SP IRRF Outcome 1 | SN Output 1 FPI: “Transformative Financing for Gender Equality and Women's Empowerment”, | Turkey PP | Turkey | Ministry of Labour, Family and Social Policy | Implementing partners: line ministries, parliament, local authorities and civil society | 2nd Q 2021 | US$ 50,000 (non-core) | Pending |  |
| Evaluations where the CO will participate |  |  |  |  |  |  |  |  |  |  |  |
| Regional and multi-country evaluation of the MADAD project `Strengthening Resilience of Syrian Women and Girls` | Y | UNW SP IRRF Outcome 5 | SN Output 3 | UN Women ECA and AS ROs in collaboration with Turkey PP | Turkey, Iraq, Jordan | Y, to be co-managed between ROAS and ECARO | Donors, key partners in implementation (CSOs, national and local authorities) | 4th Q 2020 | 20,000 Non-core (Turkey component) | pending |  |
| Final evaluation of the programme “Ending violence against women in Western Balkans and Turkey: Implementing norms, changing minds” | Y | UN Women SP IRRF Outcome 4 | SN Output 2 | ECA RO | Albania, BiH, Kosovo, Macedonia Montenegro Serbia, Turkey | N | Selected National partners, and selected CSOs, academia, MPs and GRP Experts | 3rd-4th Q 2019 | US$ 169,259.72 (allocated programme budget) | initiated |  |
| Evaluation of the implementation of the Turkey UNDAF | Y | OEE output 1 |  | UN Turkey RC Office and UN Agencies | Turkey | Y, with support of ECARO | UNCT, government | Q1 of 2020 | TBD | TBD |  |
| Total for Evaluations |  |  |  |  |  |  |  |  | Core & non-core | $359,260 |  |