# Monitoring, Evaluation and research Plan 2015-2015

Monitoring and research Plan 2014-2015

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount |
| MONITORING |  |  |  |  |
| Conduct monitoring visits to partners receiving resources from UN Women and/or participate in partners activities for quality assurance. | Ministries of Environment, Women and Social Action, Planning and Development, High Institute for Public Administration, Eduardo Mondlane University, National Human Rights Commission Men for Change Network, District Government of Angónia- Tete and Gaza | Quarterly visits | Core Non-core | $16,170 $10,500 |
| Conduct spot checks to partners receiving resources from UN Women |  | Bi-annual |  |  |
| RESEARCH |  |  |  |  |
| Produce the first biennial report on the status of women in Mozambique |  | 2014 | Non-Core | $20,000 (TBM) |
| Produce a gender statistical handbook |  | 2015 | Non-core | $30,000 |
| Conduct a sudy on Violence against women and girls in Mozambique | Ministry of Women Affairs, Gender and Community Development, National Institute of Statistics | 2014 | Non-core | 500,000 (TBM) |

Evaluation Plan 2014-2015

| Evaluation name | Mandatory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ MCO/ RO AWP Output | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |
| Evaluation of the USA Funded E-VAW project | N | UNDAF 7.4, UN Women Outcome 3. | Output 3.1.1 | Mozambique | Mozambique | Y | Men for Change Network, Mozambican association of Women survivors of Violence, Associação Coalizão Juvenil and Feminist Movement of Mozambique | 3 rd quarter 2013 | $6,300 – Non-core | Not started | 3% of $210,000 |
| Evaluation of UNiTE Campaign activities implemented from 2012 to 2013. | N | UNDAF 8, UN Women Outcome. | Output 2.1 | Mozambique | Mozambique | Y | Men for Change Network, Horizonte Azul, Coalizao, MMAS | 2nd quarter 2014 (April) | $5,000 – Non-core $1.437 (TBM) | Not started | 3% of $118.785 ($3.563) 2-day evaluation missions carried out in 2 provinces (1 Maputo /Gaza). In partnership with partners with presence in the field. |
| Evaluation of UN Womens Support to MICOA | N | UNDAF 3, UN Women Outcome. | Output 3.1 | Mozambique | Mozambique | Y | MICOA | 2nd quarter 2014 (May) | $10.650 | Not started | (3% of $355.000) Including day missions to Matutuine and Mafuiane. |
| Evaluation name | Mandatory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ MCO/ RO AWP Output | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |
| Evaluation 1: Evaluation of UNDAF UNDAF 2012-2015 (to be confirmed) | No | UNDAF Outcomes 1, 3, 7 and 8; UN Women Outcomes 1, 2, 3 , 4 and 5. | All Outputs | RCO | Mozambique | Yes | All Partners and Stakeholders | 3th quarter 2012 | NA | NA | Date to be established |

Annex 2: Evaluation Justification Matrix

| List of selected evaluation | Criteria used for the selection | Potential evaluability | Intended use of evaluation findings |
| --- | --- | --- | --- |
| Evaluation of the USA Funded E-VAW project | The intervention has potential for replication and scalling up. | High | Validate the potential impact and replicability of the approach to mobilize young boys and girls as well as community and opinion leaders to act as truly agents of change in the fight to VAW. |
| Evaluation of UNiTE Campaign activities implemented from 2012 to 2013. | The UNiTE Campaign’s visibility was significally boosted with the visit of the SG in May 2013. Also this represents the largest portion of funding and huma resources investment of all UN Women’s interventions in Mozambique. | High | The findings of the evaluation will help to redesign the campaign’s work methodology in a more cost effective and sustainable manner. Seven (7) locations have benefited from the UNiTE Campaign training since 2012, due to limited resources and an attempt to increase effectiveness it is important to assess the immediate results of the interventions. |
| Evaluation of UN Women’s Support to MICOA | Relatively significant investment in the past 3 years and lack of funding to continue support. | High | Inform decision making on the most appropriate type and level of support to the Ministry of Coordination of Environment in the future. |
| Evaluation of the CO Programme | Advised | High | Inform CO work for the following period – 2016-2020 aligned with UNDAF. |
| Evaluation of UNDAF UNDAF 2012-2015 (to be confirmed) | Mandatory |  | Inform CO work for the following cycle 2016-2020. |

Once the funding from Finland comes through.

Joint  UN Value Chain Project

Once the funding from Belgium comes through

3% of total Core

Additional non-core to be established upon confirmation of annualbudgets based on ongoing negotiations with donors.

Idem

Project Title: Consolidation of a Replicable Model of Partnership Based Engagement between Youngsters in Schools and Community Leaders and Community and  Opinion Leaders to accelerate the Prevention of Violence against Women and Girls in the Context of the UNiTE Campaign

Project Title: Consolidation of a Replicable Model of Partnership Based Engagement between Youngsters in Schools and Community Leaders and Community and  Opinion Leaders to accelerate the Prevention of Violence against Women and Girls in the Context of the UNiTE Campaign