KYRGYZSTAN CO – MONITORING, EVALUATION AND RESEARCH PLAN (MERP) 2018-2022

NOTE: Examples have been included below to illustrate how to complete each column; they are not meant to be accurate to real life activities. Remember that MERP has to be linked with many of the outputs and activities planned for in the OEEF.

Monitoring 2018-2022

| SN Impact/Outcome | Activity | Responsible staff member | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Source | Amount |
| MONITORING |  |  |  |  |  |  |
| Quarterly monitoring of activities | Update RMS | Focal point per Output in RMS | Internal staff | 1/2018-12-2022 | n/a | n/a |
| Outcome 1. Women and men, especially youth, value social norms supporting gender equality and women’s empowerment at individual and community levels | Omnibus survey on perception indicators | M&E focal point | Internal staff | 1/2018-12-2022 | Core | $1000 |
| Mid-term review of SN | Survey, Desk review, Workshop | Representative & M&E focal point (support from RO Planning & Coordination Specialist) | Office staff, beneficiaries, government and other state institutions, civil society, UN system, key donors and development partners | 8/2019-11/2019 | Core | $30,000 |
| UNCT-SWAP Gender Scorecard | Survey, Desk review, Workshop | Representative & National Programme Officer | Un system | TBC | Core | TBC |
| FGE project monitoring | Update RMS | Focal point for the project | Internal staff, partners | TBC | n/a | n/a |

Research Plan 2018-2022

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount |
| RESEARCH |  |  |  |  |
| Research on women’s roles in preventing, promotion and participation in violent extremism | UN System, Academia | 1/2018-12/2018 | Non-core | $80,000 |
| Audience research for BCC strategy | UNCG, academia, media development NGOs and media outlets | 2/2018, 2/2019, 2/2020, 2/2021 | TBC | TBC |

Evaluation Plan 2018-2022

| Evaluation name | Mandatory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ MCO/ RO AWP Output | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |
| Evaluation 1 Final evaluation of the ‘Livelihoods through participation and equal access to water’ | Y | UNDAF Outcome 2 / UN Women SP Output 11 / SN Outcome 1 | TBC | Kyrgyzstan CO | Kyrgyzstan | N | Ministry of Labour and Social Development, district administrations, partner municipalities, water users associations | January – March 2018 | US$20,000, non-core funds | Pending |  |
| Evaluation 2 Country Portfolio Evaluation | Y | UNDAF Outcome 2 / UN Women SP Outputs 11 and 5 / SN Outcomes 1 and 2 | TBC | Kyrgyzstan CO | Kyrgyzstan | N | Civil society partners, Government and State Agencies, Parliament, Beneficiaries, UN system, Donors and Development Partners | November 2021-April 2022 | TBC | Pending |  |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |
| Evaluation 1 Evaluation of the Joint UN Programme on Prevention of Violent Extremism | Y | UNDAF Outcome 2 / UN Women SP Outputs 11 and 5 / SN Outcomes 1 and 2 | TBC | UNDP and UNICEF CO | Kyrgyzstan | Y | UN System, Government, Civil society, Development partners and Media | January 2020-April 2020 | TBC | Pending |  |
| Evaluation 2 UNDAF Final evaluation | Y | UNDAF Outcomes 1-4 / UN Women SP Outputs 11 and 5 / SN Outcomes 1 and 2 | TBC | RCO | Kyrgyzstan | Y | UN System, UN System, Government, Civil society and Development partners | December 2020-June 2021 | TBC | Pending |  |

Please see Guidance on Decentralized Evaluations, link.

Please fill out a separate row for each evaluation.