KYRGYZSTAN CO – MONITORING, EVALUATION AND RESEARCH PLAN (MERP) 2018-2022 
NOTE: Examples have been included below to illustrate how to complete each column; they are not meant to be accurate to real life activities. Remember that MERP has to be linked with many of the outputs and activities planned for in the OEEF. 


Monitoring 2018-2022

	SN Impact/Outcome
	Activity
	Responsible staff member
	Partners and stakeholders 
	Planned Dates (Month and year of start and end)
	Budget

	
	
	
	
	
	Source
	Amount

	MONITORING

	Quarterly monitoring of activities
	Update RMS
	Focal point per Output in RMS
	Internal staff
	1/2018-12-2022
	n/a
	n/a

	Outcome 1. Women and men, especially youth, value social norms supporting gender equality and women’s empowerment at individual and community levels
	Omnibus survey on perception indicators
	M&E focal point
	Internal staff
	1/2018-12-2022
	Core
	$1000

	Mid-term review of SN
	Survey, Desk review, Workshop
	Representative & M&E focal point (support from RO Planning & Coordination Specialist)
	Office staff, beneficiaries, government and other state institutions, civil society, UN system, key donors and development partners
	8/2019-11/2019
	Core
	$30,000

	UNCT-SWAP Gender Scorecard
	Survey, Desk review, Workshop
	Representative & National Programme Officer
	Un system
	TBC
	Core
	TBC

	FGE project monitoring 
	Update RMS
	Focal point for the project
	Internal staff, partners
	TBC
	n/a
	n/a




Research Plan 2018-2022

	Activity
	Partners and stakeholders 
	Planned Dates (Month and year of start and end)
	Budget

	
	
	
	Source
	Amount

	RESEARCH

	Research on women’s roles in preventing, promotion and participation in violent extremism
	UN System, Academia
	1/2018-12/2018
	Non-core
	$80,000

	Audience research for BCC strategy 
	UNCG, academia, media development NGOs and media outlets
	2/2018, 2/2019, 2/2020, 2/2021 
	TBC
	TBC




Evaluation Plan 2018-2022[footnoteRef:1] [footnoteRef:2] [1:  Please see Guidance on Decentralized Evaluations, link.]  [2:  Please fill out a separate row for each evaluation.  ] 

	Evaluation name
	Mandatory?
(Y/N)
	UNDAF Outcome/ UN Women SP Goal, Outcome  
	Country/ MCO/ RO AWP Output
	Office in charge
	Region/ country
	Joint activity 
(Y/ N, indicate partners)
	Key Stakeholders
	Planned Dates 
(start-end)
	Budget (US$) / Sources of Funding
	Status (pending/ initiated/ ongoing/ completed)
	Remarks

	Evaluations managed by the office
	

	Evaluation 1 Final evaluation of the ‘Livelihoods through participation and equal access to water’ 
	 Y
	UNDAF Outcome 2 / UN Women SP Output 11 / SN Outcome 1
	TBC
	Kyrgyzstan CO
	Kyrgyzstan
	N
	Ministry of Labour and Social Development, district administrations, partner
municipalities, water users associations
	January – March 2018

	US$20,000, non-core funds
	Pending
	

	Evaluation 2
Country Portfolio Evaluation
	Y
	UNDAF Outcome 2 / UN Women SP Outputs 11 and 5 / SN Outcomes 1 and 2
	TBC
	Kyrgyzstan CO
	Kyrgyzstan
	N
	Civil society partners, Government and State Agencies, Parliament, Beneficiaries, UN system, Donors and Development Partners
	November  2021-April 2022
	TBC
	Pending
	

	
	
	
	
	
	
	
	
	
	
	
	

	Evaluations in which the office participates
	

	Evaluation 1 
Evaluation of the Joint UN Programme on Prevention of Violent Extremism

	Y
	UNDAF Outcome 2 / UN Women SP Outputs 11 and 5 / SN Outcomes 1 and 2
	TBC
	UNDP and UNICEF CO
	Kyrgyzstan
	Y
	UN System, Government, Civil society, Development partners and Media
	January 2020-April 2020

	TBC
	Pending
	

	Evaluation 2 UNDAF Final evaluation
	Y
	UNDAF Outcomes 1-4 / UN Women SP Outputs 11 and 5 / SN Outcomes 1 and 2
	TBC
	RCO
	Kyrgyzstan
	Y
	UN System, UN System, Government, Civil society and Development partners 
	December 2020-June 2021
	TBC
	Pending
	




