MONITORING, EVALUATION AND RESEARCH PLAN (MERP) 2015-2020 (attachment to AWP 2020)

Monitoring 2015-2020

| SN Impact/Outcome | Activity | Responsible staff member | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Source | Amount |
| MONITORING |  |  |  |  |  |  |
| OEEF | Mid-term review of SN 2015-2019 | Amna Muharemovic | Selected partners | 2017-completed | Core | $ 10,000 |
| OEEF | UNDAF 2015-2019 final review | Amna Muharemovic | All key partners and stakeholders | 2019 | Core | $11,000 |
| IA 2 to 5 | Baseline data collection and analysis for DRF | Project Managers | Selected partners | Annually – mid year | n/a | n/a |
| IA 2 to 5 | Collection and analysis on monitoring data on outcomes and outputs for DRF | Project Managers | Key partners | Once a year prior to annual reporting | n/a | n/a |
| OEEF | Annual review of Annual Work Plan | Amna Muharemovic | n/a | Once a year mid-term | n/a | n/a |
| OEEF | Preparation of Annual Report | Amna Muharemovic | Selected partners | Annually – end year | n/a | n/a |
| OEEF | Quarterly monitoring of AWP in RMS | Amna Muharemovic | n/a | Quarterly | n/a | n/a |

Research Plan 2015-2020

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount |
| RESEARCH |  |  |  |  |
| Research on Masculinities and Community Values (qualitative research finalized as of March 2016, awaiting for the drafting of a report) | Gender mechanisms, public authorities and civil society | September 2014 – January 2017 To be published | CRSV project | $ 9,026.85 |
| Research on costing of violence | Indepent researchers, Gender Mechanisms, safe network organisations, relevant ministries | September 2016-September 2018 | EVAW SIDA project | $30,000 |
| Gender Brief for Bosnia and Herzegovina (analysis of the gender equality situation in the country and development of recommendations based on the EU Gender Action Plan II | Gender Mechanisms, European Union Delegation to Bosnia and Herzegovina | November 2017 – March 2018 | Core | $ 30,000 |
| Ground breaking research on preventing radicalization in BiH | Independent researcher | July 2018-July 2019 | Core | $ 26,000 |
| Baseline study/data collection on attitudes and perceptions towards violence against women | CSO selected through competitive process, gender mechanisms, civil society organizations | December 2017 - completed | EVAW EU Project | $ 10,000 |
| Analysis of access to DV and EVAW protection services by marginalized groups of women in BiH | Independent researcher, local service providers, groups of marginalized women | June-September 2018 - completed | EVAW EU project | $ 3,500 |
| Country profile evaluation | Gender mechanisms, public authorities and civil society | Q3 2019 - Completed | Core | $ 6,500 |
| Behavioral insights research into women’s and girls’ decision-making when it comes to education and careers in ICT/STEM | Promente social research UN Women Gender innovation HQ | Q3-4 2019 Q1 2020 | Core | $ 50,000 |
| Research into IT companies’ HR recruitment and management practices | Independent researcher/company | Q1-2 2020 | IT Girls project, UN -UN Agreement with UNICEF | $ 20,000 |

Evaluation Plan 2015-2020

| Evaluation name | Mandatory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ MCO/ RO AWP Output | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |
| Evaluation of SN 2015-2019 | Y | UN Women SP OEEF Output 3 | BiH CO SP OEEF Output 3 | UNW BiH CO | BiH | N | n/a | 2020 | $ 35,000 | Pending |  |
| Project: Standards and Engagement for EVAW in BIH | Y | UNDAF Outcome 13 | Output 3.2.1 Output 3.3.1 | UNW BIH | BIH | Y | Gender mechanisms, local municipality, CSO’s | 2019 | $ 45,000 0. | Completed | Resource mobilization vis-à-vis SIDA ongoing (by UNW BiH) |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |
| Evaluation of UN Women’s contribution to GRB initiatives in the Europe and Central Asia Region | Y | n/a | Impact Area 5 SN (2015-2019) | ECA RO | ECA | Y | Gender mechanisms, Ministries of Finance, selected municipalities, CSOs | 2016 | TBD | Completed |  |
| UNDAF 2015-2019 Final evaluation | Y | n/a | Output 1.1 | RC BiH | BiH | Y | Government and partners | 2019 | $ 11,000 | Compled |  |
| Regional Project: Implementing Norms, Changing Minds (in EVAW) | Y | UNDAF Outcome 13 | Output 3.2.1 | RO ECA | ALB, BIH, Kosovo, FYROM, Monte negro, Serbia and Turkey | Y | Gender mechanisms, line ministries, local governments, CSO’s | 2019 | $ 0,00 | Initiated | Resource mobilization vis-à-vis EU ongoing (by ECA) |
| Evaluation of GRB Phase III Project | Y | SP Outcome 2 | Output 1.1.2 | EO ECA | ALB, BIH, Republic of Northern Macedonia | Y | Gender mechanisms, line ministries, local governments, CSO’s | 2018 | $ 0,00 | Completed | Funded by Regional project |

Please see Guidance on Decentralized Evaluations, link.

Please fill out a separate row for each evaluation.