MONITORING, EVALUATION AND RESEARCH PLAN (MERP) 2017 – Viet Nam Country Office

Monitoring 2017

| SN Impact/Outcome | Activity | Responsible staff member | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Source | Amount |
| MONITORING |  |  |  |  |  |  |
| All SN Impact areas | Regular monitoring through field visit and/or quarterly meetings with partners to review progress against monitoring indicators | All Programme managers | All implementing partners |  | Core and Non-core | 3500 |
|  | Quarterly update of the MERP plan | Vu Phuong Ly – Programme Specialist |  | April, July, Oct and December 2017 |  | No cost |
| SN Impact area 2, VCO Outcome 2.1 | Baseline study on Safe Cities Programme | Le Thi Lan Phuong, National Consultant and Thuy Nguyen, Programe Analyst | HCMC PPC | May-Aug 2017 | Core | 15,000 |
| SN Impact area 2, VCO Outcome 2.2 | Follow up survey with trainees three months after SASA training on knowledge that has been applied. | Le Thi Lan Phuong, National Consultant | Da Nang Women’s Union | June 2017 Apr 2017 | Non-core Non-core | no cost 1,000 |
| Impact Area 3 (VCO Outcome 2.1) | Conduct baseline data for ESP in Viet Nam | Thuy Nguyen, Programe Analyst | MOLISA | June– Dec. 2017 | Non-core | 30,000 |

Research Plan 2017

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount |
| RESEARCH |  |  |  |  |
| Formative research to identify barriers and enablers for behavioral change related to maternal nutrition care among ethnic minority women in nutritionally vulnerable regions | IFGS | Feb – June 2017 | Non-core | 30,000 |
| Perception survey on women’s belief in accessing to justice | MOJ | Jan-March, 2017 | Non-core | 30,000 |
| Review of 10 years of implementation of the Gender Equality Law to identify areas for revision | MOLISA | March – Dec.2017 | Non-core | 30,000 |

Evaluation Plan 2017

| Evaluation name | Mandatory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ MCO/ RO AWP Output | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |
| Final Evaluation of the project on Strengthening women's capacity in disaster risk reduction to cope with climate change | Y | SP Impact area 1, Outcome 1.1 | Country Office | Viet Nam VCO | Viet Nam | Y | Viet Nam Women's Union | Dec 2016- April 2017 | 41,300 (Total budget evaluation is 57,000 USD, in which 15,700 was spent in 2016) Non-core |  |  |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |