MONITORING, EVALUATION AND RESEARCH PLAN 2015

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount |
| MONITORING |  |  |  |  |
| Monitoring of Women Protection Centers/Family Guidance Centers supported by UN Women (including third party monitoring) | MoWA, DoWAs, CS partners | 1-12/15 | Non-Core | 180,000 |
| 3rd party auditing of WPC/FGC supported by UN Women (External and DIM audits) | MoWA, DoWAs, CS partners | 1-12/15 | Non-Core | 100,000 |
| Monitoring of the ICT Centers | PEEP Team and DoWAs | Semi-annually | Non-Core | 10,000 |
| Capacity assessment of government institutions on gender responsive budgeting, planning and reporting (based on mapping done with UNDP to avoid duplication) | MOWA and CSO | by end 2015 | Non-core | 50,000 |

| RESEARCH |  |  |  |  |
| --- | --- | --- | --- | --- |
| KAP survey on women’s economic rights | DoWAs, MoWA, MRRD, PRRDDs | Late 2015 Pre study By 12/17 Post study | Non-Core | 100,000 |
| KAP survey on social protection (as part of the GBV referral system) | UNFPA, WHO, MoWA, MoLSA, MoJ, MoI, MoPH EVAW Commissions, CS partners etc. | 09/2015 Pre study By 12/17 Post study | Non- Core | 70,000 |
| KAP survey in Herat to identify the causes of VAW/G | Herat Governor Office, DoWAs, MoWA | 09-12 2015 | None Core | 35,000 |
| Scoping Study of Safe Markets | UN agencies, Municipality in relevant areas | Late 2015 | Non-Core | 50,000 |

Evaluation Plan 2015

| Evaluation name | Manda-tory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ MCO/ RO AWP Output | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |
| Evaluation of EVAW Special Fund | Y | UNDAF 1: SP Goal 3: Outcome 3.1: | Outputs 3.1.1, 3.1.2, 3.1.3, 3.1.4, 3.1.5 | ACO | Afghani-stan | N | MoWA, DOWAs, EVAW SF Advisory board, CS | 12/13-3/14 | 55,000 | Completed in April 2015 |  |
| Evaluations in which the office participates: EVAW SF evaluation completed by April 2015 |  |  |  |  |  |  |  |  |  |  |  |

Abbreviations:

AWN		Afghan Women’s Network

CSE		Civil Society Exchange

DoWA		Department of Women’s Affairs

FGC		Family Guidance Center

GoIRA	  	Government of Islamic Republic of Afghanistan

MoWA	              Ministry of Women’s Affairs

MRRD		Ministry of Rural Rehabilitation and Development

WPC		Women’s Protection Center

Afghanistan’s current UNDAF 2009-13 was extended for another year through 2014. UNDAF 2015-2019 is under negotiation with the new government and outcomes are not finalized yet. Therefore this MER plan refers to outcomes of the current UNDAF.