MONITORING, EVALUATION AND RESEARCH PLAN 2015

	Activity 
	Partners and stakeholders 
	Planned Dates (Month and year of start and end)
	Budget

	
	
	
	Source
	Amount

	MONITORING

	Monitoring of Women Protection Centers/Family Guidance Centers supported by UN Women (including third party monitoring)
	MoWA, DoWAs, CS partners
	1-12/15 
	Non-Core 
	180,000


	3rd party auditing of WPC/FGC supported by UN Women (External and DIM audits)
	MoWA, DoWAs, CS partners
	1-12/15
	Non-Core

	100,000


	Monitoring of the ICT Centers
	PEEP Team and DoWAs
	Semi-annually
	Non-Core
	10,000

	Capacity assessment of government institutions on gender responsive budgeting, planning and reporting (based on mapping done with UNDP to avoid duplication)
	MOWA and CSO
	by end 2015
	Non-core
	50,000




	RESEARCH

	KAP survey on women’s economic rights
	DoWAs, MoWA, MRRD, PRRDDs
	Late 2015 Pre study
By 12/17 Post study
	Non-Core
	100,000

	KAP survey on social protection (as part of the GBV referral system)
	UNFPA, WHO, MoWA, MoLSA, MoJ, MoI, MoPH EVAW Commissions, CS partners etc.
	09/2015 Pre study
By 12/17 Post study
	Non- Core
	70,000

	KAP survey in Herat to identify the causes of VAW/G 
	Herat Governor Office, DoWAs, MoWA
	09-12 2015
	None Core
	35,000

	Scoping Study of Safe Markets
	UN agencies, Municipality in relevant areas
	Late 2015
	Non-Core
	50,000


		


Evaluation Plan 2015
	Evaluation name
	Manda-tory?
(Y/N)
	UNDAF [footnoteRef:1]Outcome/ UN Women SP Goal, Outcome   [1:  Afghanistan’s current UNDAF 2009-13 was extended for another year through 2014. UNDAF 2015-2019 is under negotiation with the new government and outcomes are not finalized yet. Therefore this MER plan refers to outcomes of the current UNDAF.] 

	Country/ MCO/ RO AWP Output
	Office in charge
	Region/ country
	Joint activity 
(Y/ N, indicate partners)
	Key Stakeholders
	Planned Dates 
(start-end)
	Budget (US$) / Sources of Funding
	Status (pending/ initiated/ ongoing/ completed)
	Remarks

	Evaluations managed by the office
	

	Evaluation of EVAW Special Fund
	Y
	UNDAF 1: 
SP Goal 3: Outcome 3.1:  
	Outputs 3.1.1, 3.1.2, 3.1.3, 3.1.4, 3.1.5
	ACO
	Afghani-stan
	N
	MoWA, DOWAs, EVAW SF Advisory board, CS
	12/13-3/14


	55,000



	Completed in April 2015
	

	Evaluations in which the office participates: EVAW SF evaluation completed by April 2015
	



Abbreviations:
AWN		Afghan Women’s Network
CSE		Civil Society Exchange
DoWA		Department of Women’s Affairs
FGC		Family Guidance Center	
GoIRA	  	Government of Islamic Republic of Afghanistan
MoWA	              Ministry of Women’s Affairs
MRRD		Ministry of Rural Rehabilitation and Development
WPC		Women’s Protection Center	

