Mozambique County Office – AWP 2017

MONITORING, EVALUATION AND RESEARCH PLAN (MERP) 2017-2018

Monitoring 2017

| SN Impact/Outcome | Activity | Responsible staff member |  | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Source | Amount |
| MONITORING |  |  |  |  |  |  |
| SN Impact Areas 2-3-5 & OEEF Output Cluster 2: Quarterly monitoring of activities | Implement the CO Performance Monitoring Framework/TOC for all programme areas, produce quarterly and annual reports, conduct quarterly and annual CO AWP monitoring in RMS and donor monitoring and reporting | KM&MEO and programme staff | All programme partners and stakeholders | Quarterly | Non-Core | $113.509 |
| SN Outcomes 2-3-5: Quarterly monitoring of activities and OEEF Output Cluster 2 (Quarterly monitoring of activities) | Conduct monitoring/field visits to programme activities and/or participate in partner’s activities for quality assurance and document project impacts | KM&MEO | Internal Staff | Quarterly | Non-Core | $54,000 |
| OEEF Output Cluster 1/Outputs 1.1: To drive more effective and efficient United Nations system coordination and strategic partnerships on gender equality and women’s empowerment | UNDAF Annual Review related to Outcome 4 | Programme Specialist | Internal Staff | End of year | Non-Core | $6,228 |
| Total |  |  |  |  |  | $173,737 |

Research Plan 2017

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget (all reflected in the DRF) |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount |
| RESEARCH |  |  |  |  |
| Carry out survey on Violence against women and girls in Mozambique (partial contribution) | Ministry of Women’s Affairs, National Institute for Statistic, UEM | 3/2017-8/2017 | Non-core (TBM) | 100,000 |
| Assessment of the status and cost of gender gap in agriculture in Mozambique (Activity 5.1.1.e) | UNEP/UNDP PEI, MGCAS, Ministry of Agriculture, MTADER, OMR | 6/2017-12/2017 | Non-core (Avail) | 48,500 |
|  |  |  | Non-core (TBM) | 140,650 |
| Total research |  |  |  | 298.150 |

Evaluation Plan 2017

| Evaluation name | Mandatory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ AWP Output | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |

MONITORING, EVALUATION AND RESEARCH PLAN (MERP) 2019

Monitoring 2019

| SN Impact/Outcome | Activity | Responsible staff member | Partners and Stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Source | Amount |
| MONITORING |  |  |  |  |  |  |
| Impact 3/SP Outcome 4 : All women and girls live a life free from all forms of violence | 3.1.1.18 Direct Project Management Cost (salary and M&E quality assurance, monitoring and documentation and SSA for HeForShe Consultant) | EVAW & PMERKM Officers | Responsible Partners | Continuously during the year | Non Core - TBM | $9.900,00 |
| Impact 6/SP Outcome 1 : A comprehensive and dynamic set of global norms, policies and standards on gender equality and the empowerment of all women and girls is strengthened and implemented | 6.1.2.19 Coordinate and monitor the implementation and reporting of National Action Plans (NAP 1325, Advancement of women, Prevention of gender-based violence) , central, provincial and district level (7 provinces and 13 districts) | WPS Programme & PMERKM Officers | MGCAS & Responsible partners | 3rd and 4th quarter 2019 | Non Core - Available | $75.000,00 |
|  | 6.1.2.33. Organize annual joint monitoring field visit, annual project review of the technical advisory group and a final national project meeting | Programme Manager, WPS Programme & PMERKM Officers | MGCAS, Iceland, Norway & Members of the WPS Technical and Advisory Group | 4th Quarter 2019 | Non Core - Available | $10.000,00 |
| Impact 2/Outcome 2: Women have income security, decent work and economic autonomy | 2.1.4.10. Regular Monitoring and Quality Assurance | Programme Manager, WEE Programme & PMERKM Officers | Responsible Partners | Continuously | Non Core - Available | $44.265,00 |
| Impact 4/Outcome 5: Women and girls contribute and have greater influence in building sustainable peace and resilience, and benefit equally from the prevention of natural disasters and conflicts and from humanitarian action. | 4.1.1.18 Conduct project monitoring activities | Programme Manager, WPS Programme & PMERKM Officers | MGCAS, Iceland & Norway and members of the WPS Technical and Advisory Group | Continuously | Non-Core Available | $44.483,00 |
| OUTPUT CLUSTER 1To drive more effective and efficient United Nations system coordination and strategic partnerships on gender equality and women’s empowerment | 1.1.6. Coordinate planning, implementation, monitoring and report on UNDAF Outcome 4 (e.g. planning retreat) | Programme Manager & PMERKM Officer | UNFPA, UNICEF, IOM, WHO, WFP, FAO, UNAIDS, UNDP, | Continuously during the year | Core | $6.500,00 |
| OUTPUT CLUSTER 2 To institutionalize a strong culture of results-based management, reporting, knowledge management and evaluation | 2.1.13. Undertake joint (programme and operations) monitoring field visits and spot checks in accordance to POM/Cash advance policy, particularly in areas where IPs are involved, as well as strengthen development results and impact monitoring (costs covered under DRF monitoring) | Country Representative, Programme Manager & Operations Staff | All IPs | Continuously during the year | Core | Staff time |
|  | 2.1.14. Produce quarterly and annual reports, conduct quarterly and annual CO AWP monitoring in RMS | PMERKM and Programme Officers |  | Quarterly December 2019 | No Cost Implication | Staff time |
|  | 2.1.15. Conduct the mid-term review of the CO's SN 2016-2020 | PMERKM & Programme Manager |  | 3rd quarter to 4th quarter | Core | $35.000,00 |
| OUTPUT CLUSTER 3 To enhance organizational effectiveness, with a focus on robust capacity and efficiency at country and provincial levels | 3.1.10. Organize staff planning and review retreats, team building sessions and annual planning , review meeting with partners and participation in regional and global retreats | Country Representative, programme Manager & M&EKM officer |  | 1st and 4th quarter | Core | $31.000,00 |
|  | 3.3.15. Monitor delivery on a monthly basis and follow up on off track areas | Operations Manager & Programme Manager |  | Montly during the year | No Cost Implication | Staff time |
| Total |  |  |  |  |  | $256.148,00 |

RESEARCH PLAN 2019

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget (all reflected in the DRF) |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount |
| RESEARCH |  |  |  |  |
| 6.1.1.2. Assess the institutional and technical capacity of national gender machinery (MGCAS and sectors) and National Statistical Institute for systematic production, use and dissemination of gender statistics, for policy-making and monitoring of national and international commitments (including SDGs) and develop a strategy and action plan to address the identified gaps | Ministry of Gender, Children and Social Action and the National Statistic Institute | February to May 2019 | Core | $10.000,00 |
| 2.1.1.19. Conduct "Mozambique Women in Business Outlook" - mapping women in formal and informal business, market share, best practices of growth, opportunities and challenges for market access to facilitate narrowing gender gap on procurement and increase access to better market | Ministry of Agriculture and Food Security and the Ministry of Land and Rural Development | February to Sept 2019 | Core | $11.000,00 |
| 2.1.4.8. Conduct a demand and market analysis to identify opportunities and challenges including policy related ones to the economic empowerment of girls and young women in Zambezia. | UNFPA, UNICEF, Provincial Department of Youth and Sports, District Governments, DFID | Jan to Feb 2019 | Non Core - Available | $12.000,00 |
| 2.2.6. … 2017 & 2018 Annual report |  |  | Core | 1.000,00 |
| 4.1.3.4. Conduct research and academic debates on topics related to WPS | UEM | April-December 2019 | Non Core - Available | $28.600,00 |
| 2.2.13. Assess perception of CO in country by carrying out a survey among stakeholders, partners and actors | Operations Manager | April-Jun 2019 | No Cost Implication | 0.00 |
| Total research |  |  |  | $62.600,00 |

Evaluation Plan 2019

| Evaluation name | Mandatory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ AWP Output | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) |  | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1.1.21. WPS Mid-Term Evaluation | Yes | SP Outcome 5 : Women and girls contribute and have greater influence in building sustainable peace and resilience, and benefit equally from the prevention of natural disasters and conflicts and from humanitarian action. | 4.1.1Women and girls capacity to participate meaningfully in conflict/prevention and resolution strengthened | Mozambique | ESA | N | MGCAS, Iceland, Norway, WPS Technical and Advisory Group and IPs |  | April 2019 to Sept | Non Core – Available ($65.500.00) |  | Project mid-term evaluation planned in signedproject document |
|  |  |  |  |  |  |  |  |  |  | $48.474.00 |  | Cost of salary of CO M&E Officer |
| Total Evaluation |  |  |  |  |  |  |  |  |  | $113.974.00 |  |  |

Please see Guidance on Decentralized Evaluations, link.

Please fill out a separate row for each evaluation.

Please see Guidance on Decentralized Evaluations, link.

Please fill out a separate row for each evaluation.