Mozambique County Office – AWP 2017

MONITORING, EVALUATION AND RESEARCH PLAN (MERP) 2017-2018

Monitoring 2017

| SN Impact/Outcome | Activity | Responsible staff member |  | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Source | Amount |
| MONITORING |  |  |  |  |  |  |
| SN Impact Areas 2-3-5 & OEEF Output Cluster 2: Quarterly monitoring of activities | Implement the CO Performance Monitoring Framework/TOC for all programme areas, produce quarterly and annual reports, conduct quarterly and annual CO AWP monitoring in RMS and donor monitoring and reporting | KM&MEO and programme staff | All programme partners and stakeholders | Quarterly | Non-Core | $113.509 |
| SN Outcomes 2-3-5: Quarterly monitoring of activities and OEEF Output Cluster 2 (Quarterly monitoring of activities) | Conduct monitoring/field visits to programme activities and/or participate in partner’s activities for quality assurance and document project impacts | KM&MEO | Internal Staff | Quarterly | Non-Core | $54,000 |
| OEEF Output Cluster 1/Outputs 1.1: To drive more effective and efficient United Nations system coordination and strategic partnerships on gender equality and women’s empowerment | UNDAF Annual Review related to Outcome 4 | Programme Specialist | Internal Staff | End of year | Non-Core | $6,228 |
| Total |  |  |  |  |  | $173,737 |

Research Plan 2017

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget (all reflected in the DRF) |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount |
| RESEARCH |  |  |  |  |
| Carry out survey on Violence against women and girls in Mozambique (partial contribution) | Ministry of Women’s Affairs, National Institute for Statistic, UEM | 3/2017-8/2017 | Non-core (TBM) | 100,000 |
| Assessment of the status and cost of gender gap in agriculture in Mozambique (Activity 5.1.1.e) | UNEP/UNDP PEI, MGCAS, Ministry of Agriculture, MTADER, OMR | 6/2017-12/2017 | Non-core (Avail) | 48,500 |
|  |  |  | Non-core (TBM) | 140,650 |
| Total research |  |  |  | 298.150 |

Evaluation Plan 2017

| Evaluation name | Mandatory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ AWP Output | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |

MONITORING, EVALUATION AND RESEARCH PLAN (MERP) 2019

Monitoring 2019

| SN Impact/Outcome | Activity | Responsible staff member | Partners and Stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Source | Amount |
| MONITORING |  |  |  |  |  |  |
| Impact 3/SP Outcome 4 : All women and girls live a life free from all forms of violence | 3.1.1.18 Direct Project Management Cost (salary and M&E quality assurance, monitoring and documentation and SSA for HeForShe Consultant) | EVAW & PMERKM Officers | Responsible Partners | Continuously during the year | Non Core - TBM | $9.900,00 |
| Impact 6/SP Outcome 1 : A comprehensive and dynamic set of global norms, policies and standards on gender equality and the empowerment of all women and girls is strengthened and implemented | 6.1.2.19 Coordinate and monitor the implementation and reporting of National Action Plans (NAP 1325, Advancement of women, Prevention of gender-based violence) , central, provincial and district level (7 provinces and 13 districts) | WPS Programme & PMERKM Officers | MGCAS & Responsible partners | 3rd and 4th quarter 2019 | Non Core - Available | $75.000,00 |
|  | 6.1.2.33. Organize annual joint monitoring field visit, annual project review of the technical advisory group and a final national project meeting | Programme Manager, WPS Programme & PMERKM Officers | MGCAS, Iceland, Norway & Members of the WPS Technical and Advisory Group | 4th Quarter 2019 | Non Core - Available | $10.000,00 |
| Impact 2/Outcome 2: Women have income security, decent work and economic autonomy | 2.1.4.10. Regular Monitoring and Quality Assurance | Programme Manager, WEE Programme & PMERKM Officers | Responsible Partners | Continuously | Non Core - Available | $44.265,00 |
| Impact 4/Outcome 5: Women and girls contribute and have greater influence in building sustainable peace and resilience, and benefit equally from the prevention of natural disasters and conflicts and from humanitarian action. | 4.1.1.18 Conduct project monitoring activities | Programme Manager, WPS Programme & PMERKM Officers | MGCAS, Iceland & Norway and members of the WPS Technical and Advisory Group | Continuously | Non-Core Available | $44.483,00 |
| OUTPUT CLUSTER 1To drive more effective and efficient United Nations system coordination and strategic partnerships on gender equality and women’s empowerment | 1.1.6. Coordinate planning, implementation, monitoring and report on UNDAF Outcome 4 (e.g. planning retreat) | Programme Manager & PMERKM Officer | UNFPA, UNICEF, IOM, WHO, WFP, FAO, UNAIDS, UNDP, | Continuously during the year | Core | $6.500,00 |
| OUTPUT CLUSTER 2 To institutionalize a strong culture of results-based management, reporting, knowledge management and evaluation | 2.1.13. Undertake joint (programme and operations) monitoring field visits and spot checks in accordance to POM/Cash advance policy, particularly in areas where IPs are involved, as well as strengthen development results and impact monitoring (costs covered under DRF monitoring) | Country Representative, Programme Manager & Operations Staff | All IPs | Continuously during the year | Core | Staff time |
|  | 2.1.14. Produce quarterly and annual reports, conduct quarterly and annual CO AWP monitoring in RMS | PMERKM and Programme Officers |  | Quarterly December 2019 | No Cost Implication | Staff time |
|  | 2.1.15. Conduct the mid-term review of the CO's SN 2016-2020 | PMERKM & Programme Manager |  | 3rd quarter to 4th quarter | Core | $35.000,00 |
| OUTPUT CLUSTER 3 To enhance organizational effectiveness, with a focus on robust capacity and efficiency at country and provincial levels | 3.1.10. Organize staff planning and review retreats, team building sessions and annual planning , review meeting with partners and participation in regional and global retreats | Country Representative, programme Manager & M&EKM officer |  | 1st and 4th quarter | Core | $31.000,00 |
|  | 3.3.15. Monitor delivery on a monthly basis and follow up on off track areas | Operations Manager & Programme Manager |  | Montly during the year | No Cost Implication | Staff time |
| Total |  |  |  |  |  | $256.148,00 |

RESEARCH PLAN 2019

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget (all reflected in the DRF) |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount |
| RESEARCH |  |  |  |  |
| 6.1.1.2. Assess the institutional and technical capacity of national gender machinery (MGCAS and sectors) and National Statistical Institute for systematic production, use and dissemination of gender statistics, for policy-making and monitoring of national and international commitments (including SDGs) and develop a strategy and action plan to address the identified gaps | Ministry of Gender, Children and Social Action and the National Statistic Institute | February to May 2019 | Core | $10.000,00 |
| 2.1.1.19. Conduct "Mozambique Women in Business Outlook" - mapping women in formal and informal business, market share, best practices of growth, opportunities and challenges for market access to facilitate narrowing gender gap on procurement and increase access to better market | Ministry of Agriculture and Food Security and the Ministry of Land and Rural Development | February to Sept 2019 | Core | $11.000,00 |
| 2.1.4.8. Conduct a demand and market analysis to identify opportunities and challenges including policy related ones to the economic empowerment of girls and young women in Zambezia. | UNFPA, UNICEF, Provincial Department of Youth and Sports, District Governments, DFID | Jan to Feb 2019 | Non Core - Available | $12.000,00 |
| 2.2.6. … 2017 & 2018 Annual report |  |  | Core | 1.000,00 |
| 4.1.3.4. Conduct research and academic debates on topics related to WPS | UEM | April-December 2019 | Non Core - Available | $28.600,00 |
| 2.2.13. Assess perception of CO in country by carrying out a survey among stakeholders, partners and actors | Operations Manager | April-Jun 2019 | No Cost Implication | 0.00 |
| Total research |  |  |  | $62.600,00 |

Evaluation Plan 2019

| Evaluation name | Mandatory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ AWP Output | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) |  | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1.1.21. WPS Mid-Term Evaluation | Yes | SP Outcome 5 : Women and girls contribute and have greater influence in building sustainable peace and resilience, and benefit equally from the prevention of natural disasters and conflicts and from humanitarian action. | 4.1.1Women and girls capacity to participate meaningfully in conflict/prevention and resolution strengthened | Mozambique | ESA | N | MGCAS, Iceland, Norway, WPS Technical and Advisory Group and IPs |  | April 2019 to Sept | Non Core – Available ($65.500.00) |  | Project mid-term evaluation planned in signedproject document |
|  |  |  |  |  |  |  |  |  |  | $48.474.00 |  | Cost of salary of CO M&E Officer |
| Total Evaluation |  |  |  |  |  |  |  |  |  | $113.974.00 |  |  |

Mozambique County Office – AWP 2020

MONITORING, EVALUATION AND RESEARCH PLAN (MERP) 2020

Monitoring 2020

| SN Impact/Outcome | Activity | Responsible staff member | Partners and Stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Source | Amount |
| MONITORING |  |  |  |  |  |  |
| Impact 6/SP Outcome 1 : A comprehensive and dynamic set of global norms, policies and standards on gender equality and the empowerment of all women and girls is strengthened and implemented | 6.1.2.19 Coordinate and monitor the implementation and reporting of National Action Plans (NAP 1325, Advancement of women, Prevention of gender-based violence) , central, provincial and district level (7 provinces and 13 districts) | WPS Programme & PMERKM Officers | MGCAS & Responsible partners | 3rd and 4th quarter 2020 | Non Core - Available | $40.000,00 |
|  | 6.1.2.33. Organize annual joint monitoring field visit, annual project review of the technical advisory group and a final national project meeting | Programme Manager, WPS Programme & PMERKM Officers | MGCAS, Iceland, Norway & Members of the WPS Technical and Advisory Group | 4th Quarter 2020 | Non Core - Available | $31.000,00 |
| Impact 2/Outcome 2: Women have income security, decent work and economic autonomy | 2.1.4.10. Regular Monitoring and Quality Assurance | Programme Manager, WEE Programme & PMERKM Officers | Responsible Partners | Continuously | Non Core - Available | $44.265,00 |
| Impact 4/Outcome 5: Women and girls contribute and have greater influence in building sustainable peace and resilience and benefit equally from the prevention of natural disasters and conflicts and from humanitarian action. | 4.1.1.18 Conduct WPS project monitoring activities | Programme Manager, WPS Programme & PMERKM Officers | MGCAS, Iceland & Norway and members of the WPS Technical and Advisory Group | Continuously | Non-Core Available | $48,000.00 |
| OUTPUT CLUSTER 1To drive more effective and efficient United Nations system coordination and strategic partnerships on gender equality and women’s empowerment | 1.1.6. Coordinate planning, implementation, monitoring and report on UNDAF Outcome 4 (e.g. planning retreat) | Programme Manager & PMERKM Officer | UNFPA, UNICEF, IOM, WHO, WFP, FAO, UNAIDS, UNDP, | Continuously during the year | Core | $6.500,00 |
|  | 1.1.17 Advocate for and monitor the implementation of the gender scorecard action plan by the UNCT | Country representative; Programme Specialist | All UN agencies | January to June | Core | $0,0 |
| OUTPUT CLUSTER 2 To institutionalize a strong culture of results-based management, reporting, knowledge management and evaluation | 2.1.13. Undertake joint (programme and operations) monitoring field visits and spot checks in accordance to POM/Cash advance policy, particularly in areas where IPs are involved, as well as strengthen development results and impact monitoring (costs covered under DRF monitoring) | Country Representative, Programme Manager & Operations Staff | All IPs | Continuously during the year | Core | $0,0 |
|  | 2.1.14. Produce quarterly and annual reports, conduct quarterly and annual CO AWP monitoring in RMS | PMERKM and Programme Officers | PO | Quarterly December 2020 | Core | $0,0 |
| OUTPUT CLUSTER 3 To enhance organizational effectiveness, with a focus on robust capacity and efficiency at country and provincial levels | 3.1.10 Organize trainings (e.g. sexual exploitation and abuse, Sexual harassment, standards of conduct, ethics, diversity and inclusion, project budget management, staff retreats, team building sessions), and planning (annual, midterm, thematic reviews), review meeting with partners and participation in regional and global retreats (thematic reviews to be supported under DRF-NCA) | Country Representative, programme Manager & M&EKM officer | UNW Staff | 1st and 4th quarter | Core | $36.000,00 |
|  | 3.3.15. Monitor delivery on a monthly basis and follow up on off track areas | Operations Manager & Programme Manager | Operations manager and PMERK | Monthly and quarterly basis during the year | Staff management cost | $0,0 |
| Total |  |  |  |  |  | $ 205,765,00 |

Research Plan 2020

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget (all reflected in the DRF) |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount |
| RESEARCH |  |  |  |  |
| 2.1.3.18 Conduct an in-depth gender assessment on the impact of cyclones IDAI and Kenneth in the affected areas of Mozambique (direct payment from the High Commission of Canada) | MGCAS, UN agencies, civil society | Until March 2020 | Canada (direct payment) | $0,0 |
| 2.2.6. … 2018 & 2019 Annual report | n/a | Jan to March 2020 | Core | $0,0 |
| 4.1.3.4 Conduct research and academic debates on topics related to WPS (leveraging the 20-year anniversary of UNSCR 1325) | Joaquim Chissano University | April-December 2020 | Non Core - Available | $65.000,00 |
| 4.1.3.5 Identify, document and disseminate good practices emerging from the implementation of the WPS project in all aspects | MGCAS | April to December 2020 | Non-core available | $45,000,00 |
| 4.1.1.20 Produce, print and disseminate WPS Knowledge and communication products (including partial contribution to Communications Officer Salary) | MGCAS and IPs | April to December 2020 | Non-core available | $45.000,00 |
| 3.1.5.5 Produce a booklet for CSOs and CBOs on existing accountability mechanisms on SGBV and Early marriage and procedures to engage with them (SLI 6.2.1) | WLSA/IP | April to June 2020 | Non-core available | 32,000,00 |
| 3.1.5.1 Conduct and publish a countrywide map of women's rights groups and relevant CSOs and CBOs including those representing youth and groups facing intersecting forms of discrimination/marginalization and facilitate their integration in networks (SLI 6.3.1) | WLSA/IP | January to June 2020 | Non-core available | $50,766.00 |
| 2.1.4.6 Document and disseminate good practices on young women´s economic empowerment in Nampula and Zambezia | Beneficiaries | January to December 2020 | Non-core available | $21.500.00 |
| Total research |  |  |  | $214,266,00 |

Evaluation Plan 2020

| Evaluation name | Mandatory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ AWP Output | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) |  | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1.1.21. WPS Mid-Term Evaluation | Yes | SP Outcome 5 : Women and girls contribute and have greater influence in building sustainable peace and resilience, and benefit equally from the prevention of natural disasters and conflicts and from humanitarian action. | 4.1.1Women and girls capacity to participate meaningfully in conflict/prevention and resolution strengthened | Moz | ESA | N | MGCAS, Iceland, Norway, WPS Technical and Advisory Group and IPs |  | April 2020 to Sept | Non Core – Available ($63.100.00) | Planned | Project mid-term evaluation planned in signed project document and it was postponed from 2019 |
| 2.1.16 Conduct a Thematic evaluation to be conducted to assess programme impact on a key thematic area of focus for SLI Mozambique e.g. Harmful Practices including Early Marriage. | Yes | SP Outcome 4 : All women and girls live a life free from all forms of violence | Output cluster 2.3. Results based evaluation and research/studies are commissioned and managed for decision making, accountability and learning | Moz | ESA | Yes: UNFPA, UNICEF, UNDP | MGCAS, EU |  | April 2020 to June 2020 | $186,916,00 | Planned |  |
| 2.1.17 Conduct a Mid-term Evaluation to assess the progress and results of the project at the midway point and useful for reviewing project successes and challenges and important lessons learnt and good practice relevant to the last 2 years of programme implementation. | Yes | SP Outcome 4 : All women and girls live a life free from all forms of violence | Output cluster 2.3. Results based evaluation and research/studies are commissioned and managed for decision making, accountability and learning | Moz | ESA | Yes: UNFPA, UNICEF, UNDP | MGCAS, EU |  | July 2020 to Dec 2020 | $186,916,00 | Planned |  |
| 2.3.8 Evaluation of the Country Office Programme 2016-2020 | yes | Output cluster 2. To institutionalize a strong culture of results-based management, reporting, knowledge management and evaluation | Output cluster 2.3. Results based evaluation and research/studies are commissioned and managed for decision making, accountability and learning | Moz | ESA | yes | UN Women |  | From June to September 2020 | Core ($18.500.00) | Planned | Planned to inform the next CO SN formulation in 2020 |
| 2.3.3 Facilitate national staff and partners- access to capacity building on gender-sensitive planning and evaluations | n/a | Output cluster 2. To institutionalize a strong culture of results-based management, reporting, knowledge management and evaluation | Output cluster 2.3. Results based evaluation and research/studies are commissioned and managed for decision making, accountability and learning | Moz | ESA | N | Staff and evaluation team members |  | January to December | $0,0 | Planned | n/a |
| Total Evaluation |  |  |  |  |  |  |  |  |  | $ 455,432,00 |  |  |

MONITORING, EVALUATION AND RESEARCH PLAN 2021

Mozambique

- Monitoring and Research Plan 2021

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount |
| MONITORING |  |  |  |  |
| 6.1.2.19 Coordinate and monitor the implementation and reporting of National Action Plans (NAP 1325, Advancement of women, Prevention of gender-based violence), central, provincial and district level (7 provinces and 13 districts) | MGCAS & Responsible partners | 3rd and 4th quarter 2021 | Non-Core - Available | $8.000,00 |
| 6.1.2.33. Organize annual joint monitoring field visit, annual project review of the technical advisory group and a final national project meeting | MGCAS, Iceland, Norway & Members of the WPS Technical and Advisory Group | 4th Quarter 2021 | Non-Core - Available | $10.000,00 |
| 2.1.4.10. Regular Monitoring and Quality Assurance | Responsible Partners | Continuously | Non-Core - Available | $25.515,00 |
| 4.1.1.18 Conduct WPS project monitoring activities | MGCAS, Iceland & Norway and members of the WPS Technical and Advisory Group | Continuously | Non-Core Available | $15,000.00 |
| 3.1.5.2 Train CSOs and CBOs and provide technical support on project/programme design and management, resource mobilization, implementation and M&E (SLI 6.3.4) | SLI IPs | Continuously during the year | Non Core-Available | $12.000,00 |
| 1.1.6. Coordinate planning, implementation, monitoring and report on UNDAF Outcome 4 (e.g. planning retreat) | UNFPA, UNICEF, IOM, WHO, WFP, FAO, UNAIDS, UNDP, | Continuously during the year | Core | $2.000,00 |
| 2.1.13. Undertake joint (programme and operations) monitoring field visits and spot checks in accordance to POM/Cash advance policy, particularly in areas where IPs are involved, as well as strengthen development results and impact monitoring (costs covered under DRF monitoring) | Operations, Programme Officers and M&E | Continuously during the year | Core | $0,0 |
| 2.1.14. Produce quarterly and annual reports, conduct quarterly and annual CO AWP monitoring in RMS | M&E, Programme Officers | Quarterly December 2021 | Core | $48,517.00 |
| 3.3.15. Monitor delivery on a monthly basis and follow up on off track areas | Operations Manager | Monthly and quarterly basis during the year | Staff management cost | $0,0 |
| Total |  |  |  | 121,032,00 |
| RESEARCH |  |  |  |  |
| 2.2.6. … 2018 & 2019 Annual report | Programme Officers and M&E | Jan to March 2021 | Core | $0,0 |
| 2.2.14 Print and disseminate the Gender Country Profile nationwide | MGCAS, UN agencies | Jan to June 2021 | Core | $4.000,00 |
| 4.1.1.27 Conduct in-depth gender assessment of the impact of violent extremism in the north and central provinces with focus on women and girls and develop a CO programme intervention | MGCAS, GREPOC | April 2020 to June 2021 | Core | $20.000,00 |
| 4.1.3.4 Conduct research and academic debates on topics related to WPS (leveraging the 20-year anniversary of UNSCR 1325) | Joaquim Chissano University | April-December 2021 | Non- Core - Available | $5.000,00 |
| 4.1.3.5 Identify, document and disseminate good practices emerging from the implementation of the WPS project in all aspects | MGCAS | April to December 2021 | Non-core available | $5,000,00 |
| 4.1.1.20 Produce, print and disseminate WPS Knowledge and communication products (including reports, achievement briefs, newsletters, etc. ) | MGCAS and IPs | April to December 2021 | Non-core available | $8.000,00 |
| 3.1.5.1 Conduct and publish a countrywide map of women's rights groups and relevant CSOs and CBOs including those representing youth and groups facing intersecting forms of discrimination/marginalization and facilitate their integration in networks (SLI 6.3.1) | WLSA/IP | January to June 2021 | Non-core available | $10,000.00 |
| 2.1.4.6 Document and disseminate good practices on young women´s economic empowerment in Nampula and Zambezia | IPs, Programme Officers and communication | January to December 2021 | Non-core available | $12.500.00 |
| Total |  |  |  | 64,500.00 |

- Evaluation Plan 20xx-20xx

| Evaluation name | Mandatory? (Y/N) | UNDAF Outcome/ UN Women SP Outcome and relevant SDGs | SN Output/Relevant flagship program | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Planned Dates (start-end) |  | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluation 1: 2.3.7 Initiate conduct of the WPS final evaluation in Q4 (to be concluded in Q1 2022). | Y | SP Outcome 5/SDG 16 | Moz AWP 2021 Output cluster 2.3. | Moz CO | ERAR/Moz | N | Jan to Dec 2021 |  | Non Core – Available ($20.000,00) | Planned | This will be prepared in last quarter of 2021 as the budget need to be included being the last year of the WPS project; |  |
| 2.3.8 Evaluate the Country Office Programme 2016-2020 and formulate the New SN | Y | n/a | MOZ AWP 2021 Output cluster 2.3. | MOZ Co | ESAR/Moz | N | Jan 2021-May 2021 |  | Core (30,000.00) | Planned | The preparation will start in 2020 to ensure that in 2021- Q1 we can start. |  |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.9 Conduct a Thematic to assess programme impact on a key thematic area of focus for SLI Mozambique | Y | Goal 5, Outcome 3 | Moz AWP 2021 Output Cluster 2.3 | SLI Secretariat | HQ | N | April to June 2021 |  | NCA- $186,916,00 | Planned | This was planned for last year but it was not implemented and postponed to 2021 |  |
| Total |  |  |  |  |  |  |  |  | 239.916,00 |  |  |  |

Please see Guidance on Decentralized Evaluations, link.

Please fill out a separate row for each evaluation.

Please see Guidance on Decentralized Evaluations, link.

Please fill out a separate row for each evaluation.

Please fill out a separate row for each evaluation.

Outcomes contributing to the SDGs as per the Strategic Plan