MONITORING, EVALUATION AND RESEARCH PLAN 2021-2025

Uganda CO

- Monitoring and Research Plan 2021-2025

| Activity | UNSDCF Outcome/UN Women SP Outcome |  | SN Output/Relevant flagship program | Related indicator/KPI (Y/N, Indicator number, how and when) | Data Collection (Y/N, what data, how) | Office and Person in charge | Partners and stakeholders | Planned Dates (Month and year of start and end) | Donors Involved | Budget |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  | Source | Amount |  |
|  |  | MONITORING |  |  |  |  |  |  |  |  |  |  |
| Periodic quarterly monitoring visits to Project sites (Data Quality Assessments, program delivery, technical support, on spot financial reviews) | All Goals |  | All Outputs | Number of quarterly monitoring visited conducted | Yes, data on reporting variances | Uganda, PMER Specialist | UN Women and Implementing partners | April / July / October / December | All CO donors | Non-Core Available | $ 189,604 | Ongoing |
| Annual RBM Training for UNW Country office staff and Implementing Partners | All Outcomes |  | All SN outputs | All SN Indicators | Yes, Knowledge change results | Uganda, PMER Specialist | All Implementing Partners | February – March | All CO donors | Non-Core TBM | $150,000 | Ongoing |
| Quarterly RBM Clinics with Implementing Partners (incorporated into quarterly program reviews) | All Outcomes |  | All SN outputs | All SN Indicators | Yes, Knowledge change results | Uganda, PMER Specialist | UN Women Staff (Programs & Operations Teams) | March / June / September/ December of each year | All CO donors | Non-Core Available |  | Ongoing |
| Support knowledge management initiatives (including establishment of a one stop center for all knowledge management products, monitoring & evaluating utilization of the products, technical support in production of the products) | All Outcomes |  | All SN outputs | All SN Indicators | Yes, Available knowledge products | Uganda, PMER Specialist | UN Women and Implementing partners | Quarterly March / June / September/ December | All CO donors | Non-Core TBM | $25,000 | Ongoing (Planned session on KM for CO staff still in pipeline) |
| Establishment of digital M&E system & regular maintenance / updating | All Outcomes |  | All SN outputs | All SN Indicators | No | Uganda, PMER Specialist | UN Women M&E Team | Quarterly June / September/ December | All CO donors | Non-Core Available | $30,000 | Completed |
| Support capacity of UN Women M&E staff to monitor SN 2021 – 2025 (incl. professional training in monitoring, evaluation, documentation, and research; learning visits to other UN Agencies or UN Women country offices |  |  | All SN outputs | All SN Indicators | No | Uganda, PMER Specialist |  | 2024, 2025 | All CO donors | Non-Core TBM | $50,000 | Completed partly |
| Development of annual work plans for various programmes and projects in the SN | All outcomes |  | All SN outputs | All SN Indicators | Yes | Uganda, PMER Specialist | UN Women & All Implementing partners | 2025 | All CO donors |  |  | Completed for 2022 - 2023 |
|  |  | RESEARCH |  |  |  |  |  |  |  |  |  |  |
| Support Institutional Portfolio Reviews and Planning Development Processes (incl. 2024 – 2025 BWP review to ensure effective delivery of UN Women mandates, corporate level monitoring and accountability at field level | All Outcomes |  | All Outcomes | All SN Outputs | Yes | Uganda, PMER Specialist |  | 2021-2025 | All CO donors | Non-Core TBM | $150,000 |  |
| Impact of affirmative Action on GEWE | UNSDCF Outcome 1 |  | SN Output 1.1.2 | Indicator 1.2.1b. | Yes | Programme Specialist Intergovernmental Support | MoGLSD | 2024 - 2025 |  | TBM | 40,000 |  |
| Effectiveness of implementation of CSW recommendations in Uganda | UNSDCF Outcome 1 |  | UNSDCF Output 1.1 | Indicator 1.1.1b. | Yes | Programme Specialist Intergovernmental Support | MoGLSD | 2024 – 2025 |  | TBM | 40,000 |  |
| Gender alerts on Humanitarian situations |  |  | SN Output 3.1.3 | Indicator 3.1.3c. | Yes | GIHA Specialist | All HA Partners | 2024 – 2025 |  | Non-Core available | 80,000 |  |

- Evaluation Plan 2021-2025

| Evaluation name | Mandatory (Y/N) | UNSDCF Outcome/ UN Women SP Outcome and relevant SDGs | SN Output/ Relevant flagship program | Office and Person in charge | Region/ country | Joint activity (Y/N, indicate partners) | Planned Dates (start-end) | Donors Involved | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Annual and midterms reviews and assessments for different programs and projects in the SN | Yes | All Programs | All SN Outputs | Uganda, PMER Specialist | ESARO, Uganda | Yes, All Implementing Partners | Annually, 2021-2025 | All CO donors | $150,000 | Pending | Ongoing |
| End of Project Evaluations | Yes | LEAP Program (Japan, Norway) | SN Output 3.1.3 | Uganda, PMER Specialist | ESARO, Uganda | Yes, LEAP Responsible Partners | 2024 - 2025 | HA donors (Japan, Norway) | $70,000 | Pending |  |
| Access to Justice Programme Review | Yes | UNSDCF Outcomes 1.1 & 3.1 | SN Outputs 3.1.1 & 3.1.3 | Uganda, PMER Specialist | ESARO, Uganda | No | Mid 2025 | Austrian Development Cooperation | $25,000 | Pending |  |
| NAP III WPS Review | No | UNSDCF Output 1.3 | SN Output 1.2.1 | Uganda, PMER Specialist | ESARO, Uganda | Yes, MoGLSD | 2024 - 2025 |  | $50,000 | Pending |  |
| SN CYCLE LIGHT REVIEW 2021 – 2025 | Yes | All Outcomes | All SN Outputs | Uganda, PMER Specialist | ESARO, Uganda | Yes, All Implementing Partners | Mid 2025 | All CO donors | $20,000 | Pending | Pending |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |  |
| Support baseline, annual assessments, special studies of the UNSDCF 2021-2025 | Yes | All UNSDCF Outcomes | All SN Outputs | Uganda, PMER Specialist | ESARO, Uganda | Yes, All UN Agencies | Annually, 2021-2025 | All CO donors | $20,000 | Ongoing | Completed |
| Support Government performance assessments NAPPAR and the third Voluntary National Review Report 2024 | Yes | All UNSDCF Outcomes | All SN Outputs | Uganda, PMER Specialist | ESARO, Uganda | Yes, Other UN Agencies | Annually, 2021-2025 | All CO donors | $20,000 | Pending |  |
| UN Joint Program Assessment | Yes | All UNSDCF Outcomes | All SN Outputs | Uganda, PMER Specialist | ESARO, Uganda | Yes, ESARO, Uganda | Annually, 2021-2025 | All CO donors | $16,000 | Pending |  |

Please fill out a separate row for each evaluation.

Outcomes contributing to the SDGs as per the Strategic Plan