Evaluation Plan for year 2021

| Evaluation name | Mandatory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ MCO/ RO AWP Output | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |
| Country Programme Evaluation in preparation for developing a new Strategic Note | y | Whole SN | Whole SN | Malawi Country Office | Country | N | Ministry of Gender, CSO, NGOs and UN Agency partners | January to April 2021 | 30,000, core funds | Postponed to 2023 following extension of the Country SN |  |
| End of project evaluation for the Women Empowerment Programme | y | Whole SN | Whole AWP | Malawi Country Office | Country | N | Ministry of Gender, CSO, NGOs and UN Agency partners | January to June 2021 | 20,000, Donor funds | Initiated. Recruited Processes underway |  |
| End of Project Evaluation for the KOIKA Project | y | Whole SN | Whole AWP | Malawi Country Office | Country | N | Ministry of Gender, CSO, NGOs and UN Agency partners | January to March 2021 | 15,000, Donor funds | Initiated. Draft Report submitted by consultant. |  |