Multi-Country Office Caribbean

NOTE: Examples have been included below to illustrate how to complete each column; they are not meant to be accurate to real life activities.

- Monitoring and Research Plan 2020

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount |
| MONITORING |  |  |  |  |
| Undertake a comprehensive review, including sector-specific, on the gender inequality of disaster and climate risk in 9 Caribbean SIDS including a review of the cost of inaction as well as a mapping of gender differentiated coping and adaptive capacities for key vulnerable groups and key sectors. | UNDP | 1/2020 – 12/2020 | Donor Funds | $276,000 |
| RESEARCH |  |  |  |  |
| Gender-sensitive assessment of the Agricultural, Fisheries and Small Business Extension Services in 1 country. | FAO, UNDP, ILO | 2/2020 – 7/2020 | Donor Funds | $27,600 |
| Review of the national land access and land/business registration policy and legislation; identification of discriminatory provisions, and formulation of recommendation for change. | FAO, UNDP, ILO | 2/2020 - 12/2020 | Donor Funds | $23,000 |
| Conduct comprehensive gender assessment of national climate change policies and plans, NAPs and existing statutory and customary laws in the 9 Caribbean countries to identify gaps and opportunities for improved gender mainstreaming and alignment with existing national development and poverty reduction strategies. | UNDP | 2/2020– 12/2020 | Donor Funds | $214,000 |
| Qualitative analysis and research on experiences of violence of marginalised/ “at risk” groups of women such as women with disabilities, young and adolescent women, women who have been pregnant, and girls who may suffer multiple and intersecting forms of discrimination | UNDP, UNFPA, UNICEF | 04/2020 – 12/2020 | Donor Funds (Spotlight) | $25,000 |
| Bejing+25 Fulfilling the Commitments in the Caribbean |  | 1/2020 – 3/2020 | Core | $40,470 |
| Gender Aware Beneficiary Assessment (GABA) on gender dimensions in accessing piped water | UNDP | 7/2019 – 7/2020 | Core | $25,000 |

- Evaluation Plan 2020

| Evaluation name | Mandatory? (Y/N) | UNDAF Outcome/ UN Women SP Outcome and relevant SDGs | SN Output/Relevant flagship program | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluation of JURIST project partnership | Y | SP Outcome 1 MSDF- Safe Just and Cohesive Caribbean SDGs 5 and 16 | MCO Caribbean AWP Output 6.1 | MCO Caribbean | Trinidad and Tobago, Guyana, Belize, Jamaica, Barbados | Y- Jurist project | Jan-July 2019 | US$10,00, core funds | pending |  |
| Mid Term Evaluation | Y | MSDF1,2,3,4 SDG 1-17 | MCO Caribbean SN | MCO Caribbean | 22 Countries and territories covered by MCO | N | Jan – September 2020 | $15,000 core funds | pending |  |

Please fill out a separate row for each evaluation.

Outcomes contributing to the SDGs as per the Strategic Plan