MONITORING, EVALUATION AND RESEARCH PLAN 2014-2017

Monitoring and Research Plan 2014-2017

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount |
| MONITORING |  |  |  |  |
| Mid-term review of the Regional Strategic Plan | RO RBM team & MCO/COs M&E focal points | Ago.–Dec. 2015 | TBD | TBD |
| Preparation of RO AWP’s Indicators Tracking Tool and oversight of countries’ AWPs Indicators Tracking Tools | RO RBM team & MCO/COs M&E focal points | Quarterly | n/a | n/a |
| Preparation and submission of RO’s annual report and oversight of annual reporting processes of countries in LAC | RO RBM team & MCO/COs M&E focal points | Annually | n/a | n/a |
| Preparation and submission of LAC’s quarterly regional report to HQ | RO RBM team | Quarterly | n/a | n/a |
| Review and feedback of country quarterly progress programme and operations reports | RO RBM team | Quarterly | n/a | n/a |
| Oversight of preparation, follow-up and submission of donor progress and final programme and financial reports in LAC | RO Donor Relations Specialist and Operations Manager | As required according to donor agreements and project documents | n/a | n/a |
| RESEARCH |  |  |  |  |
| Produce regional and/or comparative analyses, including lessons learnt from UN Women’s programmes, of key trends and phenomena and emerging issues in relation to priority areas of work | UN Women MCO/COs UN, Civil Society, Government Partners, regional and sub-regional organizations | 2014-2017 | Core | 70,000 |
| Support data generation on GEWE in the region in alignment with the gender indicators of the Gender Equality Observatory in LAC | UN Women MCO/COs UN, Civil Society, Government Partners, regional and sub-regional organizations | 2014-2017 | Core | 20,000 |

Evaluation Plan 2014-2017

| Evaluation name | Manda tory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ MCO/ RO AWP Output | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |
| Regional Evaluation on Leadership and Political Participation | Y | SP Goal 1 / Outcome 1.4 | RO Output 1.4.1 | ACRO | Americas and the Caribbean | N | RO / MCO / COs National women's machineries, Parliaments, Gender advocates | Oct 2013 – March 2014 | 80,000 USD Core | On going |  |
| Regional Evaluation on Access to Justice as a prevention mechanism to EVAW | Y | SP Goal 3 / Outcomes 3.1 and 3.2 | RO Output 1.4.1 | ACRO | Americas and the Caribbean | N | RO / MCO / COs National women's machineries, UN agencies, CSO | July 2015 – January 2016 | 90,000 USD Core | Initiated | Design ToR |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |
| FGE Final Evaluation "Mujeres Bolivianas en el proceso de cambio" | Y | DRF – goal 1, outcome 1.1 |  | FGE | Bolivia | N | Coordinadora de la Mujer | Q1 2014 | 23,000 USD non- core funds (FGE) | Completed |  |
| UNDAF Evaluation 2013-2017 | Y | UNDAF |  | OCR | Bolivia | Y | UNS, RC | Q1 2017 (to be confirmed | Core | Pending |  |
| Final evaluation of Programme “Domestic Workers: Building Equality in Brazil” | Y | UNDAF Outcomes 1.1, 1.2 and 2.3 SP Impact 2, Outcome 2.2 | Brazil AWP Output 2.3.1 | Brazil CO | Brazil | Y (Fundo Elas, Themis) | ILO, FENATRAD, SPM and SEPPIR | January-June 2015 | US$30,000non- core funds (FGE) | Pending |  |
| Mid-term evaluation of Programme “Engaging women and men with gender transformative conditional cash transfer (CCT) programming” | Y | UNDAF Outcomes 1.1, 1.2 and 2.3 SP Impact 2, Outcome 2.2 | Brazil AWP Output 2.3.1 | Brazil CO | Brazil | Y (Instituto promundo Instituto Papai) | MDS | June-September 2014 | US$22,500non- core funds (FGE) | On going |  |
| Final evaluation of Programme “More Rights More Power for Brazilian Women” | Y | UNDAF Outcomes 1.1, 1.2, 1.3 and 2.3 SP Impact 1, 2, and 5; Outcomes 1.1, 2.3, 5.1 and 5.2 | Brazil AWP Output 1.1.1, 1.1.2, 2.3.1, 5.1.1 and 5.2.2 | Brazil CO | Brazil | Y (FGE consortium and SPM) | TBD | July-October 2014 | US$72,000non- core funds (FGE) | On going |  |
| Final evaluation of Programme “Engaging women and men with gender transformative conditional cash transfer (CCT) programming” | Y | UNDAF Outcomes 1.1, 1.2 and 2.3 SP Impact 2, Outcome 2.2 | Brazil AWP Output 2.3.1 | Brazil CO | Brazil | Y (Instituto promund, Instituto Papai) | MDS | September-December 2015 | TBD non- core funds (FGE) | Pending |  |
| UNDAF Final evaluation | Y | UNDAF Outcomes all SP Impact all Outcomes all | Brazil AWP Output all | Brazil CO | Brazil | Y (UNCT) | TBD | October-December 2016 | n/a | Pending |  |
| Final Evaluation related to the implementation of the National Action plan on GBV Belize – UNTF to end 2015- Bureau of Gender Affairs | Y | Outcome 3 |  | MCO Caribbean / | Belize | N | Government ministries and departments, Civil Society, Women’s organizations, Shelters | Sept- Dec 2015 | UNTF | Pending |  |
| Final Evaluation Way out Project FGE | Y | Outcome 1&2 |  | MCO Caribbean | Jamaica |  | Government ministries and departments, Household workers and Household worker associations, NGO’s, Women’s Organizations, Women Entrepreneurs | June – Sept. 2014 | 15,000 non- core funds (FGE) | Completed |  |
| Final Evaluation Network of NGOS Womens’s transformational political leadership local and national levels project | Y | Outcome 1 |  | MCO Caribbean | Trinidad and Tobago | FGE | Political parties, Local government and village councils, female candidates, young women | Jan- March 2015 | TBC non- core funds (FGE) | Pending |  |
| UNDAF Evaluation | Y | UNDAF SP Goal-Outcome | All UNDAF | OCR | Colombia | Y | SNU APC Ministry of Foreign Affairs | End 2014 | 10,000 Core (Colombia CO) | Pending |  |
| External Evaluation of the UNDAF 2015 | Y |  |  | OCR | El Salvador | Y UNS | RC Office, UNCT, Foreign Ministry | Expected year: 2015 (TBC) | TBD | Pending |  |
| Final evaluation of the IFAD project: Broadening Economic Opportunities For Rural Women Entrepreneurs In LAC Region (Beo) | Y | UNDAF II priority area/SP2.2 | Guatemala AWP | Guatemala Office | El Salvador Mexico GuatemalaNicaragua | N | TBD | Expected year: 2015 (TBC) | TBD IFAD | Pending | (funds to be managed by Guatemalan CO) |
| Mid-term evaluation UN Peace Building Fund | No | Impact 4, Outcome 4.1 | Output 4.1.2 | UNDP | GTM | Y | Ministry of the Interior, General Prosecutor’s Office | February – March 2015 | USD 0 | Pending |  |
| JUNAJIL-Asoprogal Project Evaluation | N |  | 4.1.4 | FGE | Guatemala |  |  | Sept. – Oct. 2014 | 6,500 non- core funds (FGE) | Completed |  |
| Final evaluation of the SUMA FGE-project: “Strengthening Women's Political Participation and Promoting an Economic Empowerment Agenda” | Y | UNDAF V priority area/SP 1.1 DRF Goal 1 Outcome 1.1 | Mexico AWP Output 1.1.1 | HQs | Mexico (federal and 14 States) | Y (FGE) | Implementing partners (CSOs), NWMs, Federal Electoral Institute, Federal Electoral Justice Tribunal, Political Parties, State Governments, State Parliaments, among others | Jan.– May 2014 | 22.000 non- core funds (FGE) | Completed |  |
| Final evaluation “Contributing to the Effective Implementation of the General Law on Women’s Access to a Life Free from Violence in Mexico and the Recommendations by the Inter-American Court of Human Rights in the “Campo Algodonero” Case | Y | SP Impact 3 | Mexico AWP Output 3.2.1 | HQs UNTF-EVAW | Mexico | N | Católicas por el Derecho a Decidir- Mexico, National Citizen’s Observatory on Feminicide | December 2014 | UNTF TBD as part of pending approval of non-cost extension | Second semester 2015 |  |
| Final evaluation of the European Union project: Strengthening institutional capacities in the justice sector to protect women’s right to a life free of violence | Y | UNDAF IV Priority area/SP 3.1 | Mexico AWP Output 3.1.2 | HQs | Albania, Mexico and Timor Lest | Awaiting information from HQs | Awaiting information from HQs | 2015 | EU $54,849.63 (for the 3 countries) | Pending |  |
| Final evaluation of the European Union project: Thematic Programme of Cooperation with Third Countries in the Areas of Migration and Asylum | Y | UNDAF IV Priority area/SP 2.1 | Mexico AWP Output 2.1.1 | HQs | Mexico, Moldova and Philippines | Awaiting information from HQs | Awaiting information from HQs | 2016 | EU Awaiting information from HQs | Pending |  |
| External Evaluation of the UNDAF 2014-2019 | Y |  |  | RC office | Mexico | Y UNS | RC Office, UNCT, Ministry of Foreign Affairs through AMEXCID | Expected year: 2018 (TBC) | TBD | Pending |  |
| FGE global evaluation | Y |  | Global | FGE | Sede | Global | COs | 2017 | Core | TBD |  |

## Evaluation Justification Matrix

| List of selected evaluation | Criteria used for the selection | Potential evaluability | Intended use of evaluation findings |
| --- | --- | --- | --- |
| Regional Evaluation on Leadership and Political Participation | Relevance of the subject Significant investment | High | To support the formulation of new SN, to learn and to generate accountability |
| Regional Evaluation on Normative Frameworks | Relevance of the subject Significant investment | High | To support the formulation of new SN, to learn and to generate accountability |

Including on, inter alia, effectiveness of quota and parity laws; political parties' gender sensitive programmatic, electoral and organic behavior; working with men for the prevention of violence against women and girls; tools for costing, measuring and evaluating gender violence initiatives; social tolerance to violence against women and girls; fiscal policy and gender equality; time survey analysis for programme formulation.

Please fill out a separate row for each evaluation.