# Annex 1: 2012-2013 oPt MONITORING, EVALUATION AND RESEARCH (MER) PLAN

Note: As per the Guidance “How to develop UN WOMEN Monitoring, Evaluation and Research (MER) Plans”, MER Plans are developed at country, sub-regional and regional level. The development of MER Plan needs to be closely linked with the development of Annual Work Plans.

NOTE: Examples have been included below to illustrate how to complete each column; they are not meant to be accurate to real life activities.

| Title & Type of MER activity | Mandatory (Y/ N) | Relevant UNDAF Outcome/ UN Women SP Goal and Outcome |  | Relevant Country/ SRO AWP Output | Office to manage the MER activity |  |  | Region, Sub Region or Country |  | Joint MER activity (Y/ N, indicate partners) |  | Key Stakeholders |  | Planned Dates (start-completion) |  |  | Budget (US$) for MER activity/ Sources of Funding |  | Status (pending - initiated – ongoing - completed) |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2012 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1) MONITORING activities undertaken by the Country/ Sub-regional/ Regional Office e.g. Partner visits, (Repeat) Baselines, Reviews, UN Women Annual Report, Annual Programme and UNDAF Review Process etc. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Hebron Spot Project | Y | DRF 3 Indicator: number of VAW victims pursuing access to formal justice through civil police family protection units. |  | oPt AWP output 3.1.1 | oPt |  |  | Arab States, oPt |  | N |  | MoSA |  |  | March2011- March 2012 | $20000 Project Funds |  |  | completed |  | This project is executed by UNDP, and implemented by an international NGO. UNDP signed an agreement with UNW to do the monitoring role given our expertise in VAW (shelters in particular). |
| Note: The oPt office have been trying to recruit an M&E person for almost 6 months but no qualified candidates were available. The M&E persons is supposed to assist the office in setting up a monitoring system , and collect baseline for the AWP. Joint efforts between oPt office and the ME&E Unit at HQ are taking place to identify strong qualified candidates for this post. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2a) EVALUATIONS managed by the Country/ Sub-regional/ Regional Office e.g. outcome, thematic, programme evaluations etc. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Socially Responsible Development through Women-run School Canteens Final Evaluation | Y | DRF 2 Indicator: Number of female headed household that receive food support in oPt. Increase in assets (living space, household, equipment, savings, land/garden) of targeted women. |  | oPt AWP output 2.2.1 | oPt |  |  | Arab States, oPt |  | Y MoEHE |  | MoEHE Sabay Centers and CBOs |  | Aug –August 2012 |  |  | 28,750$ Project Funds |  | Completed |  |  |
| Saudi Project – Establishment, Rehabilitation and Activation of Eight Women’s Centres in the Gaza Strip and West Bank Final evaluationvcvaation 2012ntada Coalitioncan refer. | Y | DRF 2 Indicator: Number of targeted women obtaining internships and/or job opportunities |  | oPt AWP output 2.1.2 | oPt |  |  | Arab States, oPt |  | N |  | MoLG, 8 Women CBOs, |  | June-Oct 2012 |  |  | 39,000$ Project Funds |  | Completed |  |  |
| MDG-F Gender and Development Programme Final Evaluation | Y | DRF 2 Indicator: % of women participating in formal labour force |  | oPt AWP output 3.1.1 | oPt |  |  | Arab States, oPt |  | Y MoWA and other GO, NGOs, UN agencies, and Private sector |  | MoWA Members of Al Muntada Forum and Amal Coalition, Sabaya Centers, women CBOs, etc… |  | August/Sept. 2012 |  |  | covered financially by UNDP. |  | Completed |  |  |
| MDG-F Culture Programme Final Evaluation | Y | DRF 2 Increase in assets (living space, household, equipment, savings, land/garden) of targeted women. |  | oPt AWP output 2.2.1 | oPt |  |  | Arab States, oPt |  | Y MoC, MoWA, MoA, MoTA, UN agencies and NGO partners |  | MoC, MoTA, MoWA, MoA, NGO partners, private sector and Sabaya Centers, women CBOs, etc… |  | August/Sept. 2012 |  |  | This will be covered by UNESCO |  | Completed |  |  |
| Livelihood Protection and Sustainable Empowerment of Vulnerable, Rural and Refugee Communities in the Jordan Valley (oPt) Midterm Evaluation | Y | DRF 2 Indicator: Number of targeted women obtaining internships/ jobs opportunities. |  | oPt AWP output 2.1.2 | oPt |  |  | Arab States, oPt |  | Y UNESCO, FAO, UNRWA, UNWOMEN |  |  |  | July – Sept 2012 |  |  | Midterm evaluation |  | Completed |  | UNRWA is managing this evaluation. |
| 2b) Other EVALUATIONS in which Country/ Sub-regional/ Regional Office is involved but NOT managing, e.g. evaluations managed by HQ Evaluation Office, Trust Fund on VAW, UNDEF, donors, etc. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| N/A |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3) RESEARCH Activities undertaken by the Country/ Sub-regional/ Regional Office with regard to the monitoring and evaluation needs of the Annual Work Plans |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ICHR Report on Female Inmate's Human Rights | N | DRF 3 |  | oPt AWP output 3.1.1. |  | oPt |  |  | Arab States, oPt |  | Y ICHR | Palestinian Correction and Rehabilitation Centers |  |  | 1st quarter |  |  | Through ICHR |  | Completed |  |
| Market Research in the Culture and Creative Industries Sectors in the oPt and implemented by New Vision | N |  | DRF3 | oPt AWP output 1.1.1 |  | UN Women oPt |  |  | Arab States, oPt |  | N | MDG-F Gender Equality and Women’s Empowerment partners |  |  | July/August 2012 |  |  | $5,000 |  | Completed |  |
| 2013 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1) MONITORING activities undertaken by the Country/ Sub-regional/ Regional Office e.g. Partner visits, (Repeat) Baselines, Reviews, UN Women Annual Report, Annual Programme and UNDAF Review Process etc. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Review of Women’s Access to Justice Project | N | DRF3 Indicator: number of VAW victims pursuing access to formal justice through civil police family protection units. |  | oPt AWP output: 3.1.1 | The donor (DFID) is managing this activity |  |  | oPt |  | Y |  | GOs: Ministry of Justice, Ministry of Interior (Family protection Units). |  | Feb 2013 – April 2013 |  |  | Will be funded through the donor DFID |  | Completed |  | This review will be initiated and managed by the donor (DFID) for the women’s access to justice project, in close collaboration with UNW oPt. |
| Mid-term Review of Access to Justice Project | N | DRF3 Indicator: number of VAW victims pursuing access to formal justice through civil police family protection units. |  | oPt AWP output: 3.1.1 | oPt |  |  | Arab Sates |  | Y DFID |  | Ministry of Justice, Ministry of Interior (Family protection Units), Bar Association, High Judiciary Council and CSOs. |  | Feb – April 2013 |  |  | 6,000$ Project funds |  | Pending |  | Will be initiated and managed by UNW oPt |
| 2a) EVALUATIONS managed by the Country/ Sub-regional/ Regional Office e.g. outcome, thematic, programme evaluations etc. | Note: Many of oPt joint programmes and projects are planned to end in year 2012, and so there are no planned evaluations for year 2013 so far. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Mehwar Project -Final Evaluation | Y | DRF 3 Indicator: number of VAW victims pursuing access to formal justice through civil police family protection units. |  | oPt AWP output 3.1.3 3.1.2 | oPt |  |  | Arab States, oPt |  | Yes |  | MoSA Mehwar Shelter |  | June 2012-August 2012 |  |  | $19000 Project Funds |  | Ongoing |  | Evaluation has been completed in 2012, waiting for final approval of donor. |
| 2b) Other EVALUATIONS in which Country/ Sub-regional/ Regional Office is involved but NOT managing, e.g. evaluations managed by HQ Evaluation Office, Trust Fund on VAW, UNDEF, donors etc. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3) RESEARCH Activities undertaken by the Country/ Sub-regional/ Regional Office with regard to the monitoring and evaluation needs of the Annual Work Plans |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Access to Justice for women in Palestine – research | N |  | DRF 3 | oPt AWP output 3.1.1. | oPt |  | Arab States, oPt |  |  |  | Y MoJ | MoJ | July 2012 – March 2013 |  |  | 95000$ Project funds (DFID) |  |  |  | On-going |  |
| Situation Analysis of Women in Palestine | N |  | DRF 5 | oPt AWP output 5.1.1 | oPt |  | Arab States, oPt |  |  |  | Y MoWA MoPAD | MoWA MoPAD | July 2012 – June 2013 |  |  | 30.000$ CORE FUNDS |  |  |  | On-going |  |

oPt does not have an UNDAF, but an Medium Term Response Plan. This plan doesn’t have clear objectives to which we can refer.