MONITORING, EVALUATION AND RESEARCH PLAN 2023-2025

Southern Africa Multi-Country Office

- Monitoring and Research Plan 2023-2025

| Activity | UNSDCF Outcome/UN Women SP Outcome | SN Output/Relevant flagship program | Related indicator/KPI (Y/N, Indicator number, how and when) | Data Collection (Y/N, what data, how) | Office and Person in charge | Partners and stakeholders | Planned Dates (Month and year of start and end) | Donors Involved | Budget |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  | Source | Amount |
| MONITORING |  |  |  |  |  |  |  |  |  |  |  |
| Periodic quarterly monitoring visits to Project sites (Data Quality Assessments, program delivery, technical support, on spot financial reviews) | All Goals | All Outputs | Number of quarterly monitoring visited conducted | Yes, data on reporting variances | M&E Officer | UN Women and Implementing partners | April / July / October / December | All MCO donors | Non-Core Available | $ 20,000 |
| Annual RBM Training for UNW SACMO staff and Implementing Partners | All Outcomes | All SN outputs | All SN Indicators | Yes, Knowledge change results | M&E Officer | All Implementing Partners | February – March | All MCO donors | Non-Core Available | $20,000 |
| Quarterly RBM Clinics with Implementing Partners (incorporated into quarterly program reviews) | All Outcomes | All SN outputs | All SN Indicators | Yes, Knowledge change results | M&E Officer | UN Women Staff (Programs & Operations Teams) | March / June / September/ December of each year | All MCO donors | Non-Core Available |  |
| Support knowledge management initiatives (including establishment of a one stop center for all knowledge management products, monitoring & evaluating utilization of the products, technical support in production of the products) | All Outcomes | All SN outputs | All SN Indicators | Yes, Available knowledge products | M&E Officer | UN Women and Implementing partners | Quarterly March / June / September/ December | All MCO donors | Non-Core Available | $15,000 |
| Support capacity of UN Women M&E and Program staff to monitor SN 2023 – 2025 (incl. professional training in monitoring, evaluation, documentation, and research; learning visits to other UN Agencies or UN Women country offices |  | All SN outputs | All SN Indicators | No | M&E Officer |  | 2021, 2022, 2023, 2024, 2025 | All MCO donors | Non-Core Available | $15,000 |
| Development of annual work plans for various programmes and projects in the SN | All outcomes | All SN outputs | All SN Indicators | Yes | M&E Officer | UN Women & All Implementing partners | 2023, 2024, 2025 | All MCO donors |  |  |
| RESEARCH |  |  |  |  |  |  |  |  |  |  |  |
| Rapid assessment on community perceptions on women in leadership | Outcome | SN OUTPUT | Indicator 1.2.2a. Number of community members (men, women, opinion leaders) sensitized on cultural and social norms and practices on women's participation in politics and leadership | Yes | Program Leads | Implementing Partners on Women Movement Building | November, 2023 | All MCO donors | Non-Core Available | $10,000 |
| Support Institutional Portfolio Reviews and Planning Development Processes (incl. 2021 AWP bi-annual review and 2021-2025 to ensure effective delivery of UN Women mandates, corporate level monitoring and accountability at field level | All Outcomes | All Outcomes | All SN Outputs | Yes | M&E Officer |  | 2023-2025 | All MCO donors | Non-Core Available | $20,000 |

- Evaluation Plan 2023-2025

| Evaluation name | Mandatory (Y/N) | UNSDCF Outcome/ UN Women SP Outcome and relevant SDGs | SN Output/ Relevant flagship program | Office and Person in charge | Region/ country | Joint activity (Y/N, indicate partners) | Planned Dates (start-end) | Donors Involved | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Annual and midterms reviews and assessments for different programs and projects in the SN | Yes | All Programs | All SN Outputs | M&E Officer | ESARO, SAMCO | Yes, All Implementing Partners | Annually, 2022-2025 | All CO donors | $50,000 | Pending |  |
| Mid-Term Evaluation of SAMCO SN | Yes | All Outcomes | All SN Outputs | M&E Officer | ESARO, SAMCO | Yes, All Implementing Partners | Mid, 2023 | All CO donors | $20,000 | Pending |  |
| MCO Portfolio Evaluation of SN 2022 – 2025 | Yes | All Outcomes | All SN Outputs | M&E Officer | ESARO, SAMCO | Yes, All Implementing Partners | Mid 2025 | All CO donors | $30,000 | Pending |  |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |  |
| Support baseline, annual assessments, special studies of the UNSDCFs during SN Period | Yes | All UNSDCF Outcomes | All SN Outputs | M&E Officer | ESARO, SAMCO | Yes, All UN Agencies | Annually, 2022-2025 | All CO donors | $25,000 | Ongoing |  |
| UN Joint Program Assessment | Yes | All UNSDCF Outcomes | All SN Outputs | M&E Officer | ESARO, SAMCO | Yes, ESARO, SAMCO | Annually, 2021-2025 | All CO donors | $16,000 | Pending | $16,000 |

Please fill out a separate row for each evaluation.

Outcomes contributing to the SDGs as per the Strategic Plan