MONITORING, EVALUATION AND RESEARCH PLAN (MERP) MCO Kazakhstan (Central Asia) 2016-2020

Monitoring 2016-2020

| SN Impact/Outcome | Activity | Responsible staff member | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Source | Amount |
| MONITORING |  |  |  |  |  |  |
| SN/AWP related monitoring |  |  |  |  |  |  |
| Quarterly monitoring of activities | Update RMS | Project managers, KM and Communications | Internal staff | On a quarterly basis | Staff time | 10,000 |
| Annual reporting | Prepare inputs and update RMS | Programme Managers, KM and Communications, Operations | Internal staff | 12/2016 – 1/2017 12/2017 – 1/2018 12/2018 – 1/2019 12/2019 – 1/2020 12/2020 – 1/2021 | Staff time | 10,000 |
| Mid-term review of SN 2016-2020 | Desk review, stakeholder consultations and regional retreat | Programme managers, Head of MCO, KM and Communications, Operations, RO SPO | MCO personnel, RPs, key partners (Govt, CSOs, donors) | 5/2018-7/2018 | Core | 25,000 |
| Annual review of AWP at the country level (KAZ, TJK, TKM) | Stakeholder meeting | Programme/project staff | Key partners at the country level | 11/2017, 11/2018, 11/2019, 11/2020 | Core | 15,000 |
| Contribution to UNDAF/UNPFD monitoring |  |  |  |  |  |  |
| Mid-term review of KAZ PFD | Desk review and workshop | Programme managers, Head of MCO | UNCT, Government, CSO | 1/2018-7/2018 | Core | 1000 |
| Mid-term review of TKM PFD | Desk review and workshop | Programme managers, Head of MCO | UNCT, Government, CSO | 1/2018-7/2018 | Core | 500 |
| Mid-term review of TJK UNDAF | Desk review and workshop | Programme managers, Head of MCO | UNCT, Government, CSO | 1/2018-7/2018 | Core | 500 |
| Contribution to UN JPs’ monitoring |  |  |  |  |  |  |
| SN Impact area 2 UN JP funded by UNHSTF, TJK | Cumulative interim financial report and final narrative report | Tajikistan Programme Specialist | NWM, RP (NGO “Najibullo”), local government of Rasht district | - 31/01/2017- interim financial report 30/06/2017-final narrative and financial reports | Staff time | 5,000 |
| JPs annual reporting, KAZ | Input for consolidated report (compiled by UNDP) | Project manager, MCO Programme Specialist | RP, UNCT, RCO | 02/2017 – 03/2017 | Staff time | 5,000 |
| UN JP funded by UNHSTF, TJK | Input for final substantive report (compiled by UNDP); | Tajikistan Programme Specialist MCO Programme Specialist | RP, UNCT, RCO | 30/06/2017- final certified financial report 30/06/2017 – final substantive narrative ; report; | Staff time | 5,000 |
| Project related monitoring |  |  |  |  |  |  |
| PBF project, TJK | Mid-term reporting, final reporting and final project evaluation | Project manager PBF, Tajikistan Programme Specialist | Government, CSOs, UNCT | 06/2017--08/2017 | Non-core + Staff time | 5,000 |
| KAZ project (SDG, WEE, GRB) with MNE | Project implementation monitoring | Project manager, MCO Programme Specialist | Government, CSOs, UNCT | TBD | Non-core + Staff time | TBD |
| Interim report (narrative and financial) for Support to Civil Registration Reform Project, TJK (UNDP led) | Input for UNDP interim report (Narrative and financial) | Project manager CRR, Tajikistan Programme Specialist | Government, UNDP, CSOs | 30/4/2017-interim financial report 30/4/2017-interim narrative report | Staff time | TBD |
| Mid-term and annual review: Support to Civil Registration Reform Project | Project implementation monitoring | Project manager, Tajikistan Programme Specialist | UNDP CO, UNDP RO | 2017 (TBC) | Non-core + Staff time | $8,000 |
| Interim reports (narrative and financial) for Support to Civil Registration Reform Project, TJK (UNDP led) | Inputs for UNDP interim reports (Narrative and financial) | Project manager CRR, TajikistanProgramme Specialist | Government, UNDP, CSOs | 30/4/2018-interim financial report 30/4/2018-interim narrative report | Staff time | TBD |
| Mid-term and annual review: Support to Civil Registration Reform Project | Project implementation monitoring | Project manager, Tajikistan Programme Specialist | UNDP CO, UNDP RO | 2018 (TBC) | Non-core + Staff time | $8,000 |
| Interim report (Narrative and financial) for Support to Civil Registration Reform Project, TJK (UNDP led) | Input for UNDP interim report (Narrative and financial) | Project manager, Tajikistan Programme Specialist | Government, UNDP, CSOs | 30/4/2019-interim financial report 30/4/2019-interim narrative report | Staff time | TBD |
| Mid-term and annual review: Support to Civil Registration Reform Project | Project implementation monitoring | Project manager, Tajikistan Programme Specialist | UNDP CO, UNDP RO | 2019 (TBC) | Non-core + Staff time | $4,000 |
| Interim financial report and final narrative report for Support to Civil Registration Reform Project, TJK (UNDP led) | Input for UNDP interim financial and final narrative report | Project manager, Tajikistan Programme Specialist | Government, UNDP, CSOs | 31/10/2019 – final narrative report; 31/10/2019 – interim financial report; | Staff time |  |
| Final certified financial report for Support to Civil Registration Reform Project, TJK (UNDP led) | Input for final certified financial report | Project manager, Tajikistan Programme Specialist | UNDP | 31/06/2020 -final certified financial report | Staff time | $8,000 |

Research Plan 2016-2020

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount |
| RESEARCH |  |  |  |  |
| Common Country Assessment KAZ | UNCT | 1/2019-6/2019 | Core | 5,000 |
| Common Country Assessment TJK | UNCT | 1/2019-6/2019 | Core | 5,000 |
| Common Country Assessment TKM | UNCT | 1/2019-6/2019 | Core | 5,000 |

Evaluation Plan 2016-2020

| Evaluation name | Mandatory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ MCO/ RO AWP Output | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |
| Evaluation 1: “Empowering abandoned women from migrants’ families in Tajikistan” Project, funded by MFA of Norway | Y | UNDAF Outcome 2 People in Tajikistan benefit from equitable and sustainable economic growth through decent and productive employment, stable energy supply, improved access to specialized knowledge and innovation and more favourable business environment especially for entrepreneurs and farmers SP Goal 2, Outcome 2.1 |  | MCO Kazakhstan (Central Asia) | Central Asia/Tajikistan | N | Governments, CSOs, other stakeholders | 12/2013 – 4/2016 | 35,300/non-core | Pending |  |
| Evaluation 2: “Supporting achieving SDGs and enforce commitments on gender equality in Kazakhstan” project | N | PFD Outcomes: 1.2, 3.1. SP Goals 2,5,6 Outcomes 2.2, 5.1, 5.2, 6.1 | Kazakhstan MCO AWP Outputs 5.2.1. | MCO Kazakh-stan | Central Asia/Kazakhstan | N | Governments, CSOs, other stakeholders | 6/2018 – 12/2018 | US$14,000, non-core |  | Included in the project signed with the government of Kazakhstan |
| Evaluation 3 “Supporting localization of gender responsive SDGs in Central Asia project” project | N | PFD Outcomes: 3.1. SP Goals 5,6 Outcomes 5.2, 6.1 | Kazakhstan MCO AWP Outputs 5.2.1. | MCO Kazakh-stan | Central Asia/Kazakhstan | N | Governments, CSOs, other stakeholders | 1/2019 – 6/2019 | US$20,000, non-core funds (soft pipeline) |  | Pending signing of donor agreement with the Government of KAZ |
| Evaluation 4 Final evaluation of MCO Kazakhstan SN 2016-20 | Y | PFD Outcomes: 1.1., 1.2., 2.1.,2.2., 3.1. SP Goals 2,3,5,6 Outcomes 3.2 , 5.1, 5.2, 5.3, 6.1 | Kazakhstan MCO AWP Outputs … | MCO Kazakh-stan | Central Asia/Kazakhstan, Tajikistan, Turkmenistan | N | Governments, CSOs, other stakeholders | 1/2020 – 6/2020 | US$50,000, core funds |  |  |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |
| Evaluation 1: Evaluation of the JP in Kzylorda and Mangistau | Y | PFD Outcome 2.1. SP Goal 3, Outcome 3.2. | Kazakhstan /AWP Output 3.2. | MCO Kazakhstan | Kazakhstan | Y UNCT | UNCT, NGO Podrugi (RP) | 2/2017 – TBD | $1700/ non-core | Initiated | Evaluation mission conducted in December 2016 |
| Evaluation 2: Final evaluation PFD KAZ 2016-20 | Y | Entire UNDAF KAZ | N/A | UN RC Office in KAZ | UNCT KAZ | Y (UNCT) | Government, CSO, donors and IO | 2020 (TBC) | $500 core funds | pending |  |
| Evaluation 3: Final evaluation PFD TKM 2016-20 | Y | Entire PFD TKM | N/A | UN RC Office in TKM | UNCT TKM | Y (UNCT) | Government, CSO, donors and IO | 2020 (TBC) | $1,000, core funds | pending |  |
| Evaluation 4: Final evaluation UNDAF TJK 2016-20 | Y | Entire UNDAF TJK | N/A | UN RC Office in TJK | UNCT TJK | Y (UNCT) | Government, CSO, donors and IO | 2020 (TBC) | $500 core funds | pending |  |
| Evaluation 5: Final evaluation of Cross-border peace and confidence building project (PBF funded project), TJK | Y | UNDAF Outcome 1 | N/a | PBSO | Tajikistan Kyrgyzstan | Y (UNCT Krg) and (UNCT Tjk) | Government, CSO, RUNOs | 4/2017-9/2017 | TBC | pending | Not initiated yet |
| End of phase 1 External evaluation: Support to Civil Registration Reform | Y | UNDAF TJK Outcome 1. | N/A | UNDP CO, UNDP RO | Tajikistan | UNDP led Project | Government, CSOs, donors and IO | 2019 (TBC) | $4,000 | pending |  |