UN WOMEN Burundi COUNTRY OFFICE

Strategic Note 2019-2023

MONITORING, EVALUATION AND RESEARCH PLAN (MERP)

MONITORING PLAN

| Related Output | Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Source | Amount |
|  | SN |  |  |  |  |
| Cluster 3 Output 3.3 | Midterm review 2019-2023 Strategic Note | Program & Operations staff | June 2021 | Core | 6000 |
|  |  |  |  | Non/Core TBM |  |
|  | AWPS-programs |  |  |  |  |
| Cluster 3 Output 3.3 | Annual reviews 2019-2023 Strategic Note (AWPs) | Program & Operations staff | One per year | Core | 16000 |
|  |  |  |  | Non/Core TBM |  |
| Cluster 3 Output 3.3 | Semester reviews of the AWP extended to partners | UN Women, implementing partners | One per year | Core | 15000 |
|  |  |  |  | Non/Core TBM |  |
| Cluster 3 Output 3.3 | Monitoring Office thematic meetings (Programs and operations) | All staff | Each month | N/A | 0 |
| All outputs | Field mission on activities monitoring | UN Women, Implementing partners, Beneficiaries, Donors, | Each quarter | Core | 65000 |
|  |  |  |  | Non/Core TBM |  |
| Output 4.1.1 | R 1325 Monitoring of resource commitment | WPS specialist, LPP and EVAW program officers | Each quarter | N/A | 0 |
| Cluster 3 Output 3.1 | Monitoring the implementation of all 2018 study findings/recommendations (masculinity and harmful practices, leave no one behind, justice mechanisms) | EVAW program officer | Each quarter | N/A | 0 |
| Cluster 3 Output 3.3 | Preparation of the QMR, Annual and Donor reports | UN Women | Each Quarter | NA | 0 |
| Cluster 4 Output 4.1 | Monitoring evolution of staff training plan and career development | UN Women | Each Quarter | NA | 0 |
| All outputs | On Site Data Verification(OSDV) to check the progress of indicators (Mandatory and other missions) | UN Women | One per Quarter, before the QMR | Core | 10000 |
|  | UN-coordination |  |  |  |  |
| Cluster 1 output 1.1 | Monthly Gender thematic groups coordination meetings | UN Women; GT; GT/CMP | Each month | Core | 10000 |
| Cluster 1 output 1.1 | Monitoring of UNCT Gender Strategy | UNW, GTG, UNCT, PMT | Quarterly | N/A | 0 |
| Cluster 1 output 1.1 | Develop tools for tracking the GEWE accountability framework implementation | M&E | Semester | N/A | 0 |
| Cluster 1 output 1.1 | Annual review of the gender score card plan | UN Women; GTG | Novembre | Core | 25000 |
|  | UNW RESSOURCE MOBILIATION |  |  |  |  |
| Cluster 4 output 4.3 | Update the resource mobilization action plan | UN Women | Each semester | NA | 0 |
| Cluster 4 output 4.3 | Preparation of Donor reports | UN Women | Each Quarter | NA | 0 |
|  | UNDAF |  |  |  |  |
| Cluster 1 output 1.1 | Annual review of the 2019-2023 UNDAF implementation | UN Agencies; Government and Partners | Nov 2019 Nov 2020 Nov 2021 Nov 2022 | N/Core TBM | 10000 |
| Cluster 1 output 1.1 | Mid Term review of the 2019-2023 UNDAF implementation | UN Agencies; Government and Partners | June 2021 | N/Core TBM | 5000 |

RESEARCH PLAN

| Related Output | Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Source | Amount |
|  | DATA COLLECTION ON THEMATICS |  |  |  |  |
| Output 4.1. | Mapping of women peace actors across the country | UN Women /MIN Gender, | March - June 2019 | N/Core Available | 5000 |
| Output 4.2 | Research on trafficking persons “women and girls | UN Women /MIN Gender, | May - July 2019_ | Core | 5000 |
| Output 4.2 | Research on the impact of violence against women/girls and economic | UN Women/ISTEEBU | March-June 2020 | N/Core TBM | 10000 |
| Output 4.2. | Mapping of SGBV actors and availability of services for victims / survivors of violence against women and girls | UN Women | March-June 2020 | Core | 5000 |
|  |  |  |  | N/Core TBM | 35000 |
| Output 4.3 | Research on durable solution for better economic recovery | UN Women / MIN Gender | April-June 2019 | N/Core TBM | 10000 |
| Output 4.3 | Research on innovative financial product and services to improve women access to credit | UN Women | April-June 2020 | N/Core TBM | 10000 |
| Output 4.3 | Research on reducing gender gap in agriculture | UN Women | April- June 2019 | N/Core TBM | 10000 |
| Output 4.3 | Gender sensitive rapid survey on nutrition status of women and children | UN Women | April-July 19 | Core | 5000 |
|  |  |  |  | N/Core TBM | 10000 |
| Cluster 2 Output 2.3. | Mapping of the private sector, donors, etc. (OEEF) | UN Women | April-June 19 | N/Core TBM | 2000 |
|  | GEWE Coordination |  |  |  |  |
| Cluster 1 Output 1.1 | Gender score card study for the UNDAF 2019-2023 | UN Women /UN Coordination | January-March 2019 | Core NCTBM | 5000 30000 |
| Cluster 1 Output 1.1 | Gender analysis of the 2019-2023 UNDAF implementation | UN Women/UN Coordination | June 2021 | N/Core TBM | 10000 |
| Cluster 1 Output 1.1 | Conduct a Gender Needs Assessment for humanitarian assistance targeting women and girls | UN Women /UNHCR, OCHA, Others | March-June 2019 | N/Core TBM | 5000 |
| Cluster 1 Output 1.1 | Carry out a gender profile in Burundi based on gender data sets | UN Women/MIN Gender | March-June 2020 | Core/Non Core TBM | 10000 |

KNOWLEDGE PLAN

| Related Output | Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Source | Amount |
| DATA COLLECTION ON THEMATICS |  |  |  |  |  |
| Output 4.1 | Develop a practitioner’s toolkit based on WPM’s work in conflict prevention/ resolution to share experiences, lessons learned and promising practices | UN Women | October 2019 | N/Core Available | 14000 |
| DRF output 4.1 | Produce and disseminate good practices and lessons learnt on WPS, EVAW, social/economic recovery and work with media | All program officers | Each quarter | N/Core TBM | 8000 |
| Cluster 3, Output 3.1 | Dissemination of the results on studies | UN Women | 2019 -2020 | N/Core TBM | 5000 |

EVALUATION PLAN

| Evaluation name | Mandatory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ MCO/ RO AWP Output | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluation carried out by the office |  |  |  |  |  |  |  |  |  |  |  |
| Final evaluation of the 2019-2023 Strategic Note | Yes | UNDAF 2019-2023 (Outcomes 3 and 5 ) | Burundi | UN Women/ Burundi | ESARO | Yes | UN Agencies; Gvnmt; Partners | June 2023 | 40000 | Planned |  |
| Evaluation carried out with the contribution of the office |  |  |  |  |  |  |  |  |  |  |  |
| Final evaluation of the 2019-2023 UNDAF implementation | Yes | UNDAF 2019-2023 (Outcomes 3 and 5 ) | Burundi | UN Women/ Burundi | ESARO | No | UN Agencies; Gvnmt; Partners | Nov 2023 | 10000 | Planned |  |
| NAP 2017- 2021 evaluation | Yes | UNDAF 2019-2023 (Outcomes 6) | Burundi | UN Women/Mini Gender | ESARO | Yes | UN Agencies; Gvnmt; | 2021 | 10000 | Planned |  |
| Total MERP : 416 000,00 USD |  |  |  |  |  |  |  |  |  |  |  |