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      MONITORING PLAN


	Related Output
	Activity
	Partners and stakeholders
	Planned Dates
(Month and year of start and end)
	Budget

	
	
	
	
	Source
	Amount

	
	SN
	
	
	
	

	Cluster 3 Output 3.3
	Midterm review 2019-2023 Strategic Note
	Program & Operations staff
	June 2021
	Core 
	6000

	
	
	
	
	Non/Core TBM
	

	
	AWPS-programs 
	
	
	
	

	Cluster 3 Output 3.3
	Annual reviews 2019-2023 Strategic Note (AWPs)
	Program & Operations staff
	One per year
	Core 
	16000

	
	
	
	
	Non/Core TBM
	

	Cluster 3 Output 3.3
	Semester reviews of the AWP extended to partners 
	UN Women, implementing partners
	One per year
	Core 
	15000

	
	
	
	
	Non/Core TBM
	

	Cluster 3 Output 3.3
	Monitoring Office thematic meetings (Programs and operations)
	All staff
	Each month
	N/A
	0

	All outputs
	Field mission on activities monitoring
	UN Women, Implementing partners, Beneficiaries, Donors,
	Each quarter
	Core 
	      65000   

	
	
	
	
	Non/Core TBM
	

	Output 4.1.1
	R 1325 Monitoring of resource commitment 
	WPS specialist, LPP and EVAW program officers
	Each quarter
	N/A
	0

	Cluster 3 Output 3.1
	Monitoring the implementation of all 2018 study findings/recommendations (masculinity and harmful practices, leave no one behind, justice mechanisms)  
	EVAW program officer 
	Each quarter
	N/A
	0

	Cluster 3 Output 3.3
	Preparation of the QMR, Annual and Donor reports 
	UN Women
	Each Quarter
	NA
	0

	Cluster 4 Output 4.1
	Monitoring evolution of staff training plan and career development 
	UN Women
	Each Quarter
	NA
	0

	All outputs
	On Site Data Verification(OSDV) to check the progress of indicators (Mandatory and other missions) 
	UN Women  

	One per Quarter, before the QMR
	Core
	10000

	
	UN-coordination 
	
	
	
	

	Cluster 1 output 1.1
	Monthly Gender thematic groups coordination meetings 
	UN Women; GT; GT/CMP
	Each month
	Core
	      10000   

	Cluster 1 output 1.1
	Monitoring of UNCT Gender Strategy 
	UNW, GTG, UNCT, PMT 
	Quarterly 
	N/A
	0

	Cluster 1 output 1.1
	Develop tools for tracking the GEWE accountability framework implementation 
	 M&E
	 Semester 
	 N/A
	0

	Cluster 1 output 1.1
	Annual review of the gender score card plan 
	UN Women; GTG
	Novembre
	Core
	       25000 

	
	UNW RESSOURCE MOBILIATION  
	
	
	
	

	Cluster 4 output 4.3
	Update the resource mobilization action plan 
	UN Women
	Each semester
	NA
	0

	Cluster 4 output 4.3
	Preparation of Donor reports 
	UN Women
	Each Quarter
	NA
	0

	
	UNDAF   
	
	
	
	

	Cluster 1 output 1.1
	Annual review of the 2019-2023 UNDAF implementation
	UN Agencies; Government and Partners

	Nov 2019
Nov 2020
Nov 2021
Nov 2022
	N/Core TBM
	10000

	Cluster 1 output 1.1
	Mid Term review of the 2019-2023 UNDAF implementation 
	UN Agencies; Government and Partners

	June 2021
	N/Core TBM
	5000




RESEARCH PLAN

	Related Output
	Activity
	Partners and stakeholders
	Planned Dates
(Month and year of start and end)
	Budget

	
	
	
	
	Source
	Amount

	
	DATA COLLECTION ON THEMATICS
	
	
	
	

	Output 4.1.
	Mapping of women peace actors across the country 
	UN Women /MIN Gender, 
	March - June 2019
	N/Core Available 
	5000

	Output 4.2
	Research on trafficking persons “women and girls 
	UN Women /MIN Gender, 
	May - July 2019_
	Core 
	5000

	Output 4.2
	Research on the impact of violence against women/girls and economic 
	UN Women/ISTEEBU
	March-June 2020
	 N/Core TBM
	10000

	Output 4.2.
	Mapping of SGBV actors and availability of services for victims / survivors of violence against women and girls 
	UN Women
	March-June 2020
	Core 
	5000

	
	
	
	
	N/Core TBM
	35000

	Output 4.3
	[bookmark: _Hlk527702184]Research on durable solution for better economic recovery
	UN Women / MIN Gender
	April-June 2019
	N/Core TBM
	10000

	Output 4.3
	Research on innovative financial product and services to improve women access to credit
	UN Women
	April-June 2020
	N/Core TBM
	10000

	Output 4.3
	Research on reducing gender gap in agriculture
	UN Women
	April- June 2019
	N/Core TBM
	10000

	Output 4.3
	Gender sensitive rapid survey on nutrition status of women and children 
	UN Women
	April-July 19
	Core 
	5000

	
	
	
	
	N/Core TBM
	10000

	Cluster 2 Output 2.3.
	Mapping of the private sector, donors, etc. (OEEF)
	UN Women
	April-June 19
	N/Core TBM
	2000

	
	GEWE Coordination
	
	
	
	

	Cluster 1 Output 1.1
	Gender score card study for the UNDAF 2019-2023
	UN Women /UN Coordination
	January-March 2019
	Core
NCTBM 
	5000
30000

	Cluster 1 Output 1.1
	Gender analysis of the 2019-2023 UNDAF implementation
	UN Women/UN Coordination
	June 2021
	N/Core TBM
	10000

	Cluster 1 Output 1.1
	Conduct a Gender Needs Assessment for humanitarian assistance targeting women and girls
	UN Women /UNHCR, OCHA, Others
	March-June 2019
	N/Core TBM
	5000

	Cluster 1 Output 1.1
	Carry out a gender profile in Burundi based on gender data sets  
	UN Women/MIN Gender
	March-June 2020
	Core/Non Core TBM
	10000





KNOWLEDGE PLAN

	Related Output
	Activity
	Partners and stakeholders
	Planned Dates
(Month and year of start and end)
	Budget

	
	
	
	
	Source
	Amount

	DATA COLLECTION ON THEMATICS

	Output 4.1
	Develop a practitioner’s toolkit based on WPM’s work in conflict prevention/ resolution to share experiences, lessons learned and promising practices
	UN Women
	October 2019
	N/Core Available 
	14000

	DRF output 4.1
	Produce and disseminate good practices and lessons learnt on WPS, EVAW, social/economic recovery and work with media
	All program officers
	Each quarter 
	N/Core TBM
	8000

	Cluster 3, Output 3.1
	Dissemination of the results on studies 
	UN Women
	2019 -2020
	N/Core TBM
	5000




        EVALUATION PLAN

	Evaluation name
	Mandatory?
(Y/N)
	UNDAF Outcome/ UN Women SP Goal, Outcome  
	Country/ MCO/ RO AWP Output
	Office in charge
	Region/ country
	Joint activity 
(Y/ N, indicate partners)
	Key Stakeholders
	Planned Dates 
(start-end)
	Budget (US$) / Sources of Funding
	Status (pending/ initiated/ ongoing/ completed)
	Remarks

	Evaluation carried out by the office
	

	Final evaluation of the 2019-2023 Strategic Note
	Yes
	UNDAF 2019-2023 (Outcomes 3 and 5 )
	Burundi
	UN Women/
Burundi
	ESARO
	Yes

	UN Agencies;
Gvnmt;
Partners
	June 2023
	40000
	Planned
	

	Evaluation carried out with the contribution of the office 
	

	Final evaluation of the 2019-2023 UNDAF implementation 
	Yes
	UNDAF 2019-2023 (Outcomes 3 and 5 )
	Burundi
	UN Women/
Burundi
	ESARO
	No
	UN Agencies;
Gvnmt;
Partners
	Nov 2023
	10000
	Planned
	

	NAP 2017- 2021 evaluation
	Yes 
	UNDAF 2019-2023 (Outcomes 6)
	Burundi
	UN Women/Mini Gender 
	ESARO
	Yes 
	UN Agencies;
Gvnmt;
	2021
	10000
	Planned 
	

	Total MERP :  416 000,00 USD
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