MONITORING, EVALUATION AND RESEARCH PLAN (MERP) 2017-2023

UN Women Brazil Country Office

Updated on 13 December 2023

Monitoring Plan 2017-2023

| SN Impact/Outcome | Activity | Responsible staff member | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Source | Amount |
| MONITORING |  |  |  |  |  |  |
| All | Bi-weekly operational monitoring meetings | Joana Chagas | UN Women CO operational staff | Every other Thursday in 2023 | n/a | n/a |
|  | Bi-weekly programme monitoring meetings | Joana Chagas | UN Women CO programme staff | Every other Wednesday in 2023 | n/a | n/a |
|  | Monthly All Staff meetings | Anastasia Divinskaya | UN Women CO staff | First Monday of the month | n/a | n/a |
|  | Six-monthly programme reports – completion of RMS | Luisa Fenizola | UN Women CO staff and UN Women ACRO | 15th January and 15th July of 2023 | n/a | n/a |
|  | Monitoring missions | Project Managers | UN Women CO staff | Quarterly | Non-core | TBD |
| DRF Outcome 1.1 Women, particularly those facing multiple forms of discrimination, increasingly participate in decision-making processes; and influence formulation, implementation and monitoring of national and subnational laws, policies, plans and budgets. | Final report to Norway | Joana Chagas and Eunice Borges | UN Women CO staff and UN Women ACRO | 05/2017-06/2017 (deadline 30 June 2017) | n/a | n/a |
|  | Interim report to Canada | Joana Chagas and Eunice Borges | UN Women CO staff and UN Women ACRO | 05/2018-06/2018 (deadline 30 June 2018) | n/a | n/a |
|  | Final report to Canada | Joana Chagas and Eunice Borges | UN Women CO staff and UN Women ACRO | 05/2018-06/2018 (deadline 30 September 2018) | n/a | n/a |
|  | Final report to Netherlands | Ana Carolina Querino, Ana Claudia Pereira and Isabel Clavelin | UN Women CO staff and UN Women ACRO | 09/2019-10/2019 (deadline 15 October 2019) | n/a | n/a |
|  | Final report to US National Committee | Ana Claudia Pereira | UN Women CO staff and UN Women ACRO | 11/2020-12/2020 (deadline 19 December 2020) | n/a | n/a |
|  | Interim report to Itabira | Ana Claudia Pereira | UN Women CO staff and UN Women ACRO | 12/2020-02/2021 (deadline 15 February 2021) | n/a | n/a |
|  | Final report to WPF (send inputs to headquarters) | Ana Claudia Pereira | UN Women CO staff, UN Women ACRO and UN Women Headquarters | 12/2020-02/2021 (deadline 28 February 2021) | n/a | n/a |
|  | Final report to Sweden (send inputs to headquarters) | Ana Claudia Pereira | UN Women CO staff and UN Women ACRO | 03/2021-06/2021 (deadline 29 June 2021) | n/a | n/a |
|  | Interim report to Itabira | Lívia Alen | UN Women CO staff and UN Women ACRO | 09/2021-02/2022 (deadline 15 February 2022) | n/a | n/a |
|  | Final report to Itabira | Lívia Alen | UN Women CO staff and UN Women ACRO | 03/2022-06/2022 (deadline 30 September 2022) | n/a | n/a |
|  | Interim report to Norway | Ana Claudia Pereira | UN Women CO staff and UN Women ACRO | 09/2021-02/2022 (deadline 18 February 2022) | n/a | n/a |
|  | Interim report to ABC | Vanessa Sampaio | UN Women CO staff and UN Women ACRO | 03/2022-06/2022 (deadline 05 Jun 2022) | n/a | n/a |
|  | Interim narrative and financial report to Norway | Ana Claudia Pereira | UN Women CO staff and UN Women ACRO | 03/2022-12/2022 (deadline 20 February 2023) | n/a | n/a |
|  | Final narrative and provisional financial report to ABC | Lívia Salles | UN Women CO staff and UN Women ACRO | 07/2022-12/2022 (deadline 05 June 2023) | n/a | n/a |
| DRF Outcome 2.1 Policies and strategies of public and private companies and institutions to strengthen women’s economic rights and opportunities are adopted, implemented and monitored. | Interim report to Lojas Renner | Ana Carolina Querino and Adriana Carvalho | UN Women CO staff and UN Women ACRO | 08/2017-09/2017 (deadline 23 September 2017) | n/a | n/a |
|  | Interim report to Itaipu | Ana Carolina Querino and Adriana Carvalho | UN Women CO staff and UN Women ACRO | 10/2017-11/2017 (deadline 16 November 2017) | n/a | n/a |
|  | Final report to Braskem | Ana Carolina Querino and Adriana Carvalho | UN Women CO staff and UN Women ACRO | 05/2018-06/2018 (deadline 30 June 2018) | n/a | n/a |
|  | Interim report to Lojas Renner | Ana Carolina Querino, Adalgisa Soares and Adriana Carvalho | UN Women CO staff and UN Women ACRO | 08/2018-09/2018 (deadline 16 September 2018) | n/a | n/a |
|  | Final report to Itaipu | Ana Carolina Querino and Adriana Carvalho | UN Women CO staff and UN Women ACRO | 10/2018-11/2018 (deadline 16 November 2018) | n/a | n/a |
|  | Final report to C&A Foundation | Adalgisa Soares and Adriana Carvalho | UN Women CO staff and UN Women ACRO | 01/2019-02/2019 (deadline 02 February 2019) | n/a | n/a |
|  | Interim report to Furnas | Adalgisa Soares and Adriana Carvalho | UN Women CO staff and UN Women ACRO | 02/2019-03/2019 (deadline 19 March 2019) | n/a | n/a |
|  | Interim report to the European Union | Esther Senso | UN Women CO staff and UN Women ACRO | 03/2019-05/2019 (deadline 31 May 2019) | n/a | n/a |
|  | Interim report to Lojas Renner | Adalgisa Soares and Adriana Carvalho | UN Women CO staff and UN Women ACRO | 12/2019-01/2020 (deadline 14 January 2020) | n/a | n/a |
|  | Interim report to the European Union | Adriana Carvalho | UN Women CO staff and UN Women ACRO | 02/2020-05/2020 (deadline 31 May 2020) | n/a | n/a |
|  | Interim report to Luxembourg | Liliam Huzioka | UN Women CO staff and UN Women ACRO | 02/2020-05/2020 (deadline 31 May 2020) | n/a | n/a |
|  | Final report to Furnas | Adalgisa Soares | UN Women CO staff and UN Women ACRO | 06/2020-09/2020 (deadline 17 September 2020) | n/a | n/a |
|  | Final report to Lojas Renner | Tayná Leite | UN Women CO staff and UN Women ACRO | 10/2020-01/2021 (deadline 14 January 2021) | n/a | n/a |
|  | Interim report to Luxembourg | Liliam Huzioka | UN Women CO staff and UN Women ACRO | 02/2021-05/2021 (deadline 31 May 2021) | n/a | n/a |
|  | Final report to Luxembourg | Flavia Muniz | UN Women CO staff and UN Women ACRO | 05/2021-04/2022 (deadline 30 April 2022) | n/a | n/a |
|  | Final report to the European Union | Esther Corral Cutillas | UN Women CO staff and UN Women ACRO | 04/2021-03/2022 (deadline 01 March 2022) | n/a | n/a |
|  | Final report to UNOPS | Vanessa Sampaio | UN Women CO staff and UN Women ACRO | 08/2021-01/2022 (deadline 07 Jan 2022) | n/a | n/a |
|  | Interim narrative and financial report to Luxembourg | Mariana Salvadori | UN Women CO staff and UN Women ACRO | 01/2022-12/2022 (deadline 31 May 2023) | n/a | n/a |
|  | Interim narrative and financial report to OSF | Vanessa Sampaio | UN Women CO staff and UN Women ACRO | 05/2022-05/2023 (deadline 22 November 2023) | n/a | n/a |
|  | Inputs to final report MPTF-SDG Fund | Vanessa Sampaio | UNICEF, UN Women CO staff and UN Women ACRO | 01/2022 – 01/2022 (deadline 31 Jan 2022) | n/a | n/a |
|  | Interim report to Luxembourg (Moverse) | Mariana Salvadori | UNHCR, UNFPA, UN Women CO staff and UN Women ACRO | 09/2021 - 12/2021 (deadline 31 May 2022) | n/a | n/a |
|  | Interim narrative and financial report to Luxembourg | Mariana Salvadori | UN Women CO staff and UN Women ACRO | 01/2022-12/2022 (deadline 31 May 2023) | n/a | n/a |
|  | Interim narrative and financial report to OSF | Vanessa Sampaio | UN Women CO staff and UN Women ACRO | 05/2022-05/2023 (deadline 22 November 2023) | n/a | n/a |
| DRF Outcome 3.1 An enabling legislation, policy and social environment is in place to prevent and respond to VAWG | Final report to Austria | Joana Chagas and Carolina Ferracini | UN Women CO staff and UN Women ACRO | 11/2017-12/2017 (deadline 31 December 2017) | n/a | n/a |
|  | Final report to UNDP | Joana Chagas and Carolina Ferracini | UN Women CO staff and UN Women ACRO | 11/2017-12/2017 (deadline 31 December 2017) | n/a | n/a |
|  | Interim report to Procter and Gamble | Joana Chagas and Carolina Ferracini | Women Win, UN Women CO staff and UN Women ACRO | 12/2017-01/2018 (deadline 31 January 2018) | n/a | n/a |
|  | Final report to the IOC | Joana Chagas and Carolina Ferracini | Women Win, UN Women CO staff and UN Women ACRO | 02/2018-03/2018 (deadline 31 March 2018) | n/a | n/a |
|  | Final report to the Swedish Lottery | Joana Chagas and Carolina Ferracini | Women Win, UN Women CO staff and UN Women ACRO | 02/2018-03/2018 (deadline 31 March 2018) | n/a | n/a |
|  | Baseline study and M&E Plan – One Win Leads to Another | Joana Chagas and Carolina Ferracini | Women Win, Empodera, Fundo Elas, UN Women CO | 09/2018-10/2018 | IOC | 15,000 |
|  | Final report to Procter and Gamble | Carolina Ferracini | Women Win, UN Women CO staff and UN Women ACRO | 12/2018-01/2019 (deadline 31 January 2019) | n/a | n/a |
|  | Interim report to Instituto Avon | Carolina Ferracini | UN Women CO staff and UN Women ACRO | 03/2019-04/2019 (deadline 14 April 2019) | n/a | n/a |
|  | Final report to UNDP | Carolina Ferracini | UN Women CO staff and UN Women ACRO | 09/2019-10/2019 (deadline 30 October 2019) | n/a | n/a |
|  | First Interim report to the IOC (phase II) | Carolina Ferracini | Women Win, UN Women CO staff and UN Women ACRO | 11/2019-12/2019 (deadline 13 December 2019) | n/a | n/a |
|  | Final report to Instituto Avon | Carolina Ferracini | UN Women CO staff and UN Women ACRO | 11/2019-12/2019 (deadline 30 December 2019) | n/a | n/a |
|  | Progress Update on 2019 results to the IOC (phase II) | Carolina Ferracini and Raíssa Pereira | Empodera, Fundo ELAS, Women Win, UN Women CO staff and UN Women ACRO | 05/2020-08/2020 (deadline 31 August 2020) | n/a | n/a |
|  | First interim report to the EU | Camila Almeida and Aline Yamamoto | UN Women CO staff and UN Women ACRO | 12/2020-03/2021 (deadline 31 March 2021) | n/a | n/a |
|  | Second Interim report to the IOC (phase II) | Carolina Ferracini and Raíssa Pereira | Empodera, Fundo ELAS, Women Win, UN Women CO staff and UN Women ACRO | 03/2021 - 06/2021 (deadline 30 June 2021) | n/a | n/a |
|  | Second interim report to the EU | Débora Albu | UN Women CO staff and UN Women ACRO | 12/2021-03/2022 (deadline 31 March 2022) | n/a | n/a |
|  | Third Interim report to the IOC (phase II) | Gabriela Bastos | Empodera, Women Win, ICA, UN Women CO staff and UN Women ACRO | 02/2022 – 06/2022 (deadline 30 June 2022) | n/a | n/a |
|  | Final report to the IOC (phase II) | Gabriela Bastos | Empodera, Women Win, ICA, UN Women CO staff and UN Women ACRO | 07/2022 - 11/2022 (deadline 30 November 2022) | n/a | n/a |
|  | Final narrative and financial report to the EU | Débora Albu | UN Women CO staff and UN Women ACRO | 03/2022-01/2023 (deadline 31 July 2023) | n/a | n/a |
| DRF Outcome 4.1 Humanitarian responses (i.e Zika epidemic; Venezuelan migration) include a women’s rights perspective | Interim report to the Ford Foundation | Joana Chagas and Carolina Ferracini | UN Women CO staff and UN Women ACRO | 12/2017-01/2018 (deadline 31 January 2018) | n/a | n/a |
|  | Final report to CERF | Joana Chagas and Liliam Huzioka | UN Women CO staff and UN Women ACRO | 11/2018-12/2018 (deadline 8 January 2019) | n/a | n/a |
|  | Final report to the Ford Foundation | Joana Chagas and Carolina Ferracini | UN Women CO staff and UN Women ACRO | 12/2018-01/2019 (deadline 31 January 2019) | n/a | n/a |
|  | Final report to CERF | Joana Chagas and Liliam Huzioka | UN Women CO staff and UN Women ACRO | 06/2019-07/2019 (deadline 8 July 2019) | n/a | n/a |
| OEEF Output 4.3 Increased UN Women CO communication capacity | Final report to Banco Itaú | Ana Carolina Querino and Adriana Carvalho | UN Women CO staff and UN Women ACRO | 06/2018-07/2018 (deadline 31 July 2018) | n/a | n/a |
|  | UN Women Brazil CO Strategic Note 2017-2022 report | Joana Chagas | UN Women CO staff and UN Women ACRO | 09/2022-03/2023 | Core | USD 3720 |

Research Plan 2017-2023

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount |
| RESEARCH |  |  |  |  |
| Research on the gender pay gap | Aliança Member companies | 2017-2018 | Non-core fund | 20,000 |
| Annual Report on the Social-Economic Situation of Women (5.2.1.2) | Ministry of Women, Racial Equality and Human Rights | 2017-2021 | n/a | n/a |
| Case study on the pilot implementation of the curriculum “The Brave is not Violence” in schools (3.1.1.2) | SPM/BA | 2018 | Non-core fund | 20,000 |
| Research on the costs of Violence against Women in CASSEMS (3.1.2.2) | PAHO/WHO, CASSEMS | 2018 | Core funds Non-core fund | 10,000 27,778 |
| Research on companies that buy from women and barriers faced by women to sell to companies | UN Women HQ and FGV | 2018-2019 | Non-core fund | 10,000 |
| Analytical report on women and social protection (2.1.1.6) | IPEA | 2019 | Core Funds | 4,000 |
| Analytical report on gender, macroeconomic policies and women´s empowerment (2.3.3.1) | IPEA, ENAP | 2019 | Core funds | 3,000 |
| Research on companies’ role to end violence against women | ILO/ PAHO | 2019 | Non-core fund | 3,500 |
| Mapping of existing methodologies on measuring gender pay gap (2.1.1) | UN Women, ILO | 2019 | Non-core Funds | 30,000 |
| Research on cotton farming, local development and women’s empowerment in Bahia (2.1.1.6) | UN Women | 2020 | Non-core funds | 11,000 |
| Impacts of COVID on black, indigenous and quilombola women | APIB, CONAQ | 2020 | Core funds | $10,000 |
| Analytical report on COVID impacts on domestic workers | UN Women, IPEA | 2020 | Non-core funds | 1,000 |
| Research on the impact of interiorization in the livelihood of migrant and refugee from Venezuela, with gender perspective. | UN Women, UNHCR, UNFPA, OBMigra/UnB | 2020-2021 | Non-core funds | 25,000 |
| Research on COVID impacts in the migrant and refugee socioeconomic integration | UN Women, UNHCR, IOM, Unicamp, PUC/MG | 2020-2021 | Non-core funds | 5,000 |
| Research on social protection gaps for women who are primary caretakers for children beneficiary of Happy Child Programme | UN Women | 2020-2021 | Non-Core Funds | 20,000 |
| Analytical report on Women’s Political Participation and performance in the 2020 Municipal Election | UN Women | 2020-2021 | Non-core funds | 2,000 |
| Analytical report on VAW in Politics in the 2020 Municipal Elections | UN Women | 2020-2021 | Non-core funds | 2,000 |
| Rapid Gender Assessment Survey – Impacts of COVID-19 | UN Women and IPEA | 2020-2021 | n/a | n/a |
| Country Gender Equality Profile (CGEP) | UN Women | 2021 | Core funds | 10,000 |
| First Wave of Social Perception Survey of WHRDs | UN Women | 2021 | Non-Core | 31,000 |
| Annual report on the types of obstacles, attacks/violence and other human rights violations against WHRDs in Brazil | UN Women | 2021 | Non-Core | 6,000 |
| Case study on the implementation of LEAP joint programme | UN Women | 2021 | Non-core funds | (staff time) |
| Toolkit: initiatives for migrant and refugee women protection and empowerment | UN Women, INESC | 2020-2021 | Non-core funds | TBD |
| Women during the pandemic (Unstereotype Alliance) | UN Women, Maternativa | 2021 | Non-core funds | 5,000 |
| Todxs – diversity in marketing (Unstereotype Alliance) | UN Women and Unstereotype Alliance members | 2020 - 2021 | Non-core funds | 5,000 |
| Women entrepreneurs in the pandemic (win win) | UN Women, Rede Mulher Empreendedora | 2021 | Non-core funds | 10,000 |
| Research on Parental Leave (win win) | UN Women | 2021 | Non-core funds | (Staff time) |
| The Relocation Strategy for Venezuelan refugees, asylum seekers and migrants in Brazil during Covid-19 pandemic: building evidence to inform gender responsive policy making | UN Women | 2022 | Non-core funds | TBD |
| Limites e desafios à integração local de refugiadas, refugiados e pessoas migrantes da Venezuela interiorizadas durante a pandemia de Covid-19 - II | UN Women | 2022 | Non-core funds | TBD |
| Research on economic autonomy of rural women in Latin America and the Caribbean | ABC, FLACSO, IICA | Feb-Oct 2023 | Non-core | USD 90,000 |
| Technical Documents on the contribution of women to national development strategies | ABC | Nov 2022-Jan 2023 | Non-core funds | USD 7.780 |
| Research on production and data analysis on women | ABC | Jan-Ago 2023 | Non-core funds | USD 39,000 |
| Voluntary Relocation Programme Research: Third wave | UNFPA, UNCHR, CEDEPLAR | Jan-Nov 2023 | Non-core funds | USD 45,000 |
| IPSOS research Second Wave | IPSOS | Jan-Nov 2023 | Non-core funds | USD 12,335 |
| “’Não sou a única, nem a primeira, nem a última’”, paper on the pilot experience in promotion of collective care in WHRDs mental health | UN Women | Jun 2022-May 2023 | Non-core funds | TBD |

Evaluation Plan 2017-2023

| Evaluation name | Mandatory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ MCO/ RO AWP Output | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |
| Evaluation 1: Final Evaluation of Programme One Win Leads to Another (phase 1) | Y | UN Women SP Outcomes 4 | SN Output 3.1.2 | Brazil CO | Brazil | N | Bola pra Frente, Olympic Vilas, Subnational authorities | May - June 2017 | US$ 20,000 Non-core funds | Cancelled | The CO decided to conduct a self-evaluation. |
| Evaluation 2: Final Evaluation of Programme Strengthening public policies for women | Y | UN Women SP Outcomes 1, 2, 3, 4 and 5 | SN Output 1.1.1, 1.1.2, 1.2.1, 1.3.1, 2.1.1, 2.1.2, 2.1.3, 3.1.1, 3.1.2, 4.1.1 | Brazil CO | Brazil | N | National Secretariat for Policies for Women (SPM) | November-December 2021 | US$ 35,000 Non-core funds | Cancelled | The Programme was terminated, and the evaluation was cancelled. |
| Evaluation 3: Final Evaluation of Programme One Win Leads to Another (phase 2) | Y | UN Women SP Outcomes 4 | SN Output 3.1.2 | Brazil CO | Brazil | N | International Olympic Committee, National Olympic Committee, Women Win, Empodera, REMS, ICA, NGO partners | October-November 2020 | US$ 25,000 Non-core funds | Completed | The final evaluation was conducted as part of the Country Portfolio Evaluation. |
| Evaluation 4: Final Evaluation of Country Programme | N | UN Women SP Outcomes 1, 2, 3, 4 and 5 | SN Output 1.1.1, 1.1.2, 1.2.1, 1.3.1, 2.1.1, 2.1.2, 2.1.3, 3.1.1, 3.1.2, 4.1.1 | Brazil CO | Brazil | N | National and subnational authorities and partners, CSAG, UNCT | December 2020 - April 2021 | US$ 25,000 Core funds (ACRO) | Completed | It was co-financed and led by IEAS. Postponed to Nov 2021 – May 2022 due to extension of the Strategic Note. |
| Evaluation 5: Final Evaluation of Programme Win Win: gender equality means good business | Y | Impacts 2 Outcome 2.1 | All under Impacts 2 | Brazil CO | Brazil | Y ILO | Private sector partners, civil society organizations | November-December 2020 | US$50,000 Non-core funds | Completed | Evaluation was managed by UN Women Brazil CO, although initially planned to be managed by ILO and ACRO. The evaluation was postponed until April-August 2021 following a No Cost Extension. |
| Evaluation 6: Final Evaluation of Programme Connecting Women, Defending Rights | Y | UN Women SP 2022-2025 Outcome 5 | SN Output 3.1.2 | Brazil CO | Brazil | N | Criola, European Union | Dec 2023 - Apr 2024 | US$12,000.00 Non-core funds | Initiated | Initially planned for 2022, postponed to 2023 following the cost extension with the EU. Reclassified as an “assessment” as agreed with donor, with a simplified scope and a focus only on relevance, effectiveness and efficiency. |
| Evaluation 7: Final Evaluation of Human Rights of Indigenous and Quilombola Women: A Governance Matter | Y | UN Women SP 2022-2025 Outcome 1 | SN Output 1.1.1 | Brazil CO | Brazil | N | Government of Norway | Dec 2023 – Mar 2024 | US$40,000.00 Non-core funds | Initiated |  |
| Evaluation 8: Final Evaluation of Economic Empowerment of Refugee and Migrant Women in Brazil | Y | UN Women SP 2022-2025 Outcome 2 | SN Output 2.1.1 | Brazil CO | Brazil | Y UNHCR UNFPA | Government of Luxembourg | Dec 2023 – Feb 2024 | US$15,000.000 Non-core funds | Initiated | Reclassified as an “assessment” as agreed with donor, with a simplified scope and a focus only on coherence, effectiveness, and sustainability. |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |
| Evaluation 1: Mid-term Evaluation of Programme Win Win: gender equality means good business | Y | Impacts 2 Outcome 2.1 | All under Impacts 2 | Brazil CO | Brazil | Y ILO | Private sector partners, civil society organizations | April - June 2019 | US$70,000 Non-core funds | Completed | The evaluation was postponed until October-December 2019 due extended hiring process and change of personnel. |
| Evaluation 2: Final Evaluation of the United Nations Sustainable Development Partnership Framework 2017-2021 | Y | UN Women SP Outcomes 1, 2, 3, 4 and 5 | SN Output 1.1.1, 1.1.2, 1.2.1, 1.3.1, 2.1.1, 2.1.2, 2.1.3, 3.1.1, 3.1.2, 4.1.1 | Brazil CO | Brazil | Y UNCT | UNCT, government partners, civil society organizations | March-June 2020 | US$20,000 Non-core funds | Completed | The evaluation was postponed to 2021/2022 due to other emerging priorities related to COVID-19. |
| Evaluation 3: Final independent, gender responsive evaluation of Scaling up the Happy Child programme | Y | Impact 2 Outcome 2.1 | All under Impact 2 | UNDP Brazil | Brazil | Y UNDP UNICEF UNESCO UNFPA RCO | Federal Government (Ministry of citizenship) | September-December 2021 | 0 | Completed |  |