# Annex 1: 2012-2013 MONITORING, EVALUATION AND RESEARCH (MER) PLAN

Note: As per the Guidance “How to develop UN WOMEN Monitoring, Evaluation and Research (MER) Plans”, MER Plans are developed at country, sub-regional and regional level. The development of MER Plan needs to be closely linked with the development of Annual Work Plans.

| Title & Type of MER activity | Mandatory (Y/ N) | Relevant UNDAF Outcome/ UN Women SP Goal and Outcome | Relevant Country/ SRO AWP Output | Office to manage the MER activity | Region, Sub Region or Country | Joint MER activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-completion) | Budget (US$) for MER activity/ Sources of Funding | Status (pending - initiated – ongoing - completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2013 |  |  |  |  |  |  |  |  |  |  |  |
| 1) MONITORING activities undertaken by the Country/ Sub-regional/ Regional Office e.g. Partner visits, (Repeat) Baselines, Reviews, UN Women Annual Report, Annual Programme and UNDAF Review Process etc. |  |  |  |  |  |  |  |  |  |  |  |
| Complete the LAC’s monitoring tools | Y | Ecuador: UN WOMEN SP MRF 2 | AWP MR 2 | Ecuador | Ecuador | Y | UN Women LAC | Each month June 2013 Nov 2013 | Part of salaries staff (Core) | Ongoing |  |
| Complete the monitoring tool with information for each agreement and consultancy | Y | Ecuador: UN WOMEN SP MRF 2 | AWP MR 2 | Ecuador | Ecuador | N | Government institutions at national and local level. Women’s organizations | January 2013 – December 2013 | Part of salaries staff (Core) | Ongoing |  |
| Field visits and consultations/meetings with partners to review logical frameworks and track progress towards target | Y | Ecuador: UN WOMEN SP MRF 2 | AWP MR 2 | Ecuador | Ecuador | N | Government institutions at national and local level. Women’s organizations | January 2013 – December 2013 | Part of salaries staff (Core) | Ongoing |  |
| Final reports: GRB: AECID, UNV Indigenous Programme: UN WOMEN,AECID, BMZ, ACCD. | Y | Ecuador: UNDAF Result 7. UNWOMEN SP: Outcome 1.4 | Multicountry AWP: Output 1.1 and 3.1 | Ecuador | Ecuador | N | UNV Indigenous Organizations, women’s indigenous organizations, national and local State institutions, Regional Networks (FIMI, RMIB) | AECID: April 2013 UNV: Dic 2013 BMZ: August 2013 ACCD June 2013 | Part of salaries staff (Belgium Funds and UNV) | On going |  |
| Financial monitoring through Atlas and monitoring financial tables each month (Ecuador AWP) | Y | Ecuador: UN WOMEN SP MRF 2 | AWP MR 2 | Ecuador | Ecuador | N | Government institutions at national and local level. Women’s organizations | January 2013 – December 2013 | Part of salaries staff (Core) | Ongoing |  |
| Review process and production of a progress report on the UNDAF 2010-2014 | Y | UNWOMEN SP MRF 1 | AWP: MRF Output 1.1 | Ecuador | Ecuador | Y Interagency technical group monitoring Partners: CEF, UNFPA, PMA, UNICEF,ONU ONU MUJERES, PNUD, FAO, OPS, OACNUDH, OCR | SNU SENPLADES | January – July 2013 | ONU Mujeres technical support | On going |  |
| Monitoring activities of Gender Score Card | Y | UNWOMEN SP MRF 1 | Multicountry AWP: MRF Output 1.1 | Andean SRO | Ecuador | UNCT Gender Theme Group | SNU | Enero-diciembre | US$ 5,000 | Initiated |  |
| 2a) EVALUATIONS managed by the Country/ Sub-regional/ Regional Office e.g. outcome, thematic, programme evaluations etc. |  |  |  |  |  |  |  |  |  |  |  |
| 2b) Other EVALUATIONS in which Country/ Sub-regional/ Regional Office is involved but NOT managing, e.g. evaluations managed by HQ Evaluation Office, Trust Fund on VAW, UNDEF, donors, etc. |  |  |  |  |  |  |  |  |  |  |  |
| UN System Common Country Assessment | Y | UNWOMEN SP MRF 1 | AWP | OCR Ecuador | Ecuador | Y | UN System | May – December 2013 | ONU Mujeres technical support | On going |  |
| 3) RESEARCH Activities undertaken by the Country/ Sub-regional/ Regional Office with regard to the monitoring and evaluation needs of the Annual Work Plans |  |  |  |  |  |  |  |  |  |  |  |
| Mapping Organizations and NGO working for women´s rights | Y | UNWOMEN SP MRF 1 | AWP: MRF Output 1.2 | Ecuador | Ecuador | N | ONU Mujeres; Civil Society; Govern- ment; SNU; Coopera tion | January – June 2013 | 2012 Core Funds | Ongoing |  |
| Interagency online course on gender | Y | UNWOMEN SP MRF 1 | AWP: MRF Output 1.2 | Ecuador | Ecuador | Y Onu Mujeres Gender Theme Group | UNCT SNU | January – July 2013 | 2012 core Funds | On going |  |
| Case study on gender equality and cultural diversity policy (MDG Project on Cultural Diversity) | N | UNWOMEN SP MRF 1 | AWP: MRF Output 1.2 | Ecuador | Perú, Ecuador | Y | Ministry of cultural Heritage | May to June 2013 | US$ 10,000 from HQ | Ongoing |  |