MONITORING, EVALUATION AND RESEARCH PLAN 2023-2026

Kenya Country Office

- Monitoring and Research Plan 2023-2026

| Activity | UNSDCF Outcome/UN Women SP Outcome | SN Output/Relevant flagship program | Related indicator/KPI (Y/N, Indicator number, how and when) | Data Collection (Y/N, what data, how) | Office and Person in charge | Partners and stakeholders | Planned Dates (Month and year of start and end) | Donors Involved | Budget |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  | Source | Amount |
| MONITORING |  |  |  |  |  |  |  |  |  |  |
| Regular monitoring of all AWP activities across all outcomes (field monitoring by UN Women staff and IPs including data collection, review of IP reports etc) staff/projects meetings, and coordination meetings with implementing partners. | All SN Outcomes | All SN Outputs | All SN Indicators | Yes - Qualitative and quantitative data on implementation and reporting variance | KCO, - Planning, Monitoring, Evaluation & Reporting (PMER) Specialist - All team leaders/project focal points | KCO staff and Implementing partners | January 2023 – December 2026 | N/A | Non-Core Available | $40,000 |
| Mid-year review and AWP review meeting | All SN Outcomes | All SN Outputs | All SN Indicators | Yes - Data on implementation and reporting variance | KCO, - PMER Specialist | KCO staff | April, July, October, and January (2023 – 2026) | N/A | Non-Core Available | $10,000 |
| Mid-term review (MTR) of the SN | Yes | All SN Outcomes | All SN Outputs | KCO, PMER Specialist | ESARO, Kenya | Yes, All KCO donors and implementing partners | Q2 2024 | All KCO Donors | $25,000 | Pending |
| Donor monitoring missions | All SN Outcomes | All SN Outputs | All SN Indicators | Yes, - Interventions impacts - Donors’ perception and satisfaction levels with UN Women work in Kenya | KCO, - Country representative - Senior Management Team (SMT) - PMER Specialist | KCO Staff, Donors, GoK, Implementing Partners, Beneficiaries | January 2023 – December 2026 | All KCO Donors | Non-Core Available | $40,000 |
| Annual Outcome/results harvesting with IPs | All SN Outcomes | All SN Outputs | All SN Indicators | Yes, - All SN indicators | KCO, - PMER Specialist | KCO Staff, Implementing Partners | November (2023 – 2026) | N/A | Non-Core Available | $40,000 |
| Quarterly and annual reporting on SN implementation in RMS and donor reports | All SN Outcomes | All SN Outputs | Percentage of UN Women corporate and donor reports meeting RBM standards submitted in RMS on time | Yes, - Quality of reports produced - Timeliness of reports submission | KCO, - PMER Specialist | KCO Staff | April, July, October, and January (2023 – 2026) | N/A | N/A | N/A |
| Data collection through KOBO collect | All SN Outcomes | All SN Outputs | Number of Business Process improvement and innovation initiatives (major policy revisions are included), as part of UN-Women’s continuous business transformation | Yes, - Number of KCO beneficiaries - Impacts of KCO interventions | KCO, - PMER Specialist | KCO Staff, Implementing Partners | June 2023 – December 2023 | N/A | Non-Core Available | $15,000 |
| Concluded in 2023: Baseline survey of the KCO SN 2023-2026 | All SN Outcomes | All SN Outputs | All SN Indicators | Yes, Baseline data of all SN indicators | KCO, PMER Specialist | KCO Staff, Donors, GoK, Implementing Partners, Beneficiaries | January – December 2023 | All KCO Donors | Non-Core Available | $35,000 |
| RESEARCH |  |  |  |  |  |  |  |  |  |  |
| Common Country Assessment for Kenya | All UNSDCF Outcomes | All UNSDCF Outputs | All UNSDCF Indicators | Yes, - GEWE development status in Kenya | KCO, - PMER Specialist | KCO Staff, Donors, GoK, UN Agencies/ UNCT | 2025 | All KCO Donors | Non-Core Available | N/A |
| Support baseline, annual assessments, special studies of the UNSDCF 2022-2026 | All UNSDCF Outcomes | All UNSDCF Outputs | All UNSDCF Indicators | Yes, - Baseline data of all SN indicators | RCO Kenya, - PMER Specialist Head of M&E | KCO Staff, Donors, GoK, UN Agencies/ UNCT | January 2023 – December 2026 | All KCO Donors | Non-Core Available | N/A |

- Evaluation Plan 2023-2026

| Evaluation name | Mandatory (Y/N) | UNSDCF Outcome/ UN Women SP Outcome and relevant SDGs | SN Output/ Relevant flagship program | Office and Person in charge | Region/ country | Joint activity (Y/N, indicate partners) | Planned Dates (start-end) | Donors Involved | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations in which the office leads |  |  |  |  |  |  |  |  |  |  |  |
| Country Portfolio Evaluation of SN 2023-2026 | Yes | All SN Outcomes | All SN Outputs | KCO, PMER Specialist | ESARO, Kenya | Yes, All KCO donors and implementing partners | Early 2026 | All KCO Donors | $40,000 | Pending | Mid 2026 |
| End line evaluation of the Italy funded project- “LET IT NOT HAPPEN AGAIN PROJECT” 2019-2023 | Yes | All Italy project outcomes | All Italy Project Outputs | KCO, PMER Specialist | ESARO, Kenya | Yes, All Italy project implementing partners | 2nd June 2023 and will end on 30th Nov 2023 Kes.1,500,000 | Italy | $11,000 | Ongoing | Ongoing and will be concluded by 30th November 2024 |
| End-line evaluation for the Finland-funded Programme 2020 -2023 | Yes | All Finland Programme Outcomes | All Finland Programme Outputs | KCO, PMER Specialist | ESARO, Kenya | Yes, All Finland project implementing partners | The evaluation started in September 2023 end in November 2023 | Finland | $50,000 | Ongoing | Ongoing- to be concluded on 30th November, 2023 |
| Mid-term evaluation for the KOICA-funded WEE-CSA Programme 2020 -2023 | Yes | All WEE-CSA Project Outcomes | All WEE-CSA Project Outcomes | KCO, PMER Specialist | ESARO, Kenya | Yes, All WEE-CSA project implementing partners | Mid 2023 This evaluation was replaced by the impact Evaluation Baseline Study. | KOICA | $30,000 | Pending- Replaced on donor request | Mid 2023 This evaluation was replaced by the impact Evaluation Baseline Study. |
| End-line evaluation for the KOICA-funded WEE-CSA Programme 2020 -2023 | Yes | All WEE-CSA Project Outcomes | All WEE-CSA Project Outcomes | KCO, PMER Specialist | ESARO, Kenya | Yes, All WEE-CSA project implementing partners | Start February end June 2024 | KOICA | $30,000 | Pending | Quarter 1 of 2024 |
| End-line evaluation for the Japan-funded LEAP III Programme 2021 -2023 | Yes | All LEAP III Project Outcomes | All LEAP III Project Outcomes | KCO, PMER Specialist | ESARO, Kenya | Yes, All LEAP III project implementing partners | Started in October, end November 2023 | Japan | $20,000 | Ongoing | Started in October 2023 and will be concluded by 30th November 2023. |
| End-line evaluation for the Canada-funded Enhancing women's political participation in political leadership and decision-making Programme 2021 -2025 | Yes | All Canada Project Outcomes | All Canada Project Outcomes | KCO, PMER Specialist | ESARO, Kenya | Yes, All Canada project implementing partners | Start July and end December 2024 | Canada | $30,000 | Pending | End of 2024 |
| End line evaluation for the Italy funded project - LET IT NOT HAPPEN AGAIN. Safeguarding the Rights of Women Through Strengthening Access to Justice for GBV Survivors in Kenya May June 2022 to May 2026 | Yes | All Italy project outcomes | All Italy Project Outputs | KCO, PMER Specialist | ESARO, Kenya | Yes, All Italy project implementing partners | Start June and end in November 2023 | Italy | $15,000 | Pending | End of 2023 |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |
| Mid-term evaluation of the UNSDCF 2022-2026 | Yes | All UNSDCF Outcomes | All UNSDCF Outputs | RCO Kenya, Head of M&E | ESARO, Kenya | Yes, All Un Agencies | 2024 | All UNCT Donors | N/A | Pending | Late 2024 |
| End of project evaluation for the Consolidating Gains and Deepening Devolution in Kenya 2020 - 2023 | Yes | All JP-Devolution Project Outcomes | All JP-Devolution Project Outputs | UNDP, Head of M&E | ESARO, Kenya | Yes, UNDP, UNICEF, UN WOMEN | 2024 | All project Donors | $10,000 | Non-Core Available | Joint intervention and contribution by the three agencies. UN Women is not leading in this evaluation and is not custodian of the budget-UNDP is. |

Including the review of the TOC

Due to challenges on ownership and cost required to maintain the database, KCO opted to utilize Kobo Collect and invest in data collection tablets. This is based on the discussions with the HQ and what the KCO and the implementing partners have experience on

Outcomes contributing to the SDGs as per the Strategic Plan