# 2012-2013 MONITORING, EVALUATION AND RESEARCH (MER) PLAN

Morocco Multi-Country Office: Morocco, Tunisia and Algeria

Note: As per the Guidance “How to develop UN WOMEN Monitoring, Evaluation and Research (MER) Plans”, MER Plans are developed at country, sub-regional and regional level. The development of MER Plan needs to be closely linked with the development of Annual Work Plans.

| Title & Type of MER activity | Mandatory (Y/ N) | Relevant UNDAF Outcome/ UN Women SP Goal and Outcome |  |  | Relevant Country/ SRO AWP Output |  | Office to manage the MER activity |  | Region, Sub Region or Country |  | Joint MER activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-completion) | Budget (US$) for MER activity/ Sources of Funding | Status (pending - initiated – ongoing - completed) |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2012 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1) MONITORING activities undertaken by the Country/ Sub-regional/ Regional Office e.g. Partner visits, (Repeat) Baselines, Reviews, UN Women Annual Report, Annual Programme and UNDAF Review Process etc. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Meetings of Technical committee: the technical committee ensures monitoring of the project from a technical perspective (advancement of activities implementation and supervision of program’s implementation), the meeting reports are used for monitoring and include the decisions and recommendations of the technical commission Project : "Support the implementation of the family code by the facilitation of women's access to justice services” - Gender and Democratic Governance “ | Y | UNDAF Outcome 4 :Institutional partners and civil society appropriate principles of gender responsive democratic governance and implement them for an integrated, equitable and sustainable human development. |  | Outcome 3 / Output 3.2 : Prevent violence against women and girls and expand access to victim/survivor services |  |  | Morocco |  | NASRO |  | Y with ministry of Justice | PMU/GDG Ministry of Justice and Freedoms, Ministry of Solidarity, Woman, Family and Social DevelopmentandCS0s | Monthly | NA | completed |  |  |
| Meeting of steering committee: the steering committee provides guidance, direction and control on the strategic orientations of the programme and the annual monitoring. A meeting report is produced and used to monitor the decisions and recommendations of the steering committee Project : "Support the implementation of the family code by the facilitation of women's access to justice services” - Gender and Democratic Governance - (75424) | Y | UNDAF Outcome 4 : Institutional partners and civil society appropriate principles of gender responsive democratic governance and implement them for an integrated, equitable and sustainable human development. |  | Outcome 3 / Output 3.2 : Prevent violence against women and girls and expand access to victim/survivor s services |  |  | Morocco NA SRO |  | NASRO |  | Y (UNWomen Ministry of Justice and Freedoms; Pilot Family Justice Sections; Ministry of Solidarity, Woman, Family and Social Development , and Local NGOs) | UNWomen Ministry of Justice and Freedoms; Pilot Family Justice Sections; Ministry of Solidarity, Woman, Family and Social Development , and Local NGOs | Annual/July | NA | Completed on May 8th 2013 |  | It has been postpone to early 2013, because of the busy agenda of the ministry of Justice, which engaged in the process of mobilization for the reforme of Justice |
| Monitoring missions on the field Project : Mission reports are produced "Support the implementation of the family code by the facilitation of women's access to justice services” - Gender and Democratic Governance - (75424) | N | UNDAF Outcome 4 : Institutional partners and civil society appropriate principles of gender responsive democratic governance and implement them for an integrated, equitable and sustainable human development. |  | Outcome 3 / Output 3.2 : Prevent violence against women and girls and expand access to victim/survivor s services |  |  | Morocco NA SRO |  | NASRO |  | Y (UNWomen Ministry of Justice and Freedoms; Pilot Family Justice Sections; Ministry of Solidarity, Woman, Family and Social Development , and Local NGOs) | PMU/GDG WOMEN Ministry of Justice and Freedoms, Pilot Family Justice Sections; Ministry of Solidarity, Woman, Family and Social Development | April- May | 5000 US$ | Completed |  | 05 missions on 2 months |
| Closing workshop The workshop report was produced. It includes the recommendations and possibilities to duplicate the project in other regions In Guelmim MDG Culture: project “Cultural Heritage and Creative Industries as Vehicles for Development in Morocco” (63003 | Y | UNDAF outcome 3 vulnerability and inequality, in particular those related to gender are reduced by supporting policies / strategies and programs of economic and social development |  | Outcome 2: DRF: 2.4.2 Outcome 5 DRF: 5.2.3 |  |  | Morocco NA SRO |  | NASRO |  | Y. UNWomen UNESCO, UNDP, UNIDO | UNWomen, UNESCO, UNIDO, UNDP, UNFPA Ministry of Culture, Agency for the Socioeconimic Development of the Southern Provinces (Programme Oasis South); NGOs and women's cooperatives in 9 communes | June 20 July 2 | Budget paid by UNESCO | Completed |  | closing workshop is aimed to present the results of the program and was an opportunity to explore ways to duplicate the programme in other regions of the coutry. |
| Field mission The workshop report was produced. It includes the recommendations and possibilities to duplicate the project in other regions Closing workshop Project: Strengthening women's role in local governance through Communal Development Plans ( GuelmimEsSmara Region) | N | UNDAF outcome 3 vulnerability and inequality, in particular those related to gender are reduced by supporting policies / strategies and programs of economic and social development |  | Outcome 2 Output : 2.4.2 Outcome 5 output: 5.3.1 |  |  | Morocco |  | NASRO |  | Y. UNWomen UNESCO, UNDP, UNIDO | UNWomen, UNESCO, UNIDO, UNDP, UNFPA Ministry of Culture, Agency for the Socioeconimic Development of the Southern Provinces (Programme Oasis South); NGOs and women's cooperatives in 9 communes | May 28th July 20 | Budget paid by UNESCO | Completed |  | closing workshop is aimed to present the results of the program and was an opportunity to explore ways to duplicate the programme in other regions of the coutry. |
| Meetings to update the programme following the political context changes(New constitution, new government…) 14 meetings Meeting reports are available. They include the decisions on the changes in the programme Programme : Public Governance and Accountability | Y | UNDAF Outcome 3: vulnerability and inequality, in particular those related to gender are reduced by supporting policies / strategies and programs of economic and social development & outcome 4 Institutional partners and civil society appropriate principles of gender responsive democratic governance and implement them for an integrated, equitable and sustainable human development. UNWomen SP Outcome 5 |  | Output 5.1.1 National partners have enhanced knowledge, tools and skills to reframe the gender equality agenda and establish a policy setting and a monitoring and accountability system for its implementation |  |  | Morocco |  | NASRO |  |  | Ministry of Employment & Professional Training, Interministrial Delegation for Human Rights, Ministry of Modernization of the Public Sector, Machinary of Women, Ministry of General Affairs and Governance Ministry of Communication, Human Rights Council | May-April- June 2012 | NA | Completed |  |  |
| Monitoring Committese of studies held in the programme Reports including the decisions are produced during each meeting Programme : Public Governance and Accountability | Y | UNDAF Outcome 3: vulnerability and inequality, in particular those related to gender are reduced by supporting policies / strategies and programs of economic and social development & outcome 4 Institutional partners and civil society appropriate principles of gender responsive democratic governance and implement them for an integrated, equitable and sustainable human development. UNWomen SP Outcome 5 |  | Output 5.1.1 National partners have enhanced knowledge, tools and skills to reframe the gender equality agenda and establish a policy setting and a monitoring and accountability system for its implementation |  |  | Morocco |  | NASRO |  | Yes with all the partners | Delegation for Human Rights, Ministry of Modernization of the Public Sector, Machinry of Women, Ministry of General Affairs and Governance Ministry of Communication, Human Rights Council Machinery of Women: Ministry of Employment and Professional Training: Ministry of Communication | Ministry of Public Service & Modernization of the Administration: February, March, May, July & August Machinery of Women: May, June, July, November Ministry of General Affairs and Governance: May, June, August, September National Council of Human Rights: January, March Ministry of Employment & Professional Training: October, December Ministry of Communication : July, September, November | NA | Completed |  |  |
| Monitoring meeting of the interministerial consultation network of gender mainstreaming in the public administration HR Meeting reports are produced Programme : Public Governance and Accountability | Y | UNDAF Outcome 3: vulnerability and inequality, in particular those related to gender are reduced by supporting policies / strategies and programs of economic and social development & outcome 4 Institutional partners and civil society appropriate principles of gender responsive democratic governance and implement them for an integrated, equitable and sustainable human development. UNWomen SP Outcome 5 |  | Output 5.1.1 National partners have enhanced knowledge, tools and skills to reframe the gender equality agenda and establish a policy setting and a monitoring and accountability system for its implementation |  |  | Morocco |  | NASRO |  | Y with Ministry of Public Service and Modernization of the Administration | 24 ministries:1 Ministry of Economy and Finance 2.Ministry of Public Service and Modernization of the Administration 3.Ministry of Justice & Liberties 4.Ministry of Interior 5Ministry of Infrastructure and Transport 6.Ministry of Foreign Affairs and Cooperation 7.Ministry of General Affairs & Governance 8.Ministry of Islamic Affairs 9.Ministry of Health 10.Ministry of National Education 11.Ministry of Higher Education, Scientific Research and Superior Training 12.Ministry of Habitat, Urbanization and Policy of the City 13.Minister of Agriculture and Maritime Fisheries 14.Ministry of Youths and Sports 15.Ministry of Communication 16.Ministry of Energy, Mines, Water and Environment 17.Ministry of Employment and Professional Training 18.Ministry of Industry, Trade and New Technologies 19.Ministry of Tourism 20.Machinry of Women 21.Ministry of Culture 22.Ministry of Crafts 23.Ministry in charge of the Moroccan community abroad 24.Ministry in charge of Relations with Parliament and Civil Society | 2 meetings held February March and 2 meetings on November | US$500 | completed |  |  |
| Monitoring Committee A report will be produced, it should include the decisions of the committee and its recommendations ProgrammePublic Governance and Accountability |  | UNDAF Outcome 3: vulnerability and inequality, in particular those related to gender are reduced by supporting policies / strategies and programs of economic and social development & outcome 4 Institutional partners and civil society appropriate principles of gender responsive democratic governance and implement them for an integrated, equitable and sustainable human development. UNWomen SP Outcome 5 |  | Output 5.1.1 National partners have enhanced knowledge, tools and skills to reframe the gender equality agenda and establish a policy setting and a monitoring and accountability system for its implementation |  |  | NASRO |  | Morocco |  | Y | Ministry of Employment and Professional Training, Ministry of Public Service and Modernization of the Administration, Machinery of women, Ministry of Finance, National Council of Human Rights, Interministerial Delegation of Human Rights | 1st meeting was scheduled on June 2012, but did not take place. We do not have the new date yet. The frequency of upcoming meetings will be defined on the first meeting | NA | canceled |  | This activity was not held since there was no visibility on the funds from the Spanish Government. Since this activity concerns mainly the monitoring of the recommandations of the studies produced in the programme |
| Field Visit “MultiSectoralProgramme for the Fight Against Gender Based Violence Through the Empowerment of Women and Girls in Morocco (58215) Project : "Support the implementation of the family code by the facilitation of women's access to justice services” - Gender and Democratic Governance (75424) |  | UNDAF outcome 3 vulnerability and inequality, in particular those related to gender are reduced by supporting policies / strategies and programs of economic and social developmentSP goal 2, 3, 5 SP Outcome 2, 3, 5 Outcome 4 Institutional partners & civil society appropriate principles of gender responsive democratic governance and implement them for an integrated, equitable & sustainable HDev. |  | Output 2.1 Output 3.3 Output 5.1 Output 5.2 Output 5.3. |  |  | Morocco NA SRO |  | Morocco |  | Y | UNRC, UNWomen, Spanish Cooperation Agency, Ministry of Foreign Affairs, Machinery of Women Ministry of Justice and Freedoms and Ministry of Solidarity, Woman, Family and SD, and MUP/UNW | 23-24 May 2012 Technical committee of the programm GDG meets monthly and meeting notes are established and disseminated | US$ 3000 Programme fund | Completed |  |  |
| Programme monitoring committee meeting The meeting report is used for monitoring “MultiSectoralProgramme for the Fight Against Gender Based Violence Through the Empowerment of Women and Girls in Morocco (58215) |  | UNDAF outcome 3 vulnerability and inequality, in particular those related to gender are reduced by supporting policies / strategies and programs of economic and social development SP goal 2, 3, 5 SP Outcome 2, 3, 5 |  | Output 2.1 Output 3.3 Output 5.1 Output 5.2 Output 5.3. |  |  | Morocco NA SRO |  | Morocco |  | Y | Machinery of Women, 8 UN Agencies, institutional partners and NGOs | July 2 | US$7000 | Completed |  |  |
| National Coordination Committee: Meeting report is used for monitoring “MultiSectoralProgramme for the Fight Against Gender Based Violence Through the Empowerment of Women and Girls in Morocco (58215) |  | UNDAF outcome 3 vulnerability and inequality, in particular those related to gender are reduced by supporting policies / strategies and programs of economic and social development SP goal 2, 3, 5 SP Outcome 2, 3, 5 |  | Output 2.1 Output 3.3 Output 5.1 Output 5.2 Output 5.3. |  |  | NASRO SRO |  | Morocco |  | Y | UNRC, UNWomen, Spanish Cooperation Agency, Ministry of Foreign Affairs, Machinery of Women | January 2012 February 14th, 2012 June 25th , 2012 | NA | Completed |  |  |
| Monitoring Committee - Program: Women Election Watch |  | UNDAF outcome 4 Institutional partners and civil society appropriate principles of gender responsive democratic governance and implement them for an integrated, equitable and sustainable human development. SP: Outcome 1 |  | Output 1.2 Gender equality advocates and their organizations have strengthened capacities to effectively influence local governments and service delivery organizations to promote gender equality. |  |  | Morocco |  | NASRO |  | N | 6 NGOs, Netherlands UNWomen | July 2012 & Novembr2012 Monitoring Committee meetings will be held every quarter starting | US$ 1000 | completed |  |  |
| Quarterly reports on the advancement of all the core &non core projects are sent to HQ. the quarterly includes target data. | Y |  |  |  |  |  | NASRO |  | NASRO |  | N | UNWomen | Every quarter | NA |  |  |  |
| UNWomen Annual report including AWP Baseline data collected | Y |  |  |  |  |  | NASRO |  | NASRO Morocco, Algeria, Tunisia, Mauritania |  |  |  | December - January | NA |  |  |  |
| 2a) EVALUATIONS managed by the Country/ Sub-regional/ Regional Office e.g. outcome, thematic, programme evaluations etc. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Final Evaluation of the “MultiSectoralProgramme for the Fight Against Gender Based Violence Through the Empowerment of Women and Girls in Morocco (58215) | Y | UNDAF Outcome 3 SP Outcome 2, 3 & 4 |  |  | output 2.1, 4.1, 5.3, 5.4, |  | Morocco NA SRO |  | Morocco |  | Y: UNFPA, UNICEF, UNESCO, UNHRC, UNAIDS, FAO, BIT | 13 national entities and 50 NGOs (Ministry of Foreign Affairs, Justice, Interior, (DGCL SureteNationale), Gendarmerie Royale, Economy and Finance, Employment, Health, Agriculture, Youth and Sports, Social Development Family & Solidarity, High Commission on Planning, Communication, and Religious Affairs. | April-May 2012 | US$ 48000 | Completed |  | Programme duration has been extended until May 28th 2012. The evaluation was managed by RC office, with the technical support and coordination of UNWomen - the lead agency - (funds in UNWomen). The TOR are given by the MDG Fund Secretariat. |
| Final Evaluation of the project “Cultural Heritage and Creative Industries as Vehicles for Development in Morocco” (63003) | Y | UNDAF outcome 3 vulnerability and inequality, in particular those related to gender are reduced by supporting policies / strategies and programs of economic and social development SP goal 2, 3, 5 SP Outcome 2, 3, 5 |  |  | Output 2.1 Output 3.3 Output 5.1 Output 5.2 Output 5.3. |  | Morocco NASRO |  | Morocco |  | Y. UNWomen UNESCO, UNDP, UNIDO | UNWomen, UNESCO, UNIDO, UNDP, UNFPA Ministry of Culture, Agency for the Socioeconimic Development of the Southern Provinces (Programme Oasis South); NGOs and women's cooperatives in 9 communes | End of July 2012 | NA | Completed |  | Programme extended to 28th August, 2012. The evaluation was managedby the RC office, with the technical support and coordination of UNESCO - the lead agency. The TOR are given by the MDG Fund Secretariat |
| 2b) Other EVALUATIONS in which Country/ Sub-regional/ Regional Office is involved but NOT managing, e.g. evaluations managed by HQ Evaluation Office, Trust Fund on VAW, UNDEF, donors, etc. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3) RESEARCH Activities undertaken by the Country/ Sub-regional/ Regional Office with regard to the monitoring and evaluation needs of the Annual Work Plans |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Satisfaction Survey of the supply of services in the implementation of the Family Code by the pilot family justice sections |  |  |  |  | Outcom Output 3.2 |  | NASRO |  | Morocco |  |  | Ministry of Justice and Liberties | January 2011- May 2012 | US$ 64 255,70 Non core funding | completed |  |  |
| Conducting a study of the principles and provisions of the CEDAW and the CRC in the context of the implementation of the Family Code |  |  |  |  | Outcome 3 Output 3.2 |  | NASRO |  | Morocco |  |  | Ministry of Justice and Liberties | September 2011-February 2012 | US$ 12 694,13 Non core funding | completed |  |  |
| Comparative analysis of family & child councils |  |  |  |  |  |  | NASRO |  | Morocco |  |  | UNWomen& National Council of Human Rights | January 2012 |  | completed |  |  |
| Research to identify the challenges and opportunities for the development of projects to support women political participation and economic empowerment |  |  |  |  | Outcome 1.1 Output 1.1.1 Outcome 2.2 Output 2.1 & 2.2 |  | NASRO |  | Tunisia |  | N | UNWomen | 2012 | US$ 25500 | Ongoing |  |  |
| Study on the place of women at the responsibility positions in the public administration Project: Gender and public accountability | Y | UNDAF Outcome 3: & 4 UNWomen SP Outcome 5 |  |  | Output 5.1.1 National partners have enhanced knowledge, tools and skills to reframe the gender equality agenda and establish a policy setting and a monitoring and accountability system for its implementation |  | Morocco |  | NASRO |  |  | Ministry of the Modernization of the Public Administration | February-November 2013 | 27 631 USD | Completed |  | A guide on the integration of gender in the recruitment processes was produced using the results of the study |
| 2013 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1) MONITORING activities undertaken by the Country/ Sub-regional/ Regional Office e.g. Partner visits, (Repeat) Baselines, Reviews, UN Women Annual Report, Annual Programme and UNDAF Review Process etc. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Quarterly reports on the advancement of all the core &non core projects | Y |  |  |  |  |  |  | Morocco | NASRO Morocco, Algeria, Tunisia, |  |  |  | Every quarter | NA | Ongoing |  |  |
| UNWomen Annual report | Y |  |  |  |  |  |  | Morocco | Morocco, Algeria, Tunisia, |  |  |  | December - January | NA |  |  |  |
| Monitoring Committee – meetings of UNWomen, the donor and NGOs to monitor the implementation of the programme and to provide guidance to meet the results. A meeting report will be produced for monitoring Program: Women Election Watch |  | UNDAF outcome 4 Institutional partners and civil society appropriate principles of gender responsive democratic governance and implement them for an integrated, equitable and sustainable human development. SP: Outcome 1 |  |  | Output 1.2 Gender equality advocates and their organizations have strengthened capacities to effectively influence local governments and service delivery organizations to promote gender equality. |  |  | Morocco | MCO Maghreb |  | N | 6 NGOs, Netherlands UNWomen | January 2013 July 2013 every 6 months | US$2400 | Ongoing |  | At least 2 programme meetings to be held in 2013 |
| Field visits : participation in the programme’s activities Mission reports will be used for monitoring Program: Women Election Watch |  | UNDAF outcome 4 Institutional partners and civil society appropriate principles of gender responsive democratic governance and implement them for an integrated, equitable and sustainable human developmt SP: Outcome 1 |  |  | Output 1.2 Gender equality advocates and their organizations have strengthened capacities to effectively influence local governments and service delivery organizations to promote gender equality. |  |  | Morocco | MCO Maghreb |  | UNWomen | 6 NGOs, Netherlands UNWomen | 10 activities have been held The frequency and dates will be determined by the partners | US$2000 | Ongoing Participation in 10 workshops, trainings, Press conference (Rabat & Casablanca) |  |  |
| Monitoring Committees of the projects: studies and implementation of the recommendation Reports including the decisions are produced during each meeting Programme : Public Governance and Accountability | Y | UNDAF Outcome 3: vulnerability and inequality, in particular those related to gender are reduced by supporting policies / strategies and programs of economic and social development & outcome 4 Institutional partners and civil society appropriate principles of gender responsive democratic governance and implement them for an integrated, equitable and sustainable human development. UNWomen SP Outcome 5 |  |  | Output 5.1.1 National partners have enhanced knowledge, tools and skills to reframe the gender equality agenda and establish a policy setting and a monitoring and accountability system for its implementation |  |  | Morocco | MCO Maghreb |  | Yes with all the partners | Delegation for Human Rights, Ministry of Modernization of the Public Sector, Machinry of Women, Ministry of General Affairs and Governance Ministry of Communication, Human Rights Council Machinery of Women: Ministry of Employment and Professional Training: Ministry of Communication | The meetings are held for each project with the concerned partners (meeting per month for each project) | NA | Ongoing |  |  |
| The technical committee provides direct and constant support to the project. A meeting report is produced and used to monitor the decisions and recommendations of the technical committee. Project: “Improve the access of women and children victim of human trafficking to judicial services in Morocco.” | Y | UNDAF Outcome 4 & 3 SP Outcome 3.1 |  |  | SP Output 3.1.1 |  |  | Morocco | MCO-Maghreb |  | Y with ministry of Justice | Ministry of Justice and Freedoms | Monthly | NA | ongoing |  |  |
| The steering committee provides guidance, direction and control on the strategic orientations of the project. It approves the directions and adjustments recommended or initiated by the technical committee. Project: “Improve the access of women and children victim of human trafficking to judicial services in Morocco.” | Y | UNDAF Outcome 4 & 3 SP Outcome 3.1 |  |  | SP Output 3.1.1 |  |  | Morocco | MCO-Maghreb |  | Ministry of Justice and Freedoms And the Swiss Cooperation DDC, UNWomen | Ministry of Justice and Freedoms And the Swiss Cooperation DDC, UNWomen | May 2013 November 2013 Every 6 months | NA | Ongoing |  |  |
| Meetings of Technical committee: the technical committee ensures monitoring of the project from a technical perspective (advancement of activities implementation and supervision of program’s implementation), the meeting reports are used for monitoring and include the decisions and recommendations of the technical commission Project : "Support the implementation of the family code by the facilitation of women's access to justice services” - Gender and Democratic Governance “ | Y | UNDAF Outcome 4 : Institutional partners and civil society appropriate principles of gender responsive democratic governance and implement them for an integrated, equitable and sustainable human development. |  |  | Outcome 3 / Output 3.2 : Prevent violence against women and girls and expand access to victim/survivor services |  |  | Morocco | MCO Maghreb |  | Y with ministry of Justice | PMU/GDG Ministry of Justice and Freedoms, Ministry of Solidarity, Woman, Family and Social Development and CS0, UNWomen | Monthly | NA | Ongoing |  |  |
| Project: “Joint Initiative Marrakech Safe and friendly city for all (SFC)” Steering committee meetings: The steering committee (SC) provides guidance, direction and control on the strategic orientations of the programme and the annual monitoring. A meeting report is produced and used to monitor the decisions and recommendations of the SC. Meetings take place in Marrakech. Inter agencies meetings: monitoring of the project (advancement of activities implementation and supervision of program’s implementation), The meeting reports are used for monitoring and informing decision making. Meetings take place in Rabat. Field visits to Marrakech to provide support to the Project Management Unit (PMU) Mission reports are produced |  | UNDAF Outcome 3:Vulnerability and inequality, including those of gender, are reduced through support for policies, strategies and programs of economic and social development. Outcome 4 : Institutional partners and civil society appropriate principles of gender responsive democratic governance and implement them for an integrated, equitable and sustainable human development. |  |  | MRF 1.1.1 Outcome 3 / Output 3.1: Decision-makers have access to nationally-generated knowledge and statistics on VAW at local level (city of Marrakech) Output 3.2 : Prevent violence against women and girls and expand access to victim/survivor services |  |  | Morocco | MCO Maghreb |  | Y with UNICEF/UN Women/UN-Habitat | Municipality of Marrakech , The Prefecture of Marrakech , Regional directorates of the National Safety , Ministry of Housing, Ministry of Education, Ministry of Health, Ministry of Justice, Ministry of youth and sports, Ministry of social development, the National Offce of Statistics (HCP) and CSOs. UNWomen | Monthly Twice a year Every two months 3 missions carried out in 2012 1 field visit in 2013 the others tbd | 220 000 USD (UNICEF’s Funds) | ongoing |  |  |
| Technical committee Meetings reports are produced Project “Support for gender-responsive integration of climate change adaptation in local planning in Morocco” |  | UNDAF Outcome 3 & 5 SP Outcome 2.1 |  |  | Output 2.1.1 |  |  | MCO Maghreb | Morocco |  | UNWomen, Department of Local Municipalities (Ministry of Interior), Ministry of Environment, UNDP, and the Swiss Cooperation DDC | UNWomen, Department of Local Municipalities (Ministry of Interior), Ministry of Environment, UNDP, and the Swiss Cooperation DDC | Mars 2013 June 2013 | NA | Ongoing |  |  |
| Technical committee Meetings reports are produced Project “Support for gender-responsive integration of climate change adaptation in local planning in Morocco” |  | UNDAF Outcome 3 & 5 SP Outcome 2.1 |  |  | Output 2.1.1 |  |  | MCO Maghreb | Morocco |  | UNWomen, Department of Local Municipalities (Ministry of Interior), Ministry of Environment, UNDP, and the Swiss Cooperation DDC | UNWomen, Department of Local Municipalities (Ministry of Interior), Ministry of Environment, UNDP, and the Swiss Cooperation DDC | May 2013 December 2013 | NA | ongoing |  |  |
| Field visits mission reports are produced Project “Support for gender-responsive integration of climate change adaptation in local planning in Morocco” |  | UNDAF Outcome 3 & 5 SP Outcome 2.1 |  |  | Output 2.1.1 |  |  | MCO Maghreb | Morocco |  |  | Ministry of Interior And the Swiss Cooperation DDC | 1 field visit held other dates tbd | 1000 $ | Ongoing |  |  |
| Steering committee of the joint programme “Support the monitoring & reporting of MDGs in Morocco” Meeting reports will be produced in addition to the annual review report |  | UNDAF Outcome 4 SP Outcome 2.1 |  |  | Output2.1.1 |  |  | MCO Maghreb | Morocco |  | Higher Commissariat of Planning (HCP) UNWomen, UNDP, UNFPA, UNICEF, OMSQ, CEA, | Higher Commissariat of Planning (HCP) Ministry of Foreign Affairs , local municipalities, UNWomen, UNDP, UNFPA, UNICEF, OMSQ, CEA, media, universities | 2 meetings January and December |  | Ongoing |  |  |
| Technical committee of the joint programme “Support the monitoring &reporting of MDGs in Morocco” Meeting reports are produced |  | UNDAF Outcome 4 SP Outcome 2.1 |  |  | Output2.1.1 |  |  | MCO Maghreb | Morocco |  | Higher Commissariat of Planning (HCP) UNWomen, UNDP, UNFPA, UNICEF, OMSQ, CEA, | Higher Commissariat of Planning (HCP) UNWomen, UNDP, UNFPA, UNICEF, OMSQ, CEA, | Quarterly April, August, November | NA | Ongoing |  |  |
| Steering committee of the joint programme “Support to the National Observatory of Human Development” |  | UNDAF Outcome 4 SP Outcome 2.1 |  |  | Output2.1.1 |  |  | MCO Maghreb | Morocco |  | National Observatory of Human Development, UNWomen, UNDP, UNFPA, UNICEF | National Observatory of Human Development, Ministry of Foreign Affairs, local municipalities, UNWomen, UNDP, UNFPA, UNICEF | 2 meetings January, December | NA | Ongoing |  |  |
| Technical committee of the joint programme “Support to the National Observatory of Human Development” |  | UNDAF Outcome 4 SP Outcome 2.1 |  |  | Output2.1.1 |  |  | MCO Maghreb | Morocco |  | National Observatory of Human Development, UNWomen, UNDP, UNFPA, UNICEF | National Observatory of Human Development, , UNWomen, UNDP, UNFPA, UNICEF | quarterly January, May, July, October | NA | Ongoing |  | The meeting programmed for March was held on May |
| Steering committee of the programme monitoring of the democratic transition in Tunisia |  | SP Outcome 1 |  |  | Output 1.2 |  |  | MCO Maghreb | Tunisia |  | UNWomen EU and NGOs(Voix de femmes,Tamss,UFIM,Amal | UNWomen EU and NGOs, Voix de femmes,Tamss,UFIM,Amal | tbd | tbd | ongoing |  |  |
| 2a) EVALUATIONS managed by the Country/ Sub-regional/ Regional Office e.g. outcome, thematic, programme evaluations etc. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| EVAW Thematic Evaluation: MCO Maghreb contribution to EVAW | N | UNDAF outcome 3 SP Outcome 3.1 |  |  | Outputs 3.1.1, 3.1.2, 3.1.3, 3.1.4 |  | MCO- Maghreb |  | MCO- Maghreb | N |  | Machinery of Women in Morocco, Algeria and Tunisia Ministry of Justice and Freedoms Morocco High Commission of Planning Morocco National Council of Human Rights– Morocco Ministry of Health Morocco NGOsAlgeria: AVIFE, SMILE, Femmes En Communication, CIDDEF, SOS Femmes en Détresse NGOs Morocco : ADFM, AMVEF, Ytto, IPDF, AMDF, Spring time of Dignity NGOs Tunisia:CREDIF, ATFD, AFTURD, CAWTAR, AMAL, BEITY Morocco UN country gender group | June 2013 | 25000 US$ | ongoing |  |  |
| Final Evaluation of the project "Support the implementation of the family code by the facilitation of women's access to justice services” - Gender and Democratic Governance - (75424) | Y | UNDAF Outcome 4 |  |  | Outcome 3 / Output 3.2 : Prevent violence against women and girls and expand access to victim/survivor services |  | Morocco |  | MCO - Maghreb | N |  | Ministry of Justice and Freedoms Ministry of Solidarity Woman, Family and Social Development | September -November 2013 | US$ 20,000 Will be covered by Programme Global GDG/NY non core funds the amount allocated depends on the available funds. It was decided to use a national expertise | Will start on September-October 2013 |  | This evaluation was programmed on September-November 2012 in the previous the MER Plan. It is rescheduled since the programme has been extended |
| 2b) Other EVALUATIONS in which Country/ Sub-regional/ Regional Office is involved but NOT managing, e.g. evaluations managed by HQ Evaluation Office, Trust Fund on VAW, UNDEF, donors etc. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Final evaluation of the UN Trust Fund on VAW projet Defense of the rights of single mothers and of girls exploited in domestic work | Y | UNDAF outcome 3 vulnerability and inequality, in particular those related to gender are reduced by supporting policies / strategies and programs of economic and social development |  |  | Output 3.3.2 |  | Morocco |  | Morocco |  | N | INSAF (NGO) | June 2013 | USD 17700 | Ongoing |  | This evaluation is managed by the NGO with technical support of UNWomen |
| Corporate EVAW Thematic Evaluation – Morocco Case study |  |  |  |  |  |  | HQ |  | HQ |  |  |  |  |  |  |  |  |
| 3) RESEARCH Activities undertaken by the Country/ Sub-regional/ Regional Office with regard to the monitoring and evaluation needs of the Annual Work Plans |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Gaps between the new Constitution and existing laws Project: Women Election Watch |  | UNDAF outcome 4 Institutional partners and civil society appropriate principles of gender responsive democratic governance and implement them for an integrated, equitable and sustainable human developmt SP: Outcome 1 |  |  | Output 1.2 Gender equality advocates and their organizations have strengthened capacities to effectively influence local governments and service delivery organizations to promote gender equality. |  | Morocco |  | NASRO |  |  | NGO ADFM |  | 12000 US$ | ongoing |  |  |
| Study on the monitoring of law on APALD Project: Women Election Watch |  | UNDAF outcome 4 Institutional partners and civil society appropriate principles of gender responsive democratic governance and implement them for an integrated, equitable and sustainable human development SP: Outcome 1 |  |  | Output 1.2 Gender equality advocates and their organizations have strengthened capacities to effectively influence local governments and service delivery organizations to promote gender equality. |  | Morocco |  | MCO Maghreb |  |  | NGO ADFM |  | 11000 US$ | Completed |  |  |
| Reform of Justice and gender equality Project: Women Election Watch |  | UNDAF outcome 4 Institutional partners and civil society appropriate principles of gender responsive democratic governance and implement them for an integrated, equitable and sustainable human development SP: Outcome 1 |  |  | Output 1.2 Gender equality advocates and their organizations have strengthened capacities to effectively influence local governments and service delivery organizations to promote gender equality. |  | Morocco |  | MCO Maghreb |  |  | NGO ADFM | July 2013 | 6500 US$ | ongoing |  |  |
| 4 studies on gender and local governance: 1)Women’s perception of local governance– Municipality of SidiBernoussi; 2) Integrating prevention and response to gender based violence in the Advanced Regionalization; 3) Elaborating gender-sensitive follow-up/evaluation tools of local policies for CSOs; 4) development of mechanisms of gender-sensitive social accountability Project: Women Election Watch |  | UNDAF outcome 4 Institutional partners and civil society appropriate principles of gender responsive democratic governance and implement them for an integrated, equitable and sustainable human development SP: Outcome 1 |  |  | Output 1.2 Gender equality advocates and their organizations have strengthened capacities to effectively influence local governments and service delivery organizations to promote gender equality. |  | Morocco |  | NASRO |  | Y | NGO AMVEF |  | 35200 US$ | Studies 1 & 4 completed Studies 2& 3: ongoing |  |  |
| Study on the improvement of knowledge of social protection systems according to gender | Y | UNDAF Outcome 3 & 4 UNWomen SP Outcome 5 |  |  | Output 5.1.1 |  | MCO Maghreb |  | Morocco |  |  | Ministry of Employment and Professional Training | December 2012 - July 2013 | 40351 USD | ongoing |  |  |
| Analytical study on the representation of women at the governance bodies within large public and private companies | Y | UNDAF Outcome 3 & 4 UNWomen SP Outcome 5 |  |  | Output 5.1.1 |  | MCO Maghreb |  | Morocco |  |  | Ministry of General Affairs & Governance | 09/2012 - 04/2013 | 45 038 USD | Completed |  |  |
| Study on national laws harmonization with CEDAW dispositions | Y | UNDAF Outcome 3 & 4 UNWomen SP Outcome 5 |  |  | Output 5.1.1 |  | MCO Maghreb |  | Morocco |  |  | Interminesteral Delegation of Human Rights | Tdb | 15029 USD | Ongoing |  |  |
| Analytical study on" Protection of the rights of women through the Moroccan Law"-"From Independence to 2013" Project: Support the implementation of the family code by the facilitation of women's access to justice services” - Gender and Democratic Governance - |  | UNDAF Outcome 4 |  |  | Outcome 3 / Output 3.2 : Prevent violence against women and girls and expand access to victim/survivor services |  | MCO - Maghreb |  | Morocco |  |  | Ministry of Justice | N | 14 000 USD | Ongoing |  |  |
| Study on access of women and men to inheritance CME 95 |  | Outcome 2 |  |  | Output 2.1 |  | MCO Maghreb |  | Tunisia |  |  | CME95/UNWomen | October 2012/December2013) | 18900 USD | ongoing |  |  |

# Annex 2: Evaluation Justification Matrix

| List of selected evaluation | Criteria used for the selection | Potential evaluability | Intended use of evaluation findings |
| --- | --- | --- | --- |
| Final Evaluation of the “MultiSectoralProgramme for the Fight Against Gender Based Violence Through the Empowerment of Women and Girls in Morocco | Mandatory evaluation | All the conditions to conduct the evaluation are met | -Evaluate the contribution of the programme to meet the results development especially the MDGs; -Identify the best practices and lessons learned that may be used in other development programmes at the national level, and duplication at the international level; -Identify difficulties and problems to avoid in conducting joint programmes in the future |
| Final Evaluation of the project “Cultural Heritage and Creative Industries as Vehicles for Development in Morocco | Mandatory evaluation | All conditions to conduct the evaluation are met | Evaluate the contribution of the programme to meet the development results mainly the MDGs -Identify the best practices and lessons learned that may allow to duplicate the programme -Identify difficulties and problems to avoid in conducting joint programmes |
| Final Evaluation of the project "Support the implementation of the family code by the facilitation of women's access to justice services” - Gender and Democratic Governance - | - Required by the donor - Relevant because of the size and the strategic aspect of the programme in terms of the application of family code | All conditions are here to conduct the evaluation | The evaluation will include a reflection on the programme, the best practices, weaknesses and recommendations. This will permit to identify new opportunities, especially in the framework of the country programme to reform the Justice |