UN WOMEN NEPAL COUNTRY OFFICE (NCO)

MONITORING, EVALUATION AND RESEARCH PLAN [MERP] 2019

Monitoring Plan

| SN Impact/Outcome | Activity | Responsible staff member | Partners and stakeholders | Planned Dates [Month and year of start and end] | Budget |  | Reference – DR/OEE |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Source | Amount in USD |  |
| MONITORING |  |  |  |  |  |  |  |
| 2019 |  |  |  |  |  |  |  |
| DR 1 (Governance) – Monitoring visits to partners based on risk analysis | NPL_D_1.1.2.1 Governance Project Document | Jr. International Consultant | TBC | Quarterly | TBM Finland Core | TBC | Output 1.1.2 |
|  | NPL_D_1.1.3.1 Truth Telling | Peace & Security Specialist | Equal Access |  | Core |  |  |
|  | NPL_D_1.1.2.3 Support NWC to develop monitoring report on the implementation of CEDAW Concluding Observation | A2J Officer | National Women Commission (NWC) |  | Core |  |  |
|  | NPL_D_1.1.2.3 Support the NDC in collaboration with Dalit's women's group to monitor the situation of Dalit women's rights | A2J Officer | National Dalit Commission (NDC) |  | TBM Finland |  |  |
|  | NPL_D_1.1.2.2 Assess to Justice: Support capacity strengthening government officials in the justice sector (A2J Commission and Provincial/district Courts) with NJA on substantive equality, gender-sensitive judicial procedures to implement and monitor the new GESI Strategy | A2J Officer | National Judicial Academy (NJA) |  | TBM Finland |  |  |
|  | NPL_D_1.1.2.3 Promote Right to Information (RTI) with National Information Commission (NIC), civil society and sub-national governments | National UN Volunteer | National Information Commission (NIC) |  | TBM Finland |  |  |
|  | NPL_D_1.1.3.3 Women's Access to Justice | A2J Officer | Civil Society (TBC) |  | A2J AP non-core |  |  |
|  | NPL_D_1.1.1.1 and NPL_D_1.1.2.1Disaster Risk Reduction (DRR) in 3 districts Gender Responsive DRR | Peace & Security Specialist | Women Forum for Disaster Management Group |  | TBM IOM |  |  |
| DR 1 (Gender Statistics) – Monitoring visits to partners based on risk analysis | NPL_D_1.2.1.11, NPL_D_1.2.1.12, and NPL_D_1.2.1. 13: Support the assessment of the extent the Nepal SDGs Framework for Tracking Progress (2018) integrates gender-related indicators at federal, provincial and local level NPL_D_1.2.1.19: Support CBS, MoWCSC, and the NPC in revising and adopting a minimum set of gender indicators | Gender Statistics Programme Officer | TBC |  | Bill and Melinda Gates Foundation | Staff time |  |
| DR 2 - Monitoring visits to partners/service providers based on risk analysis | NPL_D_2.1.3.1 * Aasaman Nepal (service provider) - Field visits to monitor the implementation NPL_D_2.1.3.1 * Manakamana Training and Skill Development Institute - Field visits to monitor the implementation | Technical Education and Vocational Training (TVET) Officer Technical Education and Vocational Training (TVET) Officer | UNESCO, UNFPA UNESCO, UNFPA | February and July 2019 January, June and November 2019 | UNESCO UNESCO | 1,000 1,500 | DR2 DR2 |
| NPL_O_3.1 | Support the development of a monitoring report on the progress of SDG-5 indicators [2019] | UN Women Coordination Focal Point | UN GTG | Q-3 | IB | 1,800 | OEE |

Research Plan

| Activity | Partners and stakeholders | Planned Dates [Month and year of start and end] | Budget |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount in USD |
| RESEARCH |  |  |  |  |
| 2019 |  |  |  |  |
| NPL_D_1.2.1.11: Support the assessment of the extent the Nepal SDGs Framework for Tracking Progress (2018) integrates gender-related indicators to identify ‘missing’ indicators or indicators that need to be revised; construct a comprehensive mapping of the data sources (official and alternative ) that provide/have the potential to provide data; prepare metadata for each of the gender-related indicators identified; and prepare an action plan for addressing the gaps | CBS | 2019 [Q1-Q3] | Bill and Melinda Gates Foundation | 10,500 |
| NPL_D_1.2.1.12: Support the provincial level assessment of readiness for reporting in two provinces by identifying provincial institutions, structures and mechanisms for SDG monitoring and reporting including gender statistics. Support the identification of provincial role and assessment of provincial capacity to produce data for the national Nepal SDGs Framework for Tracking Progress (2018), particularly gender-related indicators. Identify ‘missing’ indicators or indicators that need to be revised to be relevant in the provincial context; construct a comprehensive mapping of the provincial data sources that provide/have the potential to provide data; and prepare an action plan for addressing the gaps in indicators, mechanisms and capacities. | CBS | 2019 [Q1-Q3] | Bill and Melinda Gates Foundation | 25,000 |
| NPL_D_1.2.1.13: Support the assessment of local government roles and capacities for monitoring and reporting on SDGs through the exploration of the potential production and use of data by local governments for monitoring and reporting on gender indicators within the national SDG Framework, in collaboration with NPC, CBS, provincial bodies and local governments. Support the assessment of gender-related indicators which are most relevant to local governments and any revisions to optimize relevance in the local context; map data sources that provide/have the potential to provide data; and prepare an action plan for addressing the gaps in structures, mechanisms and capacities. | CBS | 2019 [Q1-Q3] | Bill and Melinda Gates Foundation | 25,000 |
| NPL_D_1.4.1.7 Support the development of a National Gender Profile and other gender statistics report using the SDGs at the national and subnational levels/Progress of Women in Nepal | TBD | 2019 [Q2-Q3] | Non-Core Available (MEWGC) | 20,000 |
| NPL_D_1.3.1.18 Support data collection on and production of time-use related SDG indicators from time-use survey, including disaggregation at provincial and local levels, where possible (related to outputs 1.2.1 and 1.2.3) | CBS | 2019 | Non-Core Available (MEWGC) | 200,000 |
| NPL_D_1.1.1.1 Annual sectoral GRB analysis conducted in close collaboration Ministry of Finance (MoF) in 2019 | MOF | 2019 [Q3-Q4] | In-house (time) | N/A |
| Long-term comprehensive research (quantitative and qualitative methods) on the experience of elected women representatives (including focus on changes in their lives, and violence against women in politics) | Research agency | 2019 [Q2] - 2022 | Core | 30,000 (for 2019) |
| NPL_D_2.1.2.1 Perception study for WEE programming to explore social norms and practices pertaining to women’s economic and social empowerment in order to inform NCO’s future programmes. It will also set the baseline to assess the impact and contribution of NCO’s ongoing women’s economic empowerment (WEE) programmes on positive changes in social norms and practices in seven UN Women programme districts. | Research agency | Q4 2018 – Q2 2019 | AWEE | 36,000 |
| NPL_O_3.1.3 Another WEE research to answer key research questions such as “What are the social norms and structural barriers that block women’s entry into the formal economy, and how can UN Women support social transformation to remove these barriers, tapping into economic opportunities in the existing labour market?”, | Research agency | Q4 2018 – Q2 2019 | Core | 30,000 |

Evaluation Plan

| Evaluation name | Mandatory? [Y/N] | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ MCO/ RO AWP Output | Office in charge | Region/ country | Joint activity [Y/ N, indicate partners] | Key Stakeholders | Planned Dates [start-end] | Budget [USD] / Sources of Funding | Status [pending/ initiated/ ongoing/ completed] | Remarks | Reference – DRF/OEEF-2018 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |  |
| 2019 |  |  |  |  |  |  |  |  |  |  |  |  |
| Undertake Stage-1 of “Developmental Evaluation” as per the SN Evaluability Assessment with technical support from RO and HQ | N | SN | OEE NPL_O_3.1.5 | NCO | Nepal | N | UN Women RO and NCO | Q3 2019 | 15,000 |  |  | OEE 3 |
| Undertake thematic evaluation of Women’s Economic Empowerment (AWEE) programme | Y | UNDAF 1/Global SP Outcome 3 | NPL_D_2.1.2.1 | NCO | Nepal | N | Government of Finland and Zonta International | Q4 2018 – Q2 2019 | 90,000 |  |  | DR 2.1 |
| Undertake final evaluation of Joint Programme on Rural Economic Empowerment programme (RWEE) | Y | UNDAF 1/Global SP Outcome 3 | NPL_D_2.1.2.1 | NCO | Nepal | Y | FAO, IFAD and WFP, | Q3 2019 | 49,000 |  |  | DR 2.1 |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |  |
| 2019 |  |  |  |  |  |  |  |  |  |  |  |  |

The POM indicates the risk that cash transferred to a partner may not be used as intended or reported in accordance with agreements/ approved work plans and that the level of this risk may differ from institution to institution.  To mitigate this risk, close monitoring of programme implementation including cash advances to responsible parties are required to ensure that the advanced funds are being used for purposes (results) for which these are granted.  Such monitoring activities include; (a) on-site reviews of the implementing partner‘s programme (results, progress on indicators, bottlenecks), financial and administrative records and assets management  (b) periodic review meeting. The risk includes contextual, institutional and programmatic risks.

The merger of the proposed two AWEE and FWW evaluations to a thematic evaluation will be finalized post consultation with respective donors.