MONITORING, EVALUATION AND RESEARCH PLAN 2017

Jordan Country Office

| IMPACT / Outcome | Activity | Responsible Staff Member | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Source | Amount |
| MONITORING |  |  |  |  |  |  |
| Impact 2 / Outcome 2.1 | Ongoing monitoring (Field visits) of the “Promoting rural women’s food security in Jordan “project. | Radwa Nour | FAO | Ongoing April 2016-March 2017 (PMF - field visits, etc.) | Non-core | 200$ |
| Impact 3 / Outcome 3.1 Impact 4 /Outcome 4.1 | Ongoing monitoring (Field visits) of “Women’s Leadership, Empowerment, Access and Protection (LEAP) in Crisis Response – Iraq and Jordan” project | Radwa Nour Laila Hatahet | JWU | Ongoing April 2016-March 2017 | Non-core | 1000$ |
| Impact 4 /Outcome 4.2 | Ongoing monitoring (Field visits) of “Women, Peace and Security in the Arab States” project | Laila Hatahet | JNCW | Ongoing January2016 - 2015-December 2018 | Non-core | 500$ |
| Impact 2 / Outcome 2.1 Impact 4 /Outcome 4.1 | Monitoring (Field visits) of the “Supporting Women in Host Communities and in Jordan’s Refugee Camps through Prevention and Response to Gender-based Violence and Promotion of Self-reliance and Social Cohesion “project | Radwa Nour | MOSD, JNCW,WFP,JEFE | January – December 2017 | Non-core | TBD |
| Impact 3 / Outcome 3.1 | Ongoing monitoring (Field visits) of the “Raising Awareness of VAWG among Societal Actors in Jordan” project | Laila Hatahet | ARDD-Legal Aid | Ongoing January 2016 – January 2018 | Non-core | 100$ |
| Impact 3 / Outcome 3.1 | HP - Monitoring(Field visits) of the “Hemayati-Promoting Women and Girls’ Health and Well-being” | Laila Hatahet | JWU | January – December 2017 | Non-core | 1,000$ |
| Impact 4 /Outcome 4.2 | Ongoing monitoring (Field visits) WPS in Jordan: A NAP on 1325 and capacity building of Security actors on SGBV (Jordan) UNICEF/ UN Women | Radwa Nour | JNCW |  | Non-core | 500$ |
| - | Formulation of SN 2018-2021 | Ziad Sheikh | Government, Civil society | March – June 2017 | Core | $5,000 |
| RESEARCH |  |  |  |  |  |  |
| Produce advocacy oriented research on the effects of climate change in Jordan, in particular the gendered impact of climate change. |  |  | FAO | January – February 2017 | Non-Core | $30,000 |
| Situational analysis to inform the strategic note development and provide an assessment of the missing data gaps on gender equality and women's empowerment |  |  |  | January 2017 | Core | $30,000 |

Evaluation Plan 2017

| Evaluation name | Manda-tory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome |  |  | Country/ MCO/ RO AWP Output |  | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding |  | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Supporting women in host communities and in Jordan’s Refugee Camps through prevention and response to gender based violence and promotion of Self-Reliance and Social Cohesion (Eid-bi-Eid) | Y | UNAF Outcome 3.2 SN 2014-2017 outcomes 1.1. and 1.2 |  |  | Jordan UN Women SN Outcome 4 / outputs 4.1.1, 4.1.2, 4.3.1 Responds to Jordan’s National Resilience Plan (NRP) 2014-2016 |  | Jordan CO | Arab States/ Jordan | N | JEFE, AFDP, MoSD | August – December 2017 | 20,000 (Non-core TBM. Donor: Finland and Italy) |  | Pending (Postponed from 2016 due to project extension) | Responsible person: Isabella Vettolani |
| Promoting rural women’s food security in Jordan | Y | UNAF Outcome 2 SN 2014-2017 outcome 2.1 |  |  | Jordan UN Women SN Outcome 2.1 Output 2.1.1 |  | Jordan CO | Arab States/ Jordan | N |  | January - April 2017 | 20,916 (Non-core available. Donor: Japan) |  | Pending | Responsible person: Bothaina Qamar |
| Evaluation of Women’s Political Participation & Leadership Component | Y | UNDAF Outcome 1.1 SN 2014-2017 outcomes 1.1. and 1.2 |  |  | Jordan UN women SN outcome 1/outputs 1.1, 1.2 |  | Jordan CO | Arab States/ Jordan | N | MOPIC Parliament, JNCW, Ministry of Political Development | September – November 2017 |  |  | Canceled | LPP programme yet to be developed. Thematic evaluation is to be undertaken when the programme is developed. |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Empowering rural women in Mafraq Governorate through the Management and preservation of the Umm el Jimal’s archaeological site As income-generating activities in Jordan | Y |  | UNDAF, 2013-2017 Outcome 2 | Jordan UN women SN outcome 2.1 |  | Jordan CO |  | Arab States/ Jordan | Y (Managed by UNESCO) |  | September - October 2017 | 0 | pending |  | Responsible person: Marta Garbarino |
| Women’s Leadership, Empowerment, Access & Protection in Crisis Response (LEAP) – Iraq and Jordan | Y |  | UNAF Outcome 6 SN 2014-2017 outcome 4.1 | Jordan UN Women SN Outcome 4.1 |  | Jordan CO |  | Arab States/ Jordan | N | JWU | March – May 2017 | 20,000 (Non-core available. Donor: Japan) | pending |  | Responsible person: Laila Hatahet |