NEPAL NCO

MONITORING, EVALUATION AND RESEARCH PLAN (MERP) 2017

Monitoring 2017

| SN Impact/Outcome | Activity | Responsible staff member | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  | Reference – DRF/OEEF-2017 |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Source | Amount in USD |  |
| MONITORING |  |  |  |  |  |  |  |
| Quarterly monitoring of activities including of UNTF EVAW grantees | Update RMS on quarterly basis | Focal point per output in RMS in close collaboration with the M&E Officer | Internal staff | Q1, Q2, Q3 and Q4 | N/A | N/A | OEEF 2.1a |
| Continue the Mid Term Review of the project on Advancing Women’s Economic Empowerment – Ensuring Nepal’s Sustainable and Equitable Development 2015 – 2017 | Contract agency to carry out review, conduct a desk review, field visits and workshops with relevant stakeholders | M&E Officer, WEE Unit Head | Key government counterparts (Ministry of Women, Children and Social Welfare, Ministry of Labour and Employment, national Planning Commission), Embassy of Finland, responsible partners, networks of excluded women | Q1 | Non-Core – Government of (Finland) | Budgeted in 2016 | DRF 2 |
| Monitoring visits to three UNTF on EVAW grantees | Conduct field visits | EVAW Programme Officer | Restless Development, Story Kitchen and Skillshare | Q1, Q3 | EXB from (UNTF on EVAW) | 1000 | OEEF 2.1b |

Research Plan 2017

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount in USD |
| RESEARCH |  |  |  |  |
| Carry out research and consolidate existing knowledge and available data on women's economic empowerment in collaboration with National Planning Commission (NPC), Ministry of Women, Children and Social Welfare (MoWCSW), Central Bureau of Statistics (CBS) and Working Group of Economists (AWEE) - Rural women’s paid and unpaid contribution to food and nutrition security - Causes of rural women’s migration to foreign employment and ways to their reintegration into Nepalese labour market (continued from 2016) | Institutional contract | Q1- Q3 | Non-Core Finland | 90,000 |
| Desk reviews on three major areas: - Gender-biased statutory and customary land tenure frameworks, laws and policies - Women’s access to productive, time-saving and climate-resilient assets, tools and technologies - Gender responsive agriculture related subsidies. The desk review reports (knowledge products) will be disseminated with the Government, Development Partners and Civil Society Organizations (CSOs) and through the NCO website |  | Q1- Q3 | Non-Core TBM MPTF | 15,000 |
| Conduct a mapping exercise to analyse the risk factors for unsafe migration, trafficking and violence against women and prevailing structural discrimination in the selected districts, and prepare a mapping report (joint programme with International Organization for Migration (IOM) | TBD | Q1-Q2 | Non-Core Zonta | 25,000 |
| Impact assessment of tax rebate policies | Internal resources/SSA | Q1, Q3 | Non-Core Finland |  |
| Carry out a desk review on gender responsive reconstruction initiatives | Internal resources/SSA | Q1,Q3 | Non-Core Non-Core TBM | 26,000 |
| End-line Survey of the project on Advancing Women’s Economic Empowerment – Ensuring Nepal’s Sustainable and Equitable Development 2015 – 2017 | TBD | Q1, Q4 | Non-Core Finland | 50,000 |
| Carry out women’s safety audits (WSA) in three to five select municipalities/districts in collaboration with women's groups and UN Habitat to guide planning, design and reconstruction efforts | TBD | Q1, Q2, Q3 and Q4 | Non-Core TBM | 50,000 |
| Conduct an annual staff survey to assess satisfaction with NCO leadership and direction | Internal | Q1, Q2 | Core | 2,000 |

Evaluation Plan 2017

| Evaluation name | Mandatory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ MCO/ RO AWP Output | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks | Ref – DRF/OEEF-2017 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |  |
| Meta evaluation of the NCOs WPS evaluations | N | UN Women SP Goal 4 | OEEF2.3 | NCO | Nepal Country Office | N | Ministry of Peace and Reconstruction, Ministry of Women, Children and Social Welfare, Department of Women and Children | Q2 2017 | 6,000, (Non-core funds - AWEE) | To be initiated |  |  |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |  |