MONITORING, EVALUATION AND RESEARCH PLAN 2023-2026 ECUADOR CO

- Monitoring and Research Plan 2023-2026

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) |  |  | Budget |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Source | Amount |
| MONITORING |  |  |  |  |  |  |
| Quarterly review of projects: project processes and advance; technical assistance process; consultant advance. | IOM UNDP UNODC Ministry of Production Ministry of labour Municipality of Quito Human Rights Secretariat National Gender Equality Council National Electoral Council Civil society organizations (organizations will be defined in competitive processes) | March 2023, 2024, 2025, 2026 June 2023, 2024, 2025, 2026 September 2023, 2024, 2025, 2026 November 2023, 2024, 2025, 2026 |  | Core Non-Core US Department PRM MPTF Migration Peace building fund |  | Included in staff duties |
| Field visits and interviews, monitoring mission | TBD |  |  |  |  |  |
| UNW Quarterly AWP monitoring | CO staff | April 2023, 2024, 2025, 2026 July 2023, 2024, 2025, 2026 October 2023, 2024, 2025, 2026 January 2023, 2024, 2025, 2026 |  | Core |  | Included in staff duties |
| UNW Annual Reporting | CO staff | January 2024, 2025, 2026, 2027 |  | Core |  | Included in staff duties |
| Narrative and interim donor reporting | CO staff | Depending on agreement |  | Core |  | Included in staff duties |
| RESEARCH |  |  |  |  |  |  |
| Guidelines for the inclusion of GBV prevention in public spaces with Human Mobility approach. | GTRM | March 2023 |  | Non Core US Department PRM |  | 47,987 |
| Systematization Caminando Project |  | March 2023 | Non Core US Department PRM |  |  | 20,000 |
| Labor market study to identify normative, policy and economic gaps that hinder the process of socioeconomic integration for people in human mobility and identify local needs for new businesses opportunities, and available job positions with an emphasis on existing gender gaps and double discrimination factors confronted by women in human mobility and structural barriers | IOM UNDP | August 2023 | Non Core MPTF Migration |  |  | 25,000 |
| El impacto del crimen organizado en mujeres, niñas y adolescentes | UN WOMEN | March 2025 | Non Core PBF |  |  | 10.000 |

- Evaluation Plan 2023-2026

| Evaluation name | Mandatory? (Y/N) | UNSDCF Outcome/ UN Women SP Outcome and relevant SDGs | SN Output/Relevant flagship program | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Mandatory: Strategic Note Evaluation | Y | PRIORIDAD ESTRATÉGICA 3 y 4 | All | Ecuador CO IES | Ecuador - LAC | No | January - August 2026 Start TOR in Q4-2025 | 38,000 core | Pending |  |  |
| Evaluation of: Spotlight Initiative Ecuador 2.0 FIEDS Acción y conciencia: Por la erradicación de la violencia contra las mujeres | Y | PRIORIDAD ESTRATÉGICA 4 PRODUCTO 4.1 Y PRODUCTO 4.6 | DR. 2.3 | Ecuador CO | Ecuador - LAC | Y UNDP UNFPA | March 2026 | 10,000 Non-core 750.000 (2% 15.000) | Pending |  |
| Evaluation of PRM project: Promoting Gender equality and empowerment for women in situations of displacement and refuge | Y | DR. 3.1 | DR. 3.1 | Ecuador CO | LAC | No | October 2023 – February 2024 | 38,000 Non-core | Finalized |  |
| Evaluation of the Armed Forces Gender Policy | N | DR 3.5 | DR 2.3 | Ecuador CO | LAC | Yes National Council For Gender Equality Ministry of Defense | Oct 2023 – February 2024 | 25.000 | Finalized |  |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |
| Joint Programme Evaluation. Capacidades para la paz, la seguridad y la reducción de las violencias en Ecuador. | Y | PRIORIDAD ESTRATÉGICA 4 | DR. 2.1 y DR 2.4 | Ecuador CO | LAC | Yes UNDP UNODC | April 2025- June 2025 February 2025 | 89.966,86 3% (2.998.895.40) | Pending | Leading agency managing budget UNDP |  |
| Joint Programme Evaluation. Enchanced socio-economic integration of migrants and host community members (with an emphasis on women and youth) focused on enterpreneurship opportunitie. | Y | DR. 2.1 | DR. 2.1 | Ecuador CO | LAC | Yes ILO UNDP | October 2023- February 2024 | 25.457.80 3% (1.500.000 USD) | Finalized | Leading agency managing budget IOM |
| Evaluation of the Spotlight Initiative | N | Outcome 2 / UN Women SP Impact area 3 SN OUTPUT 3 |  | Spotlight Secretariat | LAC | Yes | March to June 2023 | 54,000 Non-core | Finalized |  |
| UNSDCF evaluation | N | ALL |  | RCO | LAC |  | March 2026 | 10,000 | Not Started |  |

Please fill out a separate row for each evaluation.

UN Sustainable Development Cooperation Framework (UNSDCF), formerly known as UNDAF.

Outcomes contributing to the SDGs as per the Strategic Plan