MONITORING, EVALUATION AND RESEARCH PLAN 2020

GUATEMALA CO

- Monitoring and Research Plan 2020

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount |
| MONITORING |  |  |  |  |
| Monitoring gender mainstreaming in UN planning frameworks: Common Country Assessment; Common Chapter of Strategic Plan; UNDAF/UNSDCF and wide accountability (UNCT-SWAP Gender Scorecard; Gender Marker System). | UN System Coordination | 1/2020 - 12/2020 | Core | $35,634 |
| Technical assistance and reviews on gender mainstreaming for joint programmes and UN agencies' strategic plans. | UN System Coordination | 1/2020 - 12/2020 | N.A. | N.A. |
| Submission of corporate quarterly and annual progress reports, annual report for donors and partners, and strategic planning exercises following an RBM approach. | UN Women Staff, Donors and AFPs | 1/2020 - 12/2020 | N.A. | N.A. |
| Strategic Note Planning | Analysis, workshops, interviews with participation of UN Women Staff, UN/AFP, women organizations and governmental institutions and other civil society orgs partners | 1/2020 - 6/2020 | Core | $15,000 |
| Baseline of Sepur Zarco case: Reparation Centers Index | Civil society key actors | 1/2020 - 3/2020 | Non-Core United Nation Pacebulding | $10,000 |
| Spotlight baseline review | Spotlight partners and other institutions and civil society key actors. | 1/2020 - 9/2020 | Non-Core MPTF - Spotlight | $30,000 |
| RESEARCH |  |  |  |  |
| Design of the national survey on violence against women, girls, and adolescent girls. (Specialized survey on violence against women and girls which measures the prevalence of the problem, based on international standards, and generated specialized studies that provide information for decision making.) | UN System, Civil society orgs, governmental and private sector key actors. | 3/2020 - 8/2020 | Non-Core MPTF - Spotlight | $98,700 |
| Systematization of the process of strengthening the participation of women and raising awareness of development councils to promote gender equality. | UN System, Civil society orgs, governmental and private sector key actors. | 2/2020 - 6/2020 | Non Core - TBM Joint programme REEW | $12,250 |
| Study on sexual harassment in private Universities | Civil society orgs, governmental and private sector key actors. | 1/2020 – 12/2020 | Core | $5,000 |
| American University - Documenting Good Practice on Accountability for Conflict-Related Sexual Violence in Guatemala | Civil society orgs, governmental and private sector key actors. | 1/2020 – 3/2020 | Non-Core United Nation Pacebulding | $10,000 |
| Development of knowledge products on governance gender sensitive on the frame of SDGS (Gender Profile (ASIES) and Progress in Guatemala (ASIES)) | UN System, Civil society orgs, governmental and private sector key actors. | 2/2020 - 11/2020 | Core | $10,000 |

- Evaluation Plan 2020

| Evaluation name | Mandatory? (Y/N) | UNSDCF Outcome/ UN Women SP Outcome and relevant SDGs | SN Output/Relevant flagship program | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Planned Dates (start-end) |  | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| None planned. |  |  |  |  |  |  |  |  |  |  |  |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |

Please fill out a separate row for each evaluation.

UN Sustainable Development Cooperation Framework (UNSDCF), formerly known as UNDAF.

Outcomes contributing to the SDGs as per the Strategic Plan