| MONITORING, EVALUATION AND RESEARCH PLAN 2023-2027 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Instructions: |  |  |  |  |  |  |  |  |  |  |  |
| Nigeria Country Office |  |  |  |  |  |  |  |  |  |  |  |
| Monitoring and Research Plan 2023-2027 |  |  |  |  |  |  |  |  |  |  |  |
| Activity | UN Women SN Outcome | SN Output/Relevant flagship program | Related indicator/KPI (Y/N, Indicator number, how and when) | Data Collection (Y/N, what data, how) | Office and Person in charge | Partners and stakeholders | Planned Dates (Month and year of start and end) | Donors Involved | Budget |  | Remarks |
|  |  |  |  |  |  |  |  |  | Source | Amount |  |
| Monitoring |  |  |  |  |  |  |  |  |  |  |  |
| Development of the CO's SOP on standards of monitoring/programme feedback - activities their timing/frequency, tools, roles of individual staff members, preparatory documents, etc. | All | All | All | N | All staff |  | Jan-Mar 2023 | All | Core/Non-core | Staff time |  |
| CO coordination and thematic meetings, including results and financial delivery rate monitoring | All | All | All | Y | Programme & Operations Team Leads |  | 01/01/ 2023 - 12/31/ 2027 | All | Core/Non-core | Staff time |  |
| Monitoring missions to intervention areas/sites in the targeted states and LGAs to track progress | All | All | All | Y | M&E and Prog Staff | Relevant partners (Govt. Donors & NGOs/CSOs) | Quarterly every year & as required | All | Core/Non-core | 150,000.00 |  |
| Monitoring missions to inter-agency joint programme intervention areas/sites in the targeted states and LGAs to track progress | All | All | All | Y | M&E and relevant prog. Staff | Relevant UN Agencies | Quarterly every year | EU/PBSO/ Others TBD | Non-core | 30,000.00 |  |
| Quarterly review of the AWP by Thematic Groups | All | All | All | Y | M&E and Prog Leads |  | Quarterly every year | All | Core/Non-core | 25,000.00 |  |
| Joint Annual reviews of the AWP with partners | All | All | All | Y | M&E/ Rep/Deputy Rep | Relevant partners (Govt. UN Agencies& NGOs/CSOs) | November every year | All | Core/Non-core | 60,000.00 |  |
| CO Staff Retreat | All | All | All | Y | M&E/Deputy Rep/Rep |  | Once annually | All | Core/Non-core | 150,000.00 |  |
| UNSCDF JWP monitoring and quality assurance of application of Gender Marker (GEM) code | All | All | All | Y | Deputy Rep/M&E Specialist | UN agencies contributing to the UNSDCF | Half-yearly |  | Core | 5,000.00 |  |
| Mandatory: SN Mid-term Review with partners | All | All | All | Y | M&E/Deputy Rep/Rep |  | June/July: 2025 |  | Core | 10,000.00 |  |
| Research |  |  |  |  |  |  |  |  |  |  |  |
| Mandatory: Country Gender Equality Profile | All | All | All | Y | M&E/Deputy Rep/Rep |  | Jan-March 2026 | All |  | 200,000.00 |  |
| A study on women's equitable access to decent work and entrepreneurship in targeted states Nigeria | SN Outcome 6 | SN output 6.4 | indicator 6.4.1 | Y | WEE Team Lead | Relevant partners (government and private sector) | March-June 2023 | TBD | Non-core | 50,000.00 |  |
| Gender Responsive Analysis of Public Financial Management Frameworks and Policies in Nigeria | SN Outcome 6 | SN output 6.4 | indicator 6.4.1 | Y | WEE Team Lead | Federal Ministry of Finance, Budget and National Planning, NILDS, | Jan to March 2024 | TBD | None-core | 30,000.00 |  |
| A gender audit of the social protection policy and mechanisms in Nigeria | SN Outcome 3 | SN Output 3.1 | indicator 3.1.2 | Y | EVAW/WEE Team Leads | 1. Federal Ministry of Finance, Budget and National Planning; 2. Federal Ministry of Humanitarian Affairs and Social Development | Jan to March 2024 | TBD | Non-core | 35,000.00 |  |
| Thematic studies on women, climate-smart agriculture and DDR including land rigths/decision-making etc. in the targeted states | SN Outcome 2 | SN Output 2.1 | Indicator 2.1.2 | Y | WEE Team Lead | Ministry of Agriculture and Rural Development, Ministry of Women Affairs | March-June 2024 | TBD | Non-core | 60,000.00 |  |
| A study of positive gender social norms that prevent the VAWG in targeted states and LGAS | SN Outcome 4 | SN Output 4.3 | indicator 4.3.1 | Y | EVAW/Spotlight Team Lead | Relevant MDAs/Traditional Institutions/Consultants | February -April 2023 | EU | Non-core | 100,000.00 |  |
| Thematic research on gender, humanitarian, peace, and development nexus with a focus on North-east Nigeria | SN Outcome 4 | SN Output 4.2 | indicator 4.2.1& 4.2.2 | Y | HA Team Lead | Relevant MDAs/UN Agencies/CSOs & Consultants | Jan 2023-Dec. 2026 | Japan/others TBD | Non-core | 150,000.00 |  |
| Thematic research on Women, Peace, and Security in Nigeria (UNSCR 1325) | SN Outcome 4 | SN Output 4.1 | indicators 4.1.2, 4.1.3 &4.1.4 | Y | WPS Team Lead | Relevant MDAs/ UN Agencies/consultants | 01/2023 -12/2026 | Germany/Norway/PBSO | Non-core | 150,000.00 |  |
| Gender Analysis of Nigeria's 2023 general and presidential elections | SN Outcome 5 | Output 5.1 | indicator 5.1.5 | Y | WPE Team Lead | INEC, other relevant MDAs, UN agencies, | March - May 2023 | Canada | Non-core | 30,000.00 |  |
| Other Thematic Research on Women's Political Participation in Nigeria | SN Outcome 5 | Output 5.1 | indicator 5.1.5 | Y | WPE Team Lead | INEC, other relevant MDAs, UN agencies, | July 2023- Dec. 2026 | CANADA | non-core | 100,000 |  |
| Evaluation Plan 2023 - 2027 |  |  |  |  |  |  |  |  |  |  |  |
| Evaluation name | Mandatory (Y/N) | UNSDCF Outcome/ UN Women SN Outcome and relevant SDGs2 | SN Output/ Relevant flagship program | Office and Person in charge | Region/ country | Joint activity (Y/N, indicate partners) | Planned Dates (start-end) | Donors Involved | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| Evaluations in which the office leads |  |  |  |  |  |  |  |  |  |  |  |
| Mid-term Country Programme Evaluation | Y | All | All | Rep/Deputy/M&E Specialist | Nigeria | N | July to Sept. 2025 |  | US$ 100,000, core funds | Pending |  |
| Final Country Portfolio Evaluation CPE | Y | All | All | Rep/Deputy/M&E Specialist | Nigeria | N | May to July 2026 |  | US$100,000, core funds | Pending |  |
| Midterm Evaluation of: Advanced WPE Programme | Y | SN Outcome 5, SDG 5 | Output 5.2 | M&E Specialist/WEE Team Lead | Nigeria | N | July to Sept 2025 | Canada | US$ 40,000, non-core funds | Pending |  |
| Final Evaluation of : Advanced WPE Programme | Y | SN Outcome 5, SDG 5 | Output 5.3 | M&E Specialist/WEE Team Lead | Nigeria | N | June - Sept 2023 |  | US$ 50,000.00 | Pending |  |
| Mid-Term and Final Evaluation of the Programme on Women, Peace, and Security in Nigeria | Y | Outcome 4 | Outputs 4.1 - 4.3 | Nigeria CO WPS Team Lead | Nigeria |  | Jan - March 2025 | Norway | $50,000, non-core funds | Pending |  |
| Mid -Term and Final Evaluation of the Enhancing Gender-Responsive Security Operations and Community Dialogue Project in Nigeria (Phase II) | Y | Outcome 4 | Outputs 4.1 - 4.3 | Nigeria CO WPS Team Lead | Nigeria | N | Feb -May 2024 March- May 2025 | Germany | $50,000, non-core funds | Pending |  |
| Final Evaluation of Affirmative Procurement Project | Y | Outcome 1 | Output 1.2 | Nigeria CO WPE Team Lead | Nigeria | Y | March to May 2024 | AFDB/WEFI | Example: US$60,000, non-core funds | Pending |  |
| Final Evaluation of the Spotlight Initiative in Nigeria | Y | Outcomes 3&4 | Outputs 3.1, 3.2 & 4.3 | Nigeria CO Spotlight Team Lead/M&E Specialist | Nigeria | y | January - June 2024 | EU | 250,000 | Pending |  |
| Evaluations in which the office Participates |  |  |  |  |  |  |  |  |  |  |  |
| UNSDCF Mid Term evaluation | Y | All | All | UN CT/PMT Nigeria | Nigeria | Y | 2025 | N/A | 10,000 | Pending |  |
| UNSDCF final evaluation | Y | All | All | UN CT/PMT Nigeria | Nigeria | Y | 2027 | N/A | 10,000 | Pending |  |