BCO – MONITORING, EVALUATION AND RESEARCH PLAN (MERP) 2019

Monitoring 2019

| Activity | Responsible staff member | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Source | Amount |
| Impact 2 (DRF 2 & 3): Women, especially the poorest and most excluded, are economically empowered and benefit from development |  |  |  |  |  |
| Baseline study for the CGBV project | CGBV Project Manager and Programme Analyst | ICDDR,B | 11/2018- 03/2019 | Non-core available | $ 70000 |
| Impact 4 (DRF 4): Peace and security and humanitarian action are shaped by women leadership and participation |  |  |  |  |  |
| National Resilience Programme (NRP) Implementation Committee Meeting with IPs and UN agencies | Programme Specialist | UNDP, UNOPS, LGED, DDM, DWA, | Quarterly | No cost implication | - |
| NRP Sub Project (MoWCA-UN Women) Implementation and Monitoring Committee Meeting | Programme Specialist, Programme Analyst & Sub Project Director | MoWCA, DWA | Quarterly | Non-core Available | $ 2,000 |
| PVE monthly Project Implementation Coordination Meeting | PVE project manager | BRAC, BNPS, BRAC University | Monthly | Non-core Available | $ 2,000 |
| Monitor perception of the host community and refugee women before and during the short-term project | HoSO and Monitoring and reporting Officer | DFID, IP/RP | Quarterly | Non-core TBM | - |
| Impact 1 (DRF 5): Governance and national planning fully reflect accountability for gender equality commitments and priorities |  |  |  |  |  |
| GRB Project Implementation Committee Meeting GRB Project Steering Committee Meeting Gender Statistics Project Implementation Committee Meeting | Programme Analyst Programme Analyst Programme Specialist- Gender Statistics | MoWCA MoWCA BBS, MoWCA | Quarterly Six Monthly Quarterly | No Cost Implication No Cost Implication Non-Core Avialable | 000 $ 2,000 |
| Cross Cutting |  |  |  |  |  |
| Monthly progress monitoring against AWP 2019 through online motoring tool | Programme Management Specialists | BCO | Monthly | - | No cost implication |
| Monthly Programme Delivery Report Review | Project Managers | BCO | Monthly | - | No cost implication |
| Review of IP/RP progress reports and FACE form and quarterly meetings with IP/RPs | Project Managers | BCO | Quarterly | Non Core Alliable | $ 2,000 |
| Monitoring of the progress of 2019 AWP on quarterly basis in RMS | Country Representative, Programme Management Specialist and Project Managers | BCO | Quarterly | - | No cost implication |

Research Plan 2019

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount |
| Impact 2 (DRF 2 & 3): Women, especially the poorest and most excluded, are economically empowered and benefit from development |  |  |  |  |
| Formative research to develop curriculum for promoting gender equitable roles and respectful relationships in households | Helen Keller International / ICDDRB | 01/2019-12/2019 | Non-core TBM | $ 40,000 |
| Policy brief on finding of the High-Level Panel on Women's Economic Empowerment report and policy recommendations. a | Ministry of Women and Children affairs, Planning Commission, Selected CSOs and private sector, academia | 02/2019 - 04/2019 | Non-core Available | $ 5,000 |
| An in-depth review of the MUSANED platform to address the needs of women migrant workers and recommend ways to expand this platform. | Ministry of Expatriates' Welfare and Overseas Employment, Ministry of Foreign Affairs, Bangladesh Association of International Recruiting Agencies, NGOs, CSOs | 01/2019-02/2019 | Non-core Available | $5,000 |
| Impact 4 (DRF 4): Peace and security and humanitarian action are shaped by women leadership and participation |  |  |  |  |
| Research on social mapping of women's engagement in violent extremism in Bangladesh | Targeted Communities | 10/2017-03/2018 | Non-core Available | $4,800 |
| Research on understanding family reintegration as a deradicalization process, with particular focus on the gender social norms underpinning these choices | Local Government Institutions, CSOs, CBOs | 09/2019-12/2019 | Non-core Available | $10,000 |
| Cost effectiveness of gender responsive Climate Change Adaptation (CCA) investment to build the case for gender mainstreaming in CCA | Ministry of Environment and Forests, Bangladesh Climate Change Trust | 09/2019-12/2019 | Non-core Available | 85,000 |
| Study on potential areas for livelihood and vocational skills development for host community and Rohingya women in the medium term | DFID, IP/RP | 01/2019-04/2019 | Non-core TBM | $ 35,000 |
| Baseline Survey of the host community and refugee women before and during the short-term project | HoSO and Monitoring and reporting Officer | First quarter | Non-core TBM | $25,000 |  |
| End-line Survey of the host community and refugee women at the end of the short-term project | HoSO and Monitoring and reporting Officer | Third quarter | Non-core TBM | $25,000 |  |
| Impact 1 (DRF 5): Governance and national planning fully reflect accountability for gender equality commitments and priorities |  |  |  |  |
| Scoping Study to identify areas for intervention for Gender Justice Programme with government and CSO and promotion in relations to CEDAW General Recommendations. Conduct Beijing + 25 review | UN Women UN Women and MOWCA | 07/2019-10/2019 03/2019- 10/2019 | Core Core | $ 20,000 $ 45,000 |

Evaluation Plan 2019

| Evaluation name | Mandatory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ MCO/ RO AWP Output | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |
| Impact 2 (DRF 2 & 3): Women, especially the poorest and most excluded, are economically empowered and benefit from development |  |  |  |  |  |  |  |  |  |  |  |
| Impact 4 (DRF 4): Peace and security and humanitarian action are shaped by women leadership and participation |  |  |  |  |  |  |  |  |  |  |  |
| Impact 1 (DRF 5): Governance and national planning fully reflect accountability for gender equality commitments and priorities |  |  |  |  |  |  |  |  |  |  |  |
| N/A |  |  |  |  |  |  |  |  |  |  |  |
| Cross Cutting |  |  |  |  |  |  |  |  |  |  |  |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |
| Impact 2: Women, especially the poorest and most excluded, are economically empowered and benefit from development |  |  |  |  |  |  |  |  |  |  |  |
| Final evaluation of the EWMW project | Y |  | Output 2.1.1 & 2.1.2 | ROAP, BKK | Asia pacific | N | MOEWOE, ILO, IOM, NGO/CSOs | Q1, 2019 | SDC |  | BCO is part of this evaluation |
| Impact 4: Peace and security and humanitarian action are shaped by women leadership and participation |  |  |  |  |  |  |  |  |  |  |  |
| Impact 1: Governance and national planning fully reflect accountability for gender equality commitments and priorities |  |  |  |  |  |  |  |  |  |  |  |
| N/A |  |  |  |  |  |  |  |  |  |  |  |
| Country Programme |  |  |  |  |  |  |  |  |  |  |  |
| Country Portfolio Evaluation | Y |  | OEE output 3.3 | RO, BCO | Asia Pacific | N | All relevant partners and stakeholders | Q1 2019 | $50000/New Core |  |  |
| UNDAF Evaluation | Y |  |  | RO, BCO | Asia Pacific | Y | All UN agencies | Q3 2019 |  |  |  |

MUSANED is an online recruiting system for migrant domestic workers introduced by KSA

Please see Guidance on Decentralized Evaluations, link.

Please fill out a separate row for each evaluation.