Annex 2: TEMPLATE – MONITORING, EVALUATION AND RESEARCH PLAN 2016

Monitoring and Research Plan 2016

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount |
| MONITORING |  |  |  |  |
| Projects Tracking and Monitoring activities | MoSD, JNCW, UNESCO, JWU, JEFE, AFDP, AWLN, YFY | Ongoing over years of SN 2014-2017 |  |  |
| Research |  |  |  |  |
| Government of Jordan report on the legislative framework for women’s economic empowerment – with key priorities for policy reform (produced by the Ministry of Social Development) | Government of Jordan | January – April 2016 | Governments of Italy and Finland | $40,499 |
| Assessment on women's access to services at the municipal level undertaken looking at gaps in women’s access to basic services in Jordan’s hosting communities, and entry points for addressing these. | Government of Jordan | January – July 2016 | Government of Japan | $100,0000 |
| Research and documentation on social cohesion in Jordan | Government of Jordan | April - August 2016 | Governments of Italy and Finland | $93,630 |
| Research on gender and radicalization. | Jordanian National Commission for Women | January – February 2016 | Government of Japan | $40,000 |

Evaluation Plan 2016

| Evaluation name | Mandatory? (Y/N) | UNAF Outcome/ UN Women SP Goal, Outcome | Country/ MCO/ RO AWP Output | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |
| Supporting women in host communities and in Jordan’s Refugee Camps through prevention and response to gender based violence and promotion of Self-Reliance and Social Cohesion (Eid-bi-Eid) | Y | UNAF Outcome 3.2 SN 2014-2017 outcomes 1.1. and 1.2 | Jordan UN Women SN Outcome 4 / outputs 4.1.1, 4.1.2, 4.3.1 Responds to Jordan’s National Resilience Plan (NRP) 2014-2016 | Jordan CO | Arab States/ Jordan | N | JEFE, AFDP, MoSD , ARDD | 2016 | 20,000 | Pending | Source of funding: Italy and Finland |
| Promoting Social Cohesion through Women's Economic Empowerment and Protection Initiatives in Irbid and Zarqa | Y | UNAF Outcome 2.4 SN 2014-2017 outcomes 1.1. and 1.2 | Jordan UN Women SN Outcome 4 / outputs 2.1.1, 4.2.1, 4.2.2 | Jordan CO | Arab States/ Jordan | N | JEFE (others TBC) | 2016 | 30,750 | Pending | Source: Government of Japan |
| Mid-Term Review of Jordan Strategic Note 2014-17 | Y | All outcomes under SN 2014-17 | All outputs under SN 2014-17 | Jordan CO | Arab States/ Jordan | N | TBD | June 2016 | 6000$ | initiated | Source: Core resources |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |
| Spring Forward: EU Regional Programme | Y | UNAF outcome 2, output 2.2 SN Outcomes 1.1/1.2/2.1/2.2 | Jordan UN women SN outcome 1.1,1.2, 2.1 Outputs 1.1.2, 1.2.1, 2.1.1 | RO | Arab States/ Jordan | N | JRF, JNCW, YFY | 2016 | 20,000 | Pending | Source of funding: EU |

| Projects Tracking (internally) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Monitoring of all projects AWPs | Y | All related UNAF outcomes related to UN Women SN 2015-2017 |  | Jordan SN AWPs for all components as stated in the SN 2014-2017 |  | Jordan CO | Arab States’ Jordan | N |  | Monthly meetings of the CO Projects Oversight and Monitoring Committee (POMC) |  |  |  |
| Field visits | Y | All UNAF related outcomes related to UN Women SN2014-2017 | Jordan SN AWPs for all components as stated in the SN 2014-2017 |  | Jordan CO |  | Arab States/ Jordan | N | MoSD, JNCW, UNESCO, JWU, JRF, JEFE, AFDP, AWLN, YFY | At regular basis over each year. | N/A |  |  |

| Reporting: Annual projects progress reports | Y | All related UNAF outcomes | Jordan SN AWPs for all components as stated in the SN 2014-2017 | Jordan CO | Arab States/ Jordan | N | MoSD, JNCW, UNESCO, JWU, JEFE, AFDP, AWLN, YFY | As per the various project documents requirements | N/A | Pending |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

Please fill out a separate row for each evaluation.