# Annexe 3: MONITORING, EVALUATION AND RESEARCH PLAN (2014-2018)

| Title & Type of MER Activity | Mandatory (Y/ N) | Relevant UNDAF Outcome/ UN Women SP Goal and Outcome | Relevant Country/ SRO AWP Output | Office to manage the MER activity | Region, Sub Region or Country | Joint MER activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-completion) | Budget (US$) for MER activity/ Sources of Funding | Status (pending - initiated – ongoing - completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1) MONITORING activities to be undertaken by the Country Office e.g. Partner visits, (Repeat) Baselines, Reviews, UN Women Annual Report, Annual Programme and UNDAF Review Process etc. |  |  |  |  |  |  |  |  |  |  |  |
| Training Staff and Key partners on RBM | Y | SP MRF Output 2 |  | Kenya CO | Kenya | Y (IPs and Staff) | Partners | Jan – Mar 2014 Jan – Mar 2016 | 210,000 – Non Core | Pending |  |
| Joint Field verification and monitoring missions | Y | SP MRF Output 2 |  | Kenya CO | Kenya | Y (involving Donors and IPs) | Donors and IPs | Jul&Nov 14 Jul&Nov 15 Jul&Nov 16 Jul&Nov 17 Jul&Nov 18 | 90,000 – Non Core | Initiated |  |
| Conduct quarterly reviews and semi-annual donor review meeting | Y | SP MRF Output 2 |  | Kenya CO | Kenya | Y (Key Partners and Donors) | Partners / Donors | Quarterly 2014 - 2018 | 80,000 | Initiated |  |
| Support partners to develop MER Plans based on the revised AWPs | Y | SP MRF Output 2 |  | Kenya CO | Kenya | Y (involving All partners) | Partners | Jan – Mar 2014/5/6 | 20,000 – Non Core | Pending |  |
| Track partners’ planned monitoring and evaluation budget (MER Plans) | Y | SP MRF Output 2 |  | Kenya CO | Kenya | Y (involving All partners) | Partners | Twice a year, 2014-2018 | 300,000 | Pending |  |
| Follow up on management responses on previous evaluations | Y | SP MRF Output 2 |  | Kenya CO | Kenya |  |  | Quarterly |  | Initiated |  |
| 2a) EVALUATIONS managed by the Country/ Sub-regional/ Regional Office e.g. outcome, thematic, programme evaluations etc. |  |  |  |  |  |  |  |  |  |  |  |
| Economic empowerment mid-term evaluation | Y | SP MRF Output 2 | KCO Outcome 2 | Kenya CO | Kenya | Y (involving All partners) | Partners | September 2015 | 60,000 | Pending |  |
| Kenya Country Strategy mid term evaluation | Y | SP MRF Output 2 | KCO All Outcomes | Kenya CO | Kenya | Y (involving All partners) | Partners | July 2016 | 60,000 | Pending |  |
| Economic empowerment end of project evaluation | Y | SP MRF Output 2 | KCO Outcome 2 | Kenya CO | Kenya | Y (involving All partners) | Partners | March 2017 | 60,000 | Pending |  |
| Kenya Country Strategy final evaluation | Y | SP MRF Output 2 | KCO All Outcomes | Kenya CO | Kenya | Y (involving All partners) | Partners | July 2018 | 65,000 | Pending |  |
| 2b) Other EVALUATIONS in which Country/ Sub-regional/ Regional Office is involved but NOT managing, e.g. evaluations managed by HQ Evaluation Office, Trust Fund on VAW, UNDEF, donors, etc. |  |  |  |  |  |  |  |  |  |  |  |
| 3) RESEARCH Activities undertaken by the Country/ Sub-regional/ Regional Office with regard to the monitoring and evaluation needs of the Annual Work Plans |  |  |  |  |  |  |  |  |  |  |  |
| Conduct an assessment on women friendly financial products offered by Financial Institutions | N | SP MRF Output 2 | KCO Outcome 2 | Kenya CO | Kenya | Y (Key FIs and EE partners) | Partners | Aug 2014 | 35,000 – Non Core | Pending |  |
| A study on the impact of conflict on women – with IPSTC | Y | SP MRF Output 2 | KCO Outcome 4 | Kenya CO | Kenya | Y | Relevant Partners | Nov 2014 | 50,000 – Non Core | Pending |  |
| Thematic assessments on the role of women in devolved governance and humanitarian livelihood support | Y | SP MRF Output 2 | KCO Outcome 5 | Kenya CO | Kenya | Y | Relevant Partners | Nov 2016 | 50,000 – Non Core | Pending |  |
| Thematic assessments on the impact of small grants on women in humanitarian livelihood support | Y | SP MRF Output 2 | KCO Outcome 4 | Kenya CO | Kenya | Y | Relevant Partners | Aug 2017 | 50,000 – Non Core | Pending |  |
| Social-economic impact of Public procurement and enforcement of presidential directive on women entrepreneurs | N | SP MRF Output 2 | KCO Outcome 2 | Kenya CO | Kenya | Y | Relevant Partners | March 2018 | 50,000 – Non Core | Pending |  |

# Annex 2: Evaluation Justification Matrix

| List of selected evaluation | Criteria used for the selection | Potential evaluability | Intended use of evaluation findings |
| --- | --- | --- | --- |
| Economic empowerment evaluation – mid and final | Donor mandatory evaluation |  | Inform decision‐making on policies, developmental and organizational effectiveness and programme design |
| Kenya Coutry Strategy evaluation – mid and final | Donor mandatory evaluation |  | Enhance UN‐Women’s internal accountability and accountability to its key stakeholders Inform decision‐making on policies, developmental and organizational effectiveness and programme design |
| Conduct an assessment on women friendy financial products offered by Financial Institutions | Stakeholders’ focus including donor and government priority areas For accountability to donors and other stakeholders Contributions to decision‐making to enhance effectiveness; and the Potential for organizational and national learning and knowledge generation |  | Contribute to learning and knowledge on women’s empowerment and gender equality Inform decision‐making on policies, developmental and organizational effectiveness and programme design |
| A study on the impact of conflict on women – with IPSTC | For accountability to donors and other stakeholders Contributions to decision‐making to enhance effectiveness; and the Potential for organizational and national learning and knowledge generation |  | Contribute to learning and knowledge on women’s empowerment and gender equality Inform decision‐making on policies, developmental and organizational effectiveness and programme design |
| Thematic assessments on the role of women in devolved governance and humanitarian livelihood support | Contributions to decision‐making to enhance effectiveness; and the Potential for organizational and national learning and knowledge generation Potential for project scale up and replication |  | Contribute to learning and knowledge on women’s empowerment and gender equality Inform decision‐making on policies, developmental and organizational effectiveness and programme design |
| Thematic assessments are planned on the impact of small grants on women in humanitarian livelihood support | Contributions to decision‐making to enhance effectiveness; and the Potential for organizational and national learning and knowledge generation Potential for project scale up and replication |  | Contribute to learning and knowledge on women’s empowerment and gender equality Inform decision‐making on policies, developmental and organizational effectiveness and programme design |
| Social-economic impact of Public procurement and enforcement of presidential directive on women entrepreneurs | Donor mandatory assessment |  | Contribute to learning and knowledge on women’s empowerment and gender equality Inform decision‐making on policies, developmental and organizational effectiveness and programme design |