IV. Monitoring, Evaluation and Research Plan

## IV. Monitoring, Evaluation and Research Plan, 2014-2018

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount |
| SURVEYS |  |  |  |  |
| Gender Sensitive Budget tracking surveys | CCOAIB | 2016 | Non Core | $50,000 |
| Service delivery satisfaction survey ( service delivery on OSC) | GMO, NISR | 2014 | Non core | $30,000 |
| MONITORING ACTIVITIES |  |  |  |  |
| Continous monitoring of supported programmes | All partners | 2014 - 2018 | Nonce core | 200,000 |
| RESEARCH |  |  |  |  |
| Research on access to finance for Women in Informal Cross Border Trade in Rwanda | Mission of Hope | 2014 | Non Core | $40,000 |
| Conduct a study on off farm employment opportunities for rural women | MINAGRI | 2014 | Non Core | $35,000 |

Evaluation Plan 2014-2018

| Evaluation name | Mandatory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome |  | Country/ MCO/ RO AWP Output |  | Office in charge | Region/ country |  | Joint activity (Y/ N, indicate partners) |  | Key Stakeholders |  | Planned Dates (Start-end) |  | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Mid-term evaluation for the Safe Cities Programme | y | Goal 3, Outcome 3.1 |  | Rwanda AWP Output 3.1.2 |  | Rwanda CO | Rwanda |  | N |  | City of Kigali, Rwanda Women Network |  | 2014 |  | $50,000 (non- core) | Planned | Depending on the availability of funds |
| End-line Evaluation for the Safe Cities Programme | y | Goal 3, Outcome3.1 |  | Rwanda AWP Output 3.1.2 |  | RwandaCO | HQ |  | N |  | City of Kigali, Rwanda Women Network |  | 2016 |  | $50,000 (non- core, Safe city project) | Planned | Its mandatory |
| Mid term and Final evaluation for the project for advancing and sustaining women’s gains in Rwanda | Y | Goal 1 Outcome 1.3 |  | Rwanda AWP Output 1.3.1 |  | Rwanda CO | Rwanda |  | Y |  | National Gender Machinery , One UN |  | 2014 (Mid term review)2015, Final evaluation |  | US$ 100,000 from One fund | Planned | New project |
| Final evaluation for the project on national upscaling of OSC initiative | Y | Goal 3 Outcome 3.2 |  | Rwanda AWP, Output 3.2.1 |  | Rwanda CO | Rwanda |  | Y |  | RNP, MoH,MIGEPROF, MINIJUST, One UN |  | 2015, Final evaluation |  | US$ 50,000 from One fund | Planned | New project |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Midterm and final evaluation of the UNDAP | y |  | UNDAP Outcome 2.1: |  | Rwanda AWP Output 3.1.2 | RC office |  | One UN |  | Y |  | UNCT |  | 2016 and 2018 | $200,000 from One Fund | planned | mandatory |
| Final evaluation of Gihundwe OSC | Y | Goal 3, Outcoome |  | Rwanda AWP, Output |  | One UN |  |  |  |  |  |  |  |  |  |  |  |
| Assessment of GBV partners and interventions in humanitarian action | N | Goal 4, outcome 4.2 |  | Rwanda AWP Output 4.2.2 |  | One UN | Rwanda |  | Y |  | UNCHR, UNFPA, MIDIMAR , MIGEPROF |  | 2014 |  | $20,000 from One fund | Planned |  |

Evaluation Justification Matrix

| List of selected evaluation | Criteria used for the selection | Potential evaluability | Intended use of evaluation findings |
| --- | --- | --- | --- |
| Safe Cities Project mid and end tem evaluations | Project budget (…), project duration (2010-2014) | Efficiency, effectiveness, impact, sustainability | To highlight key lessons leant an best practices for similar projects implementation |
| Advancing and Sustaining Women’s Gains in Rwanda mid-term evaluation | Project budget (…), project duration | Relevance, Efficiency, effectiveness, sustainability | Based on findings and recommendations, to define a better orientation for the project |