Bangladesh Country Office

- Evaluation Plan 2022-2026

| Evaluation name | Mandatory (Y/N) | UNSDCF Outcome/ UN Women SP Outcome and relevant SDGs | SN Output/ Relevant flagship program | Office and Person in charge | Region/ country | Joint activity (Y/N, indicate partners) | Planned Dates (Start-end) | Donors Involved | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Endline evaluation of “Combatting Gender Based Violence” (CGBV) project | Y | CF SP5 | SN Output 1.4.1 – 1.4.4 | BCO, Shrabana Datta, KM & Monitoring Analyst | Bangladesh | N | Q4 2022 – Q1 2023 | Government of Canada | USD 40,000 (Non-core) | Initiated | TOR drafted |
| Thematic evaluation of Humanitarian response Programme | Y | CF Outcome: NA/ UN Women SN Outcome 5 | Strategic Note Output 1 and 2 | Cox’s Bazar Silja Rajander, Head of Sub Office | Bangladesh | Y | Q1 2023 – Q3 2023 | CERF, SIDA | 39,500 (non-core available and core tentatively) | To be initiated | This evaluation will combine two end line project evaluations initially planned (“Means to Lead” and CERF Projects) |
| Endline evaluation of “Women’s Empowerment for Inclusive Growth” (WING) joint programme | Y | CF SP1, SDGs: 5, 8, 16 and 17 | SN Output 1.1.3 | BCO, Mehzabin Ahmed, Programme Coordinator, WING | Bangladesh | Y (UNCDF and UNDP) | Q3 2023 | Embassy of the Kingdom of Netherlands | USD 20,000 (Non - core) | Planned |  |
| SN evaluability assessment | N | All | All | BCO, Diya Nanda, DCR | Bangladesh | N | Q3 – Q4 2022 | N/A | USD 20,000 (Core) | Ongoing | Draft report submitted to BCO |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |
| Programme Evaluation of National Resilience Programme | Y | N/A | N/A | UNDP | Bangladesh | Y, UNDP | Q4 2021- Q1 2022 | N/A | N/A | Completed |  |
| Final evaluation of project “Joint Programme on Enhancing social protection for female tea garden workers and their families in Sylhet Division”. | Y | CF SP1 | SN Output 1.1.1 and 1.1.2 | BCO, Tapati Saha, Programme Analyst, WEE | Bangladesh | ILO, UNICEF, UNFPA | Q1- Q3 2022 | SDGF-MPTF | USD 20,000 (Non-core) | Completed |  |
| Evaluation of crisis response in Asia-Pacific (Annex 13 – Case Study on Cox’s Bazar) | N | N/A | SN Outcome 1.5 | RO | Regional, with a case study on Bangladesh | Y, UN Women COs | Q3 2021 – Q2 2022 | N/A | N/A | Completed |  |
| UNSDCF 2022-2026 Evaluation | Y | All UNSDCF Outcomes | All | UNCT | Bangladesh | Y | TBD | TBD | USD 0 (RCO to conduct) | To be initiated |  |

Please fill out a separate row for each evaluation.

Outcomes contributing to the SDGs as per the Strategic Plan