UN Women Bangladesh

MONITORING, EVALUATION AND RESEARCH PLAN 2014-2016 (Updated on Oct- 9-2015)

| Activity | Partners and stakeholders |  | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Source | Amount |
| MONITORING |  |  |  |  |  |
| Each unit and individual to develop own work plan to operationalize the AWP and to monitor to track progress on baseline and targets for all projects |  | UNW Staff | Plans: Q1 Monitoring: ongoing |  | 0 |  |
| Build BCO capacity in gender- and rights-sensitive results based planning, management and monitoring: |  |  | Q1 or Q2 2016 | Core | 5,000 |  |
| Develop and implement monitoring frameworks across current programming and include in all new programming / joint programs |  |  | annually |  |  |  |
| Participate in UNDAF M&E group to provide technical support on gender-sensitive M&E while at the same time strengthening our M&E capacities |  |  | Ongoing |  |  |  |
| Develop baseline data for Benetton and UNICEF funded work under DRF 2 and 3. |  |  | Q1 and Q22016 | TBM Benetton TBM UNICEF | 15,000 40,000 |  |
| Monitoring implementation of UNTF fund implemented by BNPS |  |  |  | ExB | 2,000 |
| Include resources and plan for monitoring and evaluation in all programmes as they are developed |  |  | 2014-2016 |  |  |
| Quarterly review of compliance with operational policies and procedures and progress against OEEF 3 and 4 |  |  | 2015-2016 |  |  |
| Mid-term review of SN/AWP | CSAG, UNCT, ROAP, other key partners |  | 2015 Q4 | Core | 10,000 |
| RESEARCH |  |  |  |  |  |
| An evidence base of women’s current political participation and recommendations on most promising strategies to improve both. | Election Commission, Democracy International |  | Q3, 2016 | Core | 20,000 |
| Joint research with UNDP to develop a body of evidence and analysis that will help establish programme objectives, design and expected impact. Terms of Reference (TORs) have been developed for research papers on the following four areas: 1. Macroeconomic analysis: A gender-based macroeconomic analysis and a high-level demographic summary of women in Bangladesh; 2. Social institutions analysis: Analysis of the influence of social institutions on women’s economic opportunities and constraints; 3. Opportunities analysis (A) – Market: Deep dive on unmet labor supply in the economy with highpotential opportunities for women; and 4. Opportunities analysis (B) – Policy: Deep dive on the current space for policy action, identifying | UNDP |  | Q4,2015 to Q2, 2016 | UNDP (implemented by UNDP) | 150,000 |
| Policy brief on key national and international instruments that can be used to advocate for and achieve improved rights and working conditions for women migrant workers under a Standard Terms of Employment contract. Aimed specifically at policy makers and other government stakeholders | UNW RO, Swiss Development Corporation, GoB, Recruiting Agencies, ILO, IOM |  | Q2, 2016 | Non-core (SDC via ROAP) | 6,000 |
| Research to determine the cost effectiveness of climate change action to deliver on gender outcomes. If the cost implications of gender blind/responsive/aware climate actions could be better measured and articulated that would prove to be a powerful tool for advocacy for gender responsive climate change actions in Bangladesh and other climate vulnerable countries and regions. | Athena Informatics, Shushilan, ActionAid |  | Q1, Q2 2016 | Core | 50,000 (2015) 25,000 (2016) |
| Review of existing policies and institutional practice on sexual harassment in Universities in priority districts | University Grants Commission, Universities, civil society partners |  | 2015 (completed) | SIDA |  |
| Research impacts of gender-responsive budgeting in two government agencies | Ministry of Finance, Local Government Engineering Department, Department of Secondary Education, national women’s groups |  | 2014 (completed) | NC-ADB | 115,000 |
| Comparative cost-benefit analysis of gender sensitive and gender blind climate change adaptation. | BCAS, Ministry of Environment, Bangladesh Climate Change Trust Fund |  | Q2, 2016 | TBM | 100,000 |
| Baseline study and needs assessment of women’s participation in camp management in Rohinya refugee camps | UNHCR |  | 2015 (completed) | NC-UNHCR | Cost of SC |

Evaluation Plan 2014-2016

| Evaluation name | Mandatory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ MCO/ RO AWP Output | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |
| End Evaluation of Building Capacity to Prevent VAW | N | DRF 3 | BCO Output 3.1.2 | BCO | Bangladesh | Y with partners BNWLA and Hedda Production | Four Universities, University Grants Commission Swedish Embassy | May to June 2016 | 11,000 – Non-core (SIDA) | Initiated | ToR preparation going on |
| Final evaluation of Gender and Climate Change project | Y | Outcomes 1.2, , 2.2, 2.3, 4.3 and 5.1 |  | BCO | Bangladesh | BCAS, BRAC | Ministry of Environment, Ministry of Local Government, IUCN, Action Aid | Nov-Dec 2015 | 15,000 NC-RNE | Completed | Reduced budget due to decreased funds - currency fluctuation |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |
| Final evaluation of Decent Work through Migration (lead by ILO, funded by SDC) | Y | Outcomes 2.1, 2.2, 2.3 |  | BCO | Bangladesh | ILO, IOM, BMET | Ministry of Expatriates, network of women migrant workers, other civil society and private sector partners | 2015 Q4 | Funded by ILO | Completed |  |
| Final evaluation of UNTF project, Safe School, Safe Community | Y | Outcome 3.1 | Output 3.1.3 | BCO | UNTF team | Nari Progoti Shongho | MoWCA, civil society | 2017 | Funded by UNTF | Pending |  |

Please fill out a separate row for each evaluation.