UN Women Georgia CO / MERP 2014-2015 / Evaluation Section

| Evaluation name | Mandatory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ MCO/ RO AWP Output | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |
| Final evaluation of UNJP To Enhance Gender Equality in Georgia | Y | UNDAF Outcome 2.1. SP Goal 3, Outcomes 3.1; 3.2. | Georgia AWP Outputs: 3.1.1; 3.2.1;3.2.2 | Georgia CO | Georgia CO | Y (UNDP, UNFPA) | Gender Equality Council; Interagency Council on Domestic Violence; ministry of Internal Affairs; Ministry of Health Labour and Social Affairs; Public Defender’s Office; GEOSTAT | Sep-Nov 2014 | US$27,483 / CS | pending |  |
| Mid-term Review of project Women for Equality, Peace and Development in Georgia | y | UNDAF Outcomes 1.3 & 2.1. SP Goal 2 & 4, Outcomes 2.2 & 4.1; | Georgia AWP Outputs: 2.2.1; 2.2.2; 2.2.3; 4.1.1; 4.2.1 | Georgia CO | Georgia CO | N | Gender Equality Council; Ministry of Internally Displaced Persons from the Occupied Territories, Accommodation and Refugees; Ministry of Labour Health and Social Affairs; Ministry for Regional Development and Infrastructure; Local government in the targeted four regions; Public Defender’s Office | Oct-Nov 2014 | US$10,000 / CS | pending |  |
| Final evaluation of project Women for Equality, Peace and Development in Georgia (WEPD) | y | UNDAF Outcomes 1.3 & 2.1. SP Goal 2 & 4, Outcomes 2.2; 4.1& 4.2; | Georgia AWP Outputs: 2.2.1; 2.2.2; 2.2.3; 4.1.1; 4.2.1 | Georgia CO | Georgia CO | N | Gender Equality Council; Ministry of Internally Displaced Persons from the Occupied Territories, Accommodation and Refugees; Ministry of Labour Health and Social Affairs; Ministry for Regional Development and Infrastructure; Local government in the targeted four regions; Public Defender’s Office | Oct-Nov 2015 | US$76,403 / CS | pending |  |
| Final evaluation of project Innovative Action for Gender Equality in Georgia | y | UNDAF Outcome 2.1. SP Goal 4& 5, Outcomes 4.2 & 5.2; | Georgia AWP Outputs: 4.2.1; 5.2.1; 5.2.2. | Georgia CO | Georgia CO | N | Gender Equality Council; Ministry of Internally Displaced Persons from the Occupied Territories, Accommodation and Refugees; Ministry of Labour Health and Social Affairs; Ministry for Regional Development and Infrastructure; Ministry of Corrections and Legal Assistance. | Apr-Jun 2015 | US$32,564/ CS | pending |  |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |
| UNCT – UNDAF 2011-2015 Final Evaluation | y | UNDAF as a whole | N/A | UN RC Office in Georgia | UNCT Georgia | Y | Government of Georgia – Prime Minister’s Apparatus, Civil Society, donors and international organizations | October 2015 | N/A | pending |  |

|  | GEO AWP Budget and Evaluation Budget Allocation |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | 2014 |  | 2015 |  | 2014-2015 |  |
|  | Planned | Actual | Planned | Actual | Planned | Actual |
| AWP Budget | $2,684,933 | $2,684,933 | $2,497,923 | $1,707,923 | $5,086,873 | $4,296,873 |
| Evaluation Budget |  |  |  |  |  |  |
| 3% Recommended Allocation | $77,669 | $77,669 | $74,938 | $51,238 | $152,606 | $128,906 |
| Actual Allocation | $53,500 | $53,500 | $124,967 | $124,967 | $178,467 | $178,467 |
| % AWP budget allocated to evaluation | 2% | 2% | 5% | 7.4% | 3.5% | 4.7% |
| Non-core funds allocated for evaluation | $41,500 | $41,500 | $112,967 | $112,967 | $154,467 | $154,467 |
| % Evaluation Budget from non-core funds | 78% | 78% | 90% | 90% | 84% | 84% |
|  | Evaluation Expenditure |  |  |  |  |  |
|  | 2014 |  | 2015 |  | 2014-2017 |  |
|  | Planned | Actual | Planned | Actual | Planned | Actual |
| Evaluation | $37,500 | $37,500 | $108,967 | $108,967 | $146,467 | $146,467 |
| Staff cost | $6,000 | $6,000 | $6,000 | $6,000 | $12,000 | $12,000 |
| Capacity Building | $10,000 | $10,000 | $10,000 | $10,000 | $20,000 | $20,000 |
| Evaluation KM & dissemination |  |  |  |  |  |  |
| Total | $53,500 | $53,500 | $124,967 | $124,967 | $178,467 | $178,467 |
| % Budget for evaluation | 2% | 2% | 5% | 7.4% | 3.5% | 4.7% |

Includes all secured costs;

Includes all costs related to UN Women CO functioning and operations in the country – both DRF and MRF costs (includes also the 7% support costs for the cost-share programmes)

Includes all costs directly related to evaluation conduct.

Include a monetization of time spent on evaluation related activities for relevant UNW staff (CR and NPO time and cost-sharing project manager’s time).

Includes all costs related to training of UNW staff and national partners, e.g. trainer travel and DSA, participation in evaluation network conferences / workshops.

Includes evaluation knowledge management related issues and dissemination of evaluation results and findings includes publication cost and dissemination workshops (e.g. publication cost, dissemination workshops