GUATEMALA CO

MONITORING, EVALUATION AND RESEARCH PLAN 2019

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget (per year) 2019 |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount in USD |
| MONITORING |  |  |  |  |  |
| Monitoring gender mainstreaming in UNDAF. | UN System Coordination | Q1, Q2, Q3, Q4 | N/A | N/A |
| Technical assistance and reviews on gender mainstreaming for joint programmes and UN agencies' strategic plans. | UN System Coordination | Q1, Q2, Q3, Q4 | N/A | N/A |
| Quarterly and annual progress reports, annual report for donors and partners. | UN Women Staff, Donors and AFPs | Q1, Q2, Q3, Q4 | N/A | N/A |
| Strategic Note Planning | Analysis, workshops, interviews with participation of UN Women Staff, UN/AFP, women organizations and governmental institutions and other civil society orgs partners | Q3, Q4 | New core | 10,000 |
| Spotlight baseline review | Spotlight partners and other institutions and civil society key actors. | Q1, Q2, Q3 | MPTF/Spotlight | 30,000 |
|  |  | Total |  | 40,000 |
| RESEARCH |  |  |  |  |  |
| Research programs on value chain with a gender perspective | Italy WEE partners and other key actors. | Q1, Q2, Q3, Q4 | Italy WEE | 23,148.15 |
| Country Gender Equality Profile | AFP of UNS, women organizations and governmental institutions and other civil society orgs. | Q1, Q2, Q3, Q4 | Core | 25,144 |
| Design a specialized survey and a study on EVAWG. | UN System, Civil society orgs, governmental and private sector key actors. | Q2, Q3. Q4 | MPTF/Spotlight | 94,785.01 |
| Development of knowledge products on governance gender sensitive on the frame of SDDs. | UN System, civil society organizations and governmental institutions. | Q2, Q3 | New Core | 60,000. |
|  |  | Total |  | 203,077.16 |

EVALUATION PLAN 2019

| Evaluation name | Mandatory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ MCO/ RO AWP Output | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Note Final Evaluation | Yes | Outcomes. #2: Women lead and participate in governance systems. #3: Women have economic autonomy. #4: Women and girls live free from violence. #5: Women contribute to sustainable peace. | GTM | GTM | LAC | No | UN System; Civil Society Orgs, governmental and Private Sector | Q3, Q4 (August – October) | New Core $25,000 | Planned |  |
|  |  |  |  |  |  |  |  | Total | 25,000 |  |  |
| Performance evaluations cycle finalized for all types of contracts. | No | Output Cluster #4 | GTM | GTM | LAC | No | UN Women staff | Q1, Q2, Q3, Q4 | New Core | Ongoing |  |
| Evaluation and audit's management recommendations | Yes |  | GTM | GTM | LAC | Yes | According to the Programs/Projects AFPs, civil society orgs, governamental and private sector partners | Q1, Q2, Q3, Q4 | N/A | Planned |  |
| Strategic Note final evaluation | YES |  | GTM | GTM | LAC | NO | UN System, Civil Society Orgs, governmental and Private Sector partners |  |  |  |  |

Evaluation justification matrix :

| List of selected evaluation | Criteria used for the selection | Potential evaluability | Intended use of evaluation findings |
| --- | --- | --- | --- |
| Strategic Note Final Evaluation | It is important to evaluate the Institutional efforts made to achieve the current SN to strength the Office efforts to increase the level of results-based management of our team. The new UNDAF framework and the recomposition of political forces due the new government in 2020 will be taking into consideration. Due to resource constraints, our CO investments in 2019 will be devoted to the Strategic Note 2014-2019 Final Evaluation (Country Portfolio Evaluation). | High | The findings and recommendations will be used for the design of the new Strategic Note 2020-2024, a document that is going to ensure alignment with the corporate Strategic Plan. Investments in knowledge products and innovative solutions will be embedded in programmatic components (DRF). |