# Annex 1: Jordan & Syria CO Monitoring, Evaluation and Research Plan (MERP) 2014

Monitoring and Research Plan 2014-2017

| Activity | Partners and Stakeholders | Planned Dates (month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount (US $) |
| MONITORING |  |  |  |  |
| Projects Tracking and Monitoring activities | MoPIC, MoSD, NGOs, JOHUD-ZENID, JNCW, MoTA, MoPD, FDA, FoE, UNESCO, Jordan Universities, JWU, JRF, MoF, GBD, MoH, MoL, MoSD | Ongoing over years of SN 2014-2017 | Core Non-Core | $ 1,000 $ 2,000 |
| RESEARCH |  |  |  |  |
| Jordanian Women’s Status in the ICT sector (Trend Analysis Study) | JIDARA Co. Jordanian Universities, MoICT | 20/1/2014- 31/3/2014 | USAID | $30,000 |
| Poverty Pockets Marginalized Women Needs Assessment | Queen Zain Al-Sharaf Institute for Development (ZENID) | 1/1/2014- 31/1/2014 | KAF/EU | $14,000 |
| Collect baseline information for indicators related to outcome 5 “Strengthened accountability systems and capacities of the government to address women’s priorities in national planning, budgeting systems and programming” | GBD,MOF MoPIC,,JNCW | 2014 | EU | $5,000 |
| Conduct a baseline assessment on situation of women in detention | NCHR, Public Security Directorate (PSD), Prisons and detention centers, legal and human rights NGOs visiting prisons. | 2014 | French | $ 23,000 |
| Conduct a baseline study on the management of VAW cases by the justice sector in Jordan | AWLN, MOJ, MOSD, Judicial institute, Judicial council, legal NGOs, FPD, NCFA, NCHR, JNCW | Last quarters of 2013 early 2014 | UN Women Core | $ 50, 000 |

Evaluation Plan 2014

| Evaluation name | Mandatory? (Y/N) |  | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ MCO/ RO AWP Output | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |  |
| Evaluation 1 Achieving E-Quality Project |  | Y | Jordan’s UNDAF (2013-2017) outcome 2.2/ outputs 2.1.2/ 2.2.1 | Jordan UN Women AWP outputs 2.1.2/2.2.1 | Jordan & Syria CO | Arab States/ Jordan | N | Ministry of ICT, Jordanian Universities, QREC | April – July 2014 | US$40,000, USAID | In progress | Evaluation will be implemented between January and March 2014 as per last discussions with USAID |
| Evaluation 2 Volunteerism initiative to enhance young people perception on women rights Project |  | Y | Jordan’s UNDAF (2013-2017) outcome1.2 / output 1.2.1.1/2.1.2 | Jordan UN Women AWP output 1.2.1 | Jordan & Syria CO | Arab States/ Jordan | Y | UNV, , ZENID | January- March 2014 | $10,000 UNV/UNW | in progress | To be conducted in Jan 2014 |
| Evaluations in which the office participates (there isn’t any) |  |  |  |  |  |  |  |  |  |  |  |  |

| Projects Tracking (internally) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Tracking and monitoring of all AWPs to update them regularly | Y | All related Jordan’s UNDAF (2013-2017) outcomes related to UN Women SN 2014-2017 | Jordan SN AWPs for all components as stated in the SN 2014-2017 | Jordan & Syria CO | Arab States’ Jordan | N |  | MoPIC, MoSD, NGOs, JOHUD-ZENID,MoF | 2014 |  |  | pending | This will be followed up and implemented by the M&E FP and the components’ Managers |
| Field Visits & observation | Y | All Jordan’s UNDAF (2013-2017) related outcomes related to UN Women SN2014-2017 | Jordan SN AWPs for all components as stated in the SN 2014-2017 | Jordan & Syria CO | Arab States/ Jordan | N |  | MoTA, MoICT, GBD, MoSD,MoF JNCW, Parliament, FoE, FDA, JRF, JOHUD, ZENID, National Coalition, UNESCO, JWU | At regular basis over the year, |  | N/A | Pending | According to projects schedule and plan |
| Projects Boards and Steering Committees meetings for all ongoing projects | Y | All related Jordan’s UNDAF (2013-2017) outcomes | Jordan SN AWPs for all components as stated in the SN 2014-2017 | Jordan & Syria CO | Arab States/ Jordan | N |  | MoTA, MoICT, GBD, MoSD,MoF JNCW, Parliament, FoE, FDA, JRF, JOHUD, ZENID, National Coalition, UNESCO, JWU | Over all the year( s) at regular basis according to each project management & planning |  | N/A | pending | According to projects plans and management arrangements |
| Reporting: internal progress reports (every 6 months) | Y | All related Jordan’s UNDAF (2013-2017) outcomes | Jordan SN AWPs for all components as stated in the SN 2014-2017 | Jordan &Syria CO | Arab States/ Jordan | N | MoTA, MoICT, GBD, MoSD,MoF JNCW, Parliament, FoE, FDA, JRF, JOHUD, ZENID, National Coalition, UNESCO, JWU.. |  |  | Over all the year(s) at quarterly basis | N/A | Pending |  |
| Financial Reports at quarterly basis | Y | All related Jordan’s UNDAF (2013-2017)outcomes | Jordan SN AWPs for all components as stated in the SN 2014-2017 | Jordan &Syria CO | Arab States/ Jordan | N | MoTA, MoICT, GBD, MoSD,MoF JNCW, Parliament, FoE, FDA, JRF, JOHUD, ZENID, National Coalition, UNESCO, JWU.. |  |  | Over all the year(s) at quarterly basis | N/A | Pending |  |
| Annual reports | Y | All related Jordan’s UNDAF (2013-2017) outcomes | Jordan SN AWPs for all components as stated in the SN 2014-2017 | Jordan &Syria CO | Arab States/ Jordan | N | MoTA, MoICT, GBD, MoSD,MoF JNCW, Parliament, FoE, FDA, JRF, JOHUD, ZENID, National Coalition, UNESCO, JWU |  |  | Over all the year(s) at quarterly basis | N/A | Ongoing at some projects Pending at other ones |  |

| ATLAS Project Management Tools | Y | All related Jordan’s UNDAF (2013-2017) outcomes | Jordan SN AWPs for all components as stated in the SN 2014-2017 | Jordan &Syria CO | Arab States/ Jordan | N | MoTA, MoICT, GBD, MoSD,MoF JNCW, Parliament, FoE, FDA, JRF, JOHUD, ZENID, National Coalition, UNESCO, JWU. | Over all the year(s) at quarterly basis | N/A | Ongoing at some projects Pending at other ones | This is a mandatory for programme personnel |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evidence Based/ information Portal | Y | All related Jordan’s UNDAF (2013-2017) outcomes | Jordan SN AWPs for all components as stated in the SN 2014-2017 | Jordan &Syria CO | Arab States/ Jordan | N | MoTA, MoICT, GBD, MoSD, MOF JNCW, Parliament, NGOs, ZENID, National Coalition, UNESCO, JWU.. | Over all the year(s) at quarterly basis (will be functioned in 2014) | 5,000 | Pending | This is UN Women Database at Jordan & Syria country level in order to ensure evidence based information availability for programming |

# Annex 2: Evaluation Justification Matrix

| List of selected evaluation | Criteria used for the selection | Potential Evaluability | Intended use of evaluation findings |
| --- | --- | --- | --- |
| Final Evaluation of the “Empowering Youth to advocate for women’s human rights through volunteerism Project” | - Mandatory Evaluation by Un Women and UNV - Required by the donor | All the conditions to conduct the evaluation are met | - Evaluate the contribution of the project in the advocating process for CEDAW and human rights. - Identify the project best practices to be utilized for potential planned interventions. - Draw substantive lessons learnt that may be used in any other projects and interventions at national level. - Identify the challenges, obstacles and problems to be avoided and mitigated in the upcoming implementation of other interventions. - Identify the contribution of the project in the MDG, especially the gender equality goals. |
| Final Evaluation of the “Achieving E-quality in the ICT Sector Project” | - Mandatory Evaluation - Required by Donor (USAID) - Gender Equality and Women’s Empowerment pertinence of the project in terms of size, life cycle and strategic objectives that were addressed during the whole entire of the project life cycle | All the conditions to conduct the evaluation are met | - Evaluate the contribution of the project towards GEWE at national and sectoral level. - Identify project best practices and lessons learnt to be used in the next potential upcoming projects and interventions. - Identify the project weaknesses, strengths, challenges and obstacles for being avoided during any programmed and planned projects and interventions. - Assess the contribution of the project towards the MDGs in Jordan, especially gender equality and poverty alleviation |