UN WOMEN TIMOR-LESTE

MONITORING, EVALUATION AND RESEARCH PLAN (MERP) 2020

| SN Impact/Outcome | Activity | Responsible staff member | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  | Status Update |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Source | Amount | (month/year) |
| MONITORING 2019 |  |  |  |  |  |  |  |
| SP Outcome 1: A comprehensive and dynamic set of global norms, policies and standards on gender equality and the empowerment of all women and girls is strengthened and implemented | Review Normative outcome and update the progress in the log frame; Review Normative output and Activity results and add inputs into RMS for Quarterly Reports | WEE, WPS (EVAW & Leadership) officers, OM & HO | UNFPA and other agencies, Statistics Office, SEII, MAF, and HCT. | 1/2020, 4/2020, 7/2020, 10/2020 | IB | NA (% of staff time) |  |
| SP Outcome 3: Women have income security, decent work and economic autonomy (WEE) | Review WEE outcome and update the progress in the log frame; Review WEE output and Activity results and add inputs into RMS for Quarterly Reports | WEE Officers | Ministry of Transport; Civil Service Commission; Municipality of Baucau; CSO partners (TBD) | 1/2020, 4/2020, 7/2020, 10/2020 | Core | 12,000 (travel + % of staff time= 5% of overall WEE budget) |  |
| SP Outcome 4: Normative and policy frameworks are promoted and adapted in line with international standards, and institutions have the commitment, knowledge and capacities to legislate, plan, implement and monitor policies to address VAWG and intimate partner violence. | Review EVAW outcome and update the progress in the log frame; Review EVAW output and Activity results and add inputs into RMS for Quarterly Reports, Spotlight Reports | EVAW Officers | SEII, CSOs (TBD) | 1/2020, 4/2020, 7/2020, 10/2020 | Non-core | NA (% of staff time) |  |
| SP Outcome 5: Women and girls contribute and have greater influence in building sustainable peace and resilience, and benefit equally from the prevention of natural disasters and conflicts and from humanitarian action (WPS) | Review WPS outcome and update the progress in the log frame; Review WPS Output and Activity results and add inputs into RMS for Quarterly Reports | WPS officers (including EVAW & Leadership and Prevention officers) | Ministry of Interior (MoI); MoE; Secretary of State for Equality and Inclusiveness (SEII); CSOs (ADTL) | 1/2020, 4/2020, | Non-Core | 20,000 (Travel, workshops + % of staff time) |  |
| OEE: Organizational Effectiveness and Efficiency | Monitor OEE and report: quarterly & annually | Comms Officers, OM & HO |  | 1/2020, 4/2020, 7/2020, 10/2020 | Core | NA (% of staff time) |  |
|  | Baseline of UNSDCF (and monitoring final year of UNDAF) | Programme Officers, OM and HO | UN sister agencies, | 1/2020, 4/2020, 7/2020, 10/2020 | IB | NA (% of staff time) |  |

Research Plan 2020

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount |
| RESEARCH |  |  |  |  |
| SP Impact 3: Participatory Action Research on DV Law | Under Spotlight Output 1: Participatory Action Research on survivor experiences with DV law (to be managed via PCA (Call for Proposals to be conducted in January) | 1 January – September 2020 | Non-Core | 20,000 |
| SP Impact 3: Spotlight Baseline | UNFPA to lead (CO to contribute) | January-June 2020 | Non-Core | NA -Staff time (Budget managed by UNFPA) |

Evaluation Plan 2020

| Evaluation name |  | Mandatory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome |  | Country/ MCO/ RO AWP Output |  | Office in charge |  | Region/ country | Joint activity (Y/ N, indicate partners) |  |  | Key Stakeholders | Planned Dates (start-end) |  | Budget (US$) / Sources of Funding |  | Status (pending/ initiated/ ongoing/ completed) |  |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Evaluation of the NAP 1325 (2016 – 2020) and report on UN Women’s contribution to the implementation of the NAP | Y |  | SP Outcome 5: Women and girls contribute and have greater influence in building sustainable peace and resilience, and benefit equally from the prevention of natural disasters and conflicts and from humanitarian | Timor-Leste |  | TLCO |  | Timor Leste |  |  | Y (with Ministry of Interior) | Implementing partners under the NAP 1325; RO evaluation specialist |  |  | 01/2020– 05/2020 |  | 40,000 |  | Discussions ongoing; concept note drafted | This evaluation will be done jointly with the GoTL to evaluate the NAP 1325 (2016 – 2020). A specific report will be developed to assess the contribution from UN Women to the NAP 1325 implementation, under the Japan funded project. |  |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |