MONITORING, EVALUATION AND RESEARCH PLAN (MERP) 2017 – MCO Maghreb

NOTE: Examples have been included below to illustrate how to complete each column; they are not meant to be accurate to real life activities. Remember that MERP has to be linked with many of the outputs and activities planned for in the OEEF.

Monitoring 2017

| SN Impact/Outcome | Activity | Responsible staff member | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Source | Amount |
| MONITORING |  |  |  |  |  |  |
| Morocco |  |  |  |  |  |  |
| OEEF output cluster 2.1 | Update RMS- Quarterly monitoring of activities | Focal point per Output in RMS | Internal staff | 4/2017 – 7/2017 – 10/2017 | n/a | n/a |
| OEEF output cluster 4.1 | Produce a Result- based corporate annual report Annual report | Reporting focal point | All partners and UNW | 1/2017 | n/a | n/a |
| OEEF output cluster 4.1 | Produce Result based Countries quarterly reports to RO | Reporting focal point | Internal staff | 4/2017 – 7/2017 – 10/2017 | n/a | n/a |
| SP Impact 5/Outcome 5. | Technical Committee meetings: Monthly monitoring of activities of the project ”Promote and strengthen the institutionalization of equality in the public policies, Morocco” | Programme Coordinator: Amina Lotfi | Ministry of Solidarity, Women, Family and Social Development and UNW | Monthly (first Monday of every month) | n/a | n/a |
| SP Impact 5/Outcome 5. | Technical Committee meetings: Monthly monitoring of activities of the project “Mainstreaming of gender in the public service” | Programme Coordinator: Amina Lotfi | Ministry of public service and modernization of public administration + Interdepartmental coordination network | Monthly (first Monday of every month) | n/a | n/a |
| OEEF output cluster 1.1 | Technical Monitoring Committee of the GRB Center of Excellence project | Programme Associate: Saadia Sifi | Ministry of Economy and Finance (Budget Department, Studies and Financial Forecasts Department, General Affairs Department), UNW | 3/2013 ; 6/2017 ; 9/2017 ; 12/2017 | n/a | n/a |
| SP Impact 5/Outcome 5.2 | Steering Committee meetings of the GRB Center of Excellence project | MCO Representative Leila Rhiwi | Ministry of Economy and Finance and UNW | 06/2013 ; 12/2017 | NA | NA |
| SP Impact 5/outcome 5.2 | Technical Committee meetings | Project officer: Maria Frias | Ministry of Interior and UNW | Monthly meetings | NA | NA |
| SP Impact 5/outcome 5.2 | Steering Committee meeting | MCO Representative Leila Rhiwi | Ministry of Interior and UNW | 3/2017 | NA | NA |
| TUNISIA |  |  |  |  |  |  |
| Tunisia Baseline data collection and analysis: | Support the elaboration of Gender analysis of the national 2014 census in 4 governorates | National Programme Officer, Walid Said | National Institute of Statistics & MoWFC | 1/2017 - 4/2017 | NA | $ 4,000 |
| Algeria |  |  |  |  |  |  |
| SP Impact 1/outcome 1.2 SP Impact 3 /outcome 3.1 | Technical Committee meetings: Quarterly monitoring of activities of the programme “Strengthening the effectiveness of gender equality between women and men in Algeria 2015-2018” | Project officer: Farah Outeldait | Ministry of Interior and local Collectivities/ Parliament / Ministry of Communication / Ministry of National Solidarity, Family and Women Condition | Quarterly meetings |  |  |
| SP Impact 1/outcome 1.2 SP Impact 3 /outcome 3.1 and 3.2 | Steering Committee meeting: 2 per year | National Programme Officer, Imane Hayef | MOFA and UNW and Representative of Ministry of Interior and local Collectivities/ Parliament / Ministry of Communication / Ministry of National Solidarity, Family and Women Condition | Semi-annual meetings |  |  |
| SP Impact 3 /outcome 3.2 | Technical Committee meetings: Quarterly; Monitoring the implementation of the programme communication plan | Project officer: Farah Outeldait | UNW, Communication consultant and the programme technical committee (depending on the agenda of the committee members) | Quarterly meetings |  |  |

Research Plan 2017

| Activity | Partners and stakeholders |  |  | Planned Dates (Month and year of start and end) |  | Budget |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Source | Amount |
| RESEARCH |  |  |  |  |  |  |  |
| Algeria |  |  |  |  |  |  |  |
| Brief report on knowledge products and data on VAW in Algeria produced during the last decade. |  | NGO / unit research of university | September 2017 (3rd quarter) |  | Non-core |  | $ 6,000 |
| Study on women socio- professional position in the media sector and on the gender approach in the audio-visual broadcasts. |  | Ministry of Communication | February 2017 (1rst quarter) |  | Non Core |  |  |
| Study based on a survey on Opportunities and constraints of local elected women |  | Ministry of Interior | March 2017 (1rst quarter) |  | Non Core |  |  |
| Preliminary report on a survey on the level of commitment to gender equality values in Algerian society (comparative analysis with the 2000 and 2008 results) |  | Unwomen/ CSO | November 2017 (third quarter) |  | Non Core |  | $40, 000 |
| Morocco |  |  |  |  |  |  |  |
| Gender-sensitive guide on budgeting at the local level, | Ministry of Interior- General Directorate of local governments |  |  | February 2017 |  | Non-core | $ 5,000 |
| Analytical assessment and technical support of gender equality mechanisms in the different departments of the machinery of women and other ministries at the central and regional levels | Ministry of Solidarity, Women, Family and Social Development |  |  | December 2016 - March 2017 |  | Non-core | MAD 262,000 |
| Development of the strategic framework for the social pole for Economic empowerment Of women and its operational plan | Ministry of Solidarity, Women, Family and Social Development |  |  | Dec 2016-April 2017 |  | Non-core | MAD 336,000 |
| Internal and external communication strategy of the PS on gender equality | Ministry of Solidarity, Women, Family and Social Development |  |  | June 2015-march 2017 |  | Core & non-core | MAD 492,000 |
| Perception survey on Moroccans’ (women & men) attitudes and behaviors 10 years after the application of the Family Code | Ministry of Solidarity, Women, Family and Social Development |  |  | Publication Jan 2017 |  | Non-core | $ 53,534 |
| Gender diagnosis on the local services that target women, girls, and elderly | Ministry of Solidarity, Women, Family, and Social Development |  |  | Jan – June 2017 |  | Non-core | $ 10,400 contract still not awarded |
| Study to identify promising sectors for women's income activities and a study on the structural causes of women's low labor rate | Ministry of Employment |  |  | Jan 2017 – December 2017 |  | Non-core (soft-TBM) | $40,000 |
| Analysis report on the time use survey results | High-commissioner of Plan |  |  | Aug 2016- July 2017 |  | Core | $ 25,200 |
| Guide to include gender mainstreaming in the Action Plans of the Municipalities | Ministry of Interior- General Directorate of local governments |  |  | February 2017 |  | Non-core | $ 5,000 |
| Study on elected women at the local level which includes a training programme to support the capacities of elected men and women on gender and governance. | Ministry of Interior- General Directorate of local governments |  |  | February 2017 |  | Non-core | $ 10,000 |
| Procurement Manuel to support the operationalization of the Equity, Equal Opportunities and gender approach entities at the local level | Ministry of Interior- General Directorate of local governments |  |  | February 2017 |  | Non-core | $ 5,000 |
| Study on perception of the concept of Qiwamah | National Center of studies and research in Islam (CERFI) |  |  | September 2016 – December 2017 |  | Non-core | $ 71,000 |
| Tunisia |  |  |  |  |  |  |  |
| Impact of repression on Women’s victims’ private life in Tunisia | Truth and Dignity Commission |  |  | 02/2017 - 06/2017 |  | Core | $ 6,000 |
| Study on Gender and violent extremism in Tunisia | OXFAM |  |  | 01/2017 -04/2017 |  | Non-Core | $ 16,300 |
| Baseline study on the 1325 UNSCR implementation in Tunisia | CREDIF |  |  | 09/2016 – 02/2017 |  | Non-Core | $ 9,500 |
| Joint study on the stigmatization and discrimination of people living with HIV, STIGMA index | UNAIDS and UNDP |  |  | 04/2017 - 09/2017 |  | Non-core UBRAF TBM | $ 10,000 |
| Elaborate a gender-sensitive monitoring plan of the 5-year national development plan | Ministry of development, investment & international cooperation & UNDP |  |  | 01/2017 – 06/2017 |  | Core | $ 5,000 |

Evaluation Plan 2017

| Evaluation name | Mandatory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome |  | Country/ MCO/ RO AWP Output | Office in charge |  | Region/ country |  |  | Joint activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding |  | Status (pending/ initiated/ ongoing/ completed) |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Evaluation of the partnership between Ministry of Interior, General Directorate of Local Governments and UNW | y | SP Impact 5/outcome 5.2 |  | Morocco AWP Output 5.1 | Morocco MCO |  | Morocco |  |  | Y | Ministry of Interior-General Directorate of Local Governments | August-October 2017 | $ 15,198 Non-Core |  | Pending |  |  |
| Tunisia: Mid-Term Evaluation of "Establishment of inter sectoral mechanisms for the support of women victims of violence | N | SP Goal 3, Outcome 3.2 |  | Tunisia AWP Output 3.2.2 | Tunisia PP |  | Tunisia |  |  | Y | Jointly with MoWFC & NOFP (MoPH) | May –Dec 2017 | $ 1,500 Core funds |  | Pending |  |  |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Evaluation of the project Centre Batha with the IPDF | Y | SP Impact 3, Outcome3.2 |  |  |  | Morocco MCO |  | Morocco | N |  | IPDF-Wilaya-local NGO | Jan-May 2017 |  | $ 10,000 TF to end violence against women |  | initiated |  |

Please see Guidance on Decentralized Evaluations, link.

Please fill out a separate row for each evaluation.