


Annex 4 – Monitoring, Evaluation and Research Plan (MERP) 2018-22


	Activity 
	Partners and stakeholders 
	Planned Dates 
(Month and year of start and end)
	Budget

	
	
	
	Source
	Amount USD

	MONITORING

	Quarterly and annual reporting
	Fiji MCO - all programmes plus operations 
	Quarterly (April, July, October) and annually (January)

	Core/IB
	Staff time

	WPEL ongoing monitoring
	Fiji MCO
	Monthly throughout the programme

	Non-core TBM
	75,000

	Markets for Change ongoing results monitoring including six-monthly surveys of market vendors and council staff and annual vendor profiles

	Fiji MCO, market vendors, municipal councils, national government partners  
	Monthly throughout the programme 
	Non-core (available and TBM) 

	250,000

	EVAW FPI ongoing results monitoring 

	Fiji MCO
	Monthly throughout the programme
	Non- Core (DFAT, EU)
	250,000




	Activity 
	Partners and stakeholders 
	Planned Dates 
(Month and year of start and end)
	Budget

	Humanitarian programming ongoing monitoring

	Fiji MCO
	Monthly throughout the programme
	Non Core TBM./Core
	100,000

	Develop new Strategic Note including establish indicators, baselines and targets for the 2023-2028 DRF in alignment with FPIs, the new UN Women Strategic Plan and the new UNPS

	Fiji MCO
	January to September 2022
	Core
	20,000

	Mid-Term Review of the Fiji MCO Strategic Note

	Fiji MCO
	July to September 2020
	Core
	20,000

	Participation in DMEG on UNPS results monitoring

	UN agencies within DMEG
	Annually in November
	IB
	Staff time

	RESEARCH

	M4C - Market By-Law review and assessment in Fiji, Solomon Islands and Vanuatu

	CLGF and Ministries of Local Government
	To be confirmed
	Non- Core
	50,000

	M4C - research into potential new market sites and sectors (eg, Gizo market in Solomon Islands, tbc: handicraft and seafood sectors in Fiji, Solomon Islands and Vanuatu)

	Fiji MCO and DFAT
	May-August 2018
	Non- Core
	50,000

	M4C - research on strengthening programmatic linkages between M4C and agricultural activities

	Fiji MCO and DFAT
	May-August 2018
	Non-core and Core
	100,000

	EVAW - impact evaluations on prevention programmes in Fiji and Kiribati
	Equality Institute, Fiji MCO, EU, DFAT, Ministry of Women, Children and Poverty Alleviation in Fiji, Ministry for Women, Youth, Social Affairs in Kiribati
	Continuously over four years, commencing January and to be completed by August 2021
	Non- Core (EU, DFAT)
	tbc: $1.8 million

	EVAW - barriers to women’s participation in sport 

	Fiji MCO
	July – September 2018
	Non- Core (EU, DFAT)
	tbc: S100,000

	EVAW - essential services 
(area of focus to be confirmed)

	Fiji MCO
	To be confirmed
	Non- Core (EU, DFAT)
	tbc: S100,000

	EVALUATION

	M4C Mid-term Review
	Fiji MCO, market vendors, municipal councils, national governments partners  
	05/2018 - 07/2018
	Non-Core (DFAT)
	60,000

	EVAW Final Evaluation
	Fiji MCO, national governments, partners  
	07/2022 -  09/2022
	Non-Core (DFAT)
	tbc

	M4C Final Evaluation
	Fiji MCO, market vendors, municipal councils, national governments partners  
	07/2022 -  09/2022
	Non-Core (DFAT)
	tbc

	REPORTING

	Markets for Change donor (DFAT) reporting 
	Fiji MCO, UNDP
	Six monthly (July and January,  activity based reports) and annually (June, results based report with RO review expected in April) 

	Non core
	Staff time

	EVAW donor (EU and DFAT) reporting
	Fiji MCO, PIFS, SPC 
	 Annually (June, with RO review expected in April) 

	Non core
	Staff time

	UN Trust Fund on EVAW donor reporting
(project ends 31 December 2017)
	Fiji MCO, UN Joint Program Partners in Solomon Islands and JPO service providers

	March 2018
	Non Core
	10,000

	EVAW reporting on Essential Services for Kiribati and Solomon Islands (project ends 30 June 2019)
	Fiji MCO, UNFPA
	2018 and 2019
Six monthly (July, January)
	Non Core
	Staff time

	Women, Peace and Humanitarian Fund Reporting
	Fiji MCO
	Annually in August
	Non Core
	Staff time






	
Evaluation name
	Mandatory?
(Y/N)
	DRF Output
	Office in charge
	Region/ country
	Joint activity 
(Y/ N, indicate partners)
	Key Stakeholders
	Planned Dates 
(start-end)
	Budget (USD) / Sources of Funding
	Status (pending/ initiated/ ongoing/ completed)
	Remarks

	Evaluation

	UN Trust Fund on EVAW final evaluation
(project ends 31 December 2017)
	Yes
	Tbc
	Fiji MCO
	Pacific
	N
	UNTF partners
	February-March 2018
	TBC
	
	

	M4C final evaluation
	Yes
	tbc
	Fiji MCO
	Pacific
	Yes: DFAT
	market vendors, municipal councils, national government partners  
	March – June 2019
	150,000 Non-core (DFAT) and TBM

	
	

	M4C phase 2 final evaluation 
	No
	tbc
	Fiji MCO
	Pacific
	TBD
	market vendors, municipal councils, national government partners  
	July – September 2022
	100,000 Non core TBM
	
	The project does not yet exist. This is foreseen at this stage.

	EVAW final evaluation
	Yes
	tbc
	Fiji MCO
	Pacific
	Yes: EU, DFAT, PIFS, SPC
	Government and CSO partners
	July- September 2022
	Non-core (EU, DFAT)
200,000
	
	

	End evaluation of the UNPS
	Yes
	OEEF
	UNRC Office
	Pacific
	Yes; UNRC office and UNCT
	UNCT
	September- December 2021
	5,000 Core
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