Annex 4 – Monitoring, Evaluation and Research Plan (MERP) 2018-22

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Source | Amount USD |
| MONITORING |  |  |  |  |  |
| Quarterly and annual reporting | Fiji MCO - all programmes plus operations | Quarterly (April, July, October) and annually (January) | Core/IB | Staff time |
| WPEL ongoing monitoring | Fiji MCO | Monthly throughout the programme | Non-core TBM | 75,000 |
| Markets for Change ongoing results monitoring including six-monthly surveys of market vendors and council staff and annual vendor profiles | Fiji MCO, market vendors, municipal councils, national government partners | Monthly throughout the programme | Non-core (available and TBM) | 250,000 |
| EVAW FPI ongoing results monitoring | Fiji MCO | Monthly throughout the programme | Non- Core (DFAT, EU) | 250,000 |

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |  |
| --- | --- | --- | --- | --- | --- |
| Humanitarian programming ongoing monitoring | Fiji MCO | Monthly throughout the programme | Non Core TBM./Core | 100,000 |
| Develop new Strategic Note including establish indicators, baselines and targets for the 2023-2028 DRF in alignment with FPIs, the new UN Women Strategic Plan and the new UNPS | Fiji MCO | January to September 2022 | Core | 20,000 |
| Mid-Term Review of the Fiji MCO Strategic Note | Fiji MCO | July to September 2020 | Core | 20,000 |
| Participation in DMEG on UNPS results monitoring | UN agencies within DMEG | Annually in November | IB | Staff time |
| RESEARCH |  |  |  |  |  |
| M4C - Market By-Law review and assessment in Fiji, Solomon Islands and Vanuatu | CLGF and Ministries of Local Government | To be confirmed | Non- Core | 50,000 |
| M4C - research into potential new market sites and sectors (eg, Gizo market in Solomon Islands, tbc: handicraft and seafood sectors in Fiji, Solomon Islands and Vanuatu) | Fiji MCO and DFAT | May-August 2018 | Non- Core | 50,000 |
| M4C - research on strengthening programmatic linkages between M4C and agricultural activities | Fiji MCO and DFAT | May-August 2018 | Non-core and Core | 100,000 |
| EVAW - impact evaluations on prevention programmes in Fiji and Kiribati | Equality Institute, Fiji MCO, EU, DFAT, Ministry of Women, Children and Poverty Alleviation in Fiji, Ministry for Women, Youth, Social Affairs in Kiribati | Continuously over four years, commencing January and to be completed by August 2021 | Non- Core (EU, DFAT) | tbc: $1.8 million |
| EVAW - barriers to women’s participation in sport | Fiji MCO | July – September 2018 | Non- Core (EU, DFAT) | tbc: S100,000 |
| EVAW - essential services (area of focus to be confirmed) | Fiji MCO | To be confirmed | Non- Core (EU, DFAT) | tbc: S100,000 |
| EVALUATION |  |  |  |  |  |
| M4C Mid-term Review | Fiji MCO, market vendors, municipal councils, national governments partners | 05/2018 - 07/2018 | Non-Core (DFAT) | 60,000 |
| EVAW Final Evaluation | Fiji MCO, national governments, partners | 07/2022 - 09/2022 | Non-Core (DFAT) | tbc |
| M4C Final Evaluation | Fiji MCO, market vendors, municipal councils, national governments partners | 07/2022 - 09/2022 | Non-Core (DFAT) | tbc |
| REPORTING |  |  |  |  |  |
| Markets for Change donor (DFAT) reporting | Fiji MCO, UNDP | Six monthly (July and January, activity based reports) and annually (June, results based report with RO review expected in April) | Non core | Staff time |
| EVAW donor (EU and DFAT) reporting | Fiji MCO, PIFS, SPC | Annually (June, with RO review expected in April) | Non core | Staff time |
| UN Trust Fund on EVAW donor reporting (project ends 31 December 2017) | Fiji MCO, UN Joint Program Partners in Solomon Islands and JPO service providers | March 2018 | Non Core | 10,000 |
| EVAW reporting on Essential Services for Kiribati and Solomon Islands (project ends 30 June 2019) | Fiji MCO, UNFPA | 2018 and 2019 Six monthly (July, January) | Non Core | Staff time |
| Women, Peace and Humanitarian Fund Reporting | Fiji MCO | Annually in August | Non Core | Staff time |

| Evaluation name | Mandatory? (Y/N) | DRF Output | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-end) | Budget (USD) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluation |  |  |  |  |  |  |  |  |  |  |
| UN Trust Fund on EVAW final evaluation (project ends 31 December 2017) | Yes | Tbc | Fiji MCO | Pacific | N | UNTF partners | February-March 2018 | TBC |  |  |
| M4C final evaluation | Yes | tbc | Fiji MCO | Pacific | Yes: DFAT | market vendors, municipal councils, national government partners | March – June 2019 | 150,000 Non-core (DFAT) and TBM |  |  |
| M4C phase 2 final evaluation | No | tbc | Fiji MCO | Pacific | TBD | market vendors, municipal councils, national government partners | July – September 2022 | 100,000 Non core TBM |  | The project does not yet exist. This is foreseen at this stage. |
| EVAW final evaluation | Yes | tbc | Fiji MCO | Pacific | Yes: EU, DFAT, PIFS, SPC | Government and CSO partners | July- September 2022 | Non-core (EU, DFAT) 200,000 |  |  |
| End evaluation of the UNPS | Yes | OEEF | UNRC Office | Pacific | Yes; UNRC office and UNCT | UNCT | September- December 2021 | 5,000 Core |  |  |