MONITORING, EVALUATION AND RESEARCH PLAN (MERP) 2020

Monitoring 2020

| Activity | Responsible staff member | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget (USD) |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Source | Amount |
| MONITORING 2020 |  |  |  |  |  |  |
| Impact 2: Women have income security, decent work and economic autonomy |  |  |  |  |  |  |
| Reports from Partners |  |  |  |  |  |  |
| Quarterly Narrative Report | Suhela Khan | TBD | 1st, 2nd, 3rd and 4th Quarter, 2020 | Non Core and Core | TBD |
| Monitoring Missions |  |  |  |  |  |  |
| 2 Monitoring Missions for implementing monitoring tools for program on women in value chain it will include developing training modules, tools and methodologies and undertaking follow ups, pre-post training/impact assessment Updated: In light of the COVID-19 Pandemic lockdown restrictions | Suhela Khan and Noopur Jhunjhunwala | TBD | 1st and 4th Quarter, 2020 | Non Core and Core | 2300 |
| 2.2.3.10 monitoring of WeEmpowerAsia | Suhela Khan |  |  | Non-Core | 4000 |
| 2.1.3.11 Support GEWE advocates to implement the contextualized recommendations of HLP for strengthening economic rights of women workers in the informal sector | Suhela Khan |  |  | Core |  |
| Impact 3: All women and girls live a life free from all forms of violence |  |  |  |  |  |  |
| Reports from Partners |  |  |  |  |  |
| Quarterly Narrative Reports from the NGO partners for the Essential Services Programme | Anju Pandey | TBD | 1st, 2nd, 3rd and 4th Quarter, 2020 |  |  |
| Monitoring Missions |  |  |  |  |  |
| 1 monitoring mission to support the programme on Essential Services being implemented in the Udalgiri district in Assam | Noopur Jhunjhunwala and Anju Pandey | TBD | 1st Quarter 2020 | Non Core | 800 |
| 1 Monitoring Visit to the Department of Women Empowerment in the state of Rajasthan to support the ongoing work on preventing and responding to sexual harassment in public and work spaces to make cities safer for women and girls in the focus states. Update: Deferred due to COVID-19 travel restrictions | Noopur Jhunjhunwala and Anju Pandey | Department of Women Empowerment, Government of Rajasthan | 2nd Quarter 2020 | Core | 800 |
| 1 Monitoring Visit to the Department of Women Empowerment in the state of Madhya Pradesh to support the ongoing work on preventing and responding to sexual harassment in public and work spaces to make cities safer for women and girls in the focus states. | Noopur Jhunjhunwala and Anju Pandey | Department of Women Empowerment, Government of Madhya Pradesh | 3nd Quarter 2020 | Core | 700 |
| Impact 6: A comprehensive and dynamic set of global norms, policies and standards on gender equality and the empowerment of all women and girls is strengthened and implemented |  |  |  |  |  |  |
| Monitoring Missions |  |  |  |  |  |
| 1 monitoring mission to attend the gender trainings being organized for the paramilitary forces Update: Cancelled due to COVID-19 travel restrictions | Noopur Jhunjhunwala and Sanya Seth | CUNPK; RAF; BSF |  |  |  |
| Convene and support high-level and high-impact advocacy forums with civil society and national government, including the CSW Civil Society And Youth Dialogues; Generation Equality Forums, High Level Political Forum; support CSO briefings and multi-stakeholder dialogues including through our existing partnerships with UN Women CSAG members, Beijing+25 CSO Steering Committee members and Feminist Policy Collective | Sanya Seth |  | 1st, 2nd, 3rd, 4th Quarters 2020 | Core | 23000 |
| Monitor and influence, from a gender equality perspective, processes related to Gender and Human Rights, including the Gender Vision 2035 of Niti Aayog, Gender Index by Niti Aayog, draft Women's Empowerment Bill 2016, Universal Periodic Review, CEDAW, Agenda 2030, Beijing Platform for Action and NAP on VAWG | Sanya Seth |  |  | Core | 25000 |
| Impact 5: Frontier Issue |  |  |  |  |  |  |
| 5.1.13.12 Regular Monitoring visits and reporting at country level | Kanta |  |  | Non-core | 10,000 |
| Output Cluster 2 |  |  |  |  |  |  |
| Convene bi-annual meetings of the CSAG to seek inputs on UN Women's programming and discuss key intergovernmental processes | Sanya |  |  | Non-core | 6,000 |
| Convene bi-annual meetings of the Business Sector Advisory Council to share UNW's programme and ensure shared-value base programming, | Noopur Jhunjhunwala |  |  | Non-Core | $5,000 |

Research Plan 2020

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget (USD) |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Source | Amount |
| RESEARCH |  |  |  |  |  |  |
| Impact 2: Women, especially the most marginalized, fully realize their right to sustainable livelihoods, income security and economic autonomy |  |  |  |  |  |  |
| Apply existing and conduct new research at regional/country level (e.g. reviews and assessment of the institutional, legal, economic and socio-cultural environment, good practices as well as impediments to women’s economic empowerment with particular focus on women entrepreneurs and women-led businesses associations) | European Union | 1st, 2nd, 3rd and 4th Quarter, 2020 | Non-Core | TBD |
| A study to assess gender responsiveness of stimulus package announced by the Government of India in response to Covid-19 for women SMEs. The recommendations will be submitted to the Ministry of Small, Medium and Micro Enterprises for action. | European Union | 2nd and 3rd Quarter 2020 | Non-core | $7000 |
| A Review & Analysis of Gender-Responsive Procurement by Corporate India | European Union, BSAC | 3rd & 4th Quarter 2020 | Non-core | $5000 |
| Impact 3: All women and girls live a life free from all forms of violence |  |  |  |  |  |  |
| Conduct Sectoral analysis of Transport and Tourism to develop innovative programme models, with a specific focus on economic viability of safe public spaces for women and girls in India. | TBD | 1st, 2nd, 3rd and 4th Quarter, 2020 | Core | $15000 |
| Impact 6: A comprehensive and dynamic set of global norms, policies and standards on gender equality and the empowerment of all women and girls is strengthened and implemented |  |  |  |  |
| Conduct gender analysis and assessment to inform multisectoral crisis response to inform and humanitarian planning and programming | TBD | 1st, 2nd, 3rd and 4th Quarter, 2020 | Core | $5,794.00 |
| Conduct gender analysis and impact assessment for COVID-19 in India |  | Q2 an Q3 quarter 2020 | Core | $26,974 |
| Impact 5: Frontier Issue |  |  |  |  |
| 5.1.10.2 Strengthening the evidence base/ collection of gender responsive information |  |  | Non-core | $10,000 |
| 5.1.13.8 Knowledge management and documentation including global publication |  |  | Non-core | $8,500 |
| 5.1.4.3 Assessment of employment skills gaps and demands |  |  | Non-core | $5000 |
| OEEF Output 3: |  |  |  |  |
| 3.1.54 Mid Term review of the Strategic Note 2018 - 2022 |  | Q3 and Q4 2020 | Core | $7000 |
| 3.1.46 Independent Impact Assessment Study of the Tejaswini Rural Empowerment Program under Mahila Vitt Vikas Nigam, Government of Madhya Pradesh |  | Q4 2020 | Core | $30,000 |

Evaluations 2020

| Evaluation name | Mandatory? (Y/N) | UNSDF Outcome/ UN Women SP Goal, Outcome | Country/ MCO/ RO AWP Output | Office in charge | Region/ country | Joint activity Y/ N, indicate partners | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Safe City Delhi Programme Evaluation | NO | SP Outcome 4 : All women and girls live a life free from all forms of violence | Outcome 3.1 : Gender responsive legislation, action plans and policies to prevent and respond to all forms of VAWG are effectively implemented and essential services to victims and survivors delivered including a focus on the proposed new SMART cities. | Deputy Representative and OIC, India Country Office | APAC/India | No. | Government, CSOs, Women’s Groups, Women agents of change, men and boys | September-December 2020 | USD 65,000 | ToR being drafted | The proposed evaluation is with support from the donor that provided seed funding for the programme to Delhi, one of the 5 founding cities of the Global safe Cities Programme. The evaluation will require innovative design and strict adherence to principles of safety and ‘do no harm’ in view of the unprecedented ongoing COVID 19 pandemic. |