## Sheet1
TEMPLATE – MONITORING, EVALUATION AND RESEARCH PLAN 2024-2027
Instructions:
1. This template includes 3 mandatory activities: SN Mid-term Review, Country Gender Equality Profile and Country Portfolio Evaluation. DO NOT REMOVE THEM. 2. Examples have been included below to illustrate how to complete each column; they are not meant to be accurate to real life activities. 3. Please include all planned research, including the Country Gender Equality Profile (CGEP) that should be ready before development of the Common Country Assessment starts. Other knowledge products (guidance, tools, etc. should not be included in the MERP but in the Knowledge Product Plan developed at the beginning of each year. 4. Please fill out separate rows for each activity
Name of Office: Burundi Country Office
Monitoring and Research Plan 2024-2027
Activity | UN Women SN Outcome | SN Output/Relevant flagship program | Related indicator/KPI (Y/N, Indicator number, how and when) | Data Collection (Y/N, what data, how) | Office and Person in charge | Partners and stakeholders | Planned Dates (Month and year of start and end) | Donors Involved | Budget |  | Remarks
[9 empty] | Source | Amount
Monitoring
SN Mid-term Review | All | All | All | y | M&E Analyst, Progam team | All IPs & RPs | 2025-07-01 | UE, PBF, WPHF | UE, PBF, WPHF | 25000
Conduct quarterly monitoring and site visits to UN Women RPs/IPs and projects | All SN Outcomes | All SN Outcomes | All SN indicators | Y | M&E Analyst, Progam team | All IPs & RPs | March/July/December 2024, 2025, 2026 & 2027 | All CO donors | All CO donors | 160000
Annual project progress review of Implementing partners & Responsible Parties | All SN Outcomes | All Outputs | All SN Indicators | Y | M&E Analyst, Progam team | All IPs & RPs | September 2024, 2025, 2026 &2027 | All CO donors | All CO donors | 30000
Joint field missions (Government, Donors, Partners, etc.) | All SN Outcomes | All Outputs | All SN Indicators | Y | M&E Analyst, Progam team | All IPs & RPs | July/November 2024, 2025, 2026 & 2027 | All CO donors | All CO donors | 60000
Research
Conduct a baseline study on the institutional and community responses in ending VAWG | Outcome 3, Outcome 4 | SN Output: 2.1; 2.2; 2.3 | all output 2 indicators | Y | M&E Analyst | Gender ministry | 2024-01-01 | EU | UE | 17000
Develop knowledge products on best practice and effective approaches relating to social transformation favourable to preventing SGBV, conflict prevention, to nutrition and women economic empowerment | Outcome 3, Outcome 4 | All Outputs | all output indicators | Y | M&E Analyst | IPs, UNW & RPs | 2024-11-01 | EU | UE | 47000
Study on gender disparities in food systems in the project area. | Outcome 1, Outcome 3 | SN Output 1.4, 1.5; 3.1, 3.2, 3.3 | All output 1.4, 1.5 and 3.1, 3.2 and 3.3 indicators | Y | M&E Analyst | PAM, FAO, UNCDF, UNDP | 2024-03-01 | Belgium | Belgium | 15000
Evaluation Plan 2024-2027
Evaluation name | Mandatory (Y/N) | UNSDCF Outcome/ UN Women SP Outcome and relevant SDGs2 | SN Output/ Relevant flagship program | Office and Person in charge | Region/ country | Joint activity (Y/N, indicate partners) | Planned Dates (start-end) | Donors Involved | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks
Evaluations in which the office leads
Evaluation of UN Women Burundi Strategic Note (CPE) 2024-2027 | Y | All | All | M&E Analyst | Burundi | N | May-July 2027 | CORE | 30000 | not started
Project endline evaluation "Creation d'un Observatoire National sur les VBSG" | N | UNSDCF Outcome : 4 | SN Output: 2.1; 2.2; 2.3 | M&E Analyst | Burundi | N | 2025-10-01 | European Union | 17000 | not started
Project endline evaluation « Connecter le global au local renforcer des femmes pour la localisation de la resolution1325 » | N | UNSDCF Outcome : 1 | SN Output: 1.1, 1.2, 1.3, 1.4, 1.5, 1.16, 3.1, 3.2, 3.3 | M&E Analyst | Burundi | N | 2025-11-01 | PBF | 36000 | not started
Evaluations in which the office participates
Evaluation of the Burundi UNSDCF 2023-2027 | N | All | All | M&E Analyst | Burundi | Y | May-July 2027 | All donors | 60000 | not started
GPI Project Endline evaluation | Y | UNSDCF Outcome : 1 | SN Output: 1.1, 1.2, 1.3, 1.4, 1.5, 1.16, 3.1, 3.2, 3.3 | UNW M&E Analyst | Burundi | y | ocotber 2026 | PBF | 30000 | not started
Evaluation of the National Gender Policy | Y | UNSDCF outcome 1 | SN output 1.1. | UNW M&E Analyst | Burundi | Y | 2025 | PBF | 50000 | not started