MONITORING, EVALUATION AND RESEARCH PLAN 2015- – MCO Morocco, Algeria & Tunisia

Monitoring and Research Plan 2015

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount |
| MONITORING |  |  |  |  |
| Activity : Quarterly reports Project :all projects in Morocco, Algeria and Tunisia | All partners | Quarterly basis |  | NA |
| Activity : Annual report Project : all projects in Morocco, Algeria and Tunisia | All partners | Annual basis |  | NA |
| Activity: UNDAF Outputs and thematic groups In Morocco: Output Groups: 3, 4 & 5 Thematic Groups: Lead of gender thematic group, M&E, Communication, HIV, Youth and Migration In Algeria: 2 Outcome groups In Tunisia: 3 thematic Groups | UNS, national partners | At least monthly for each group |  | NA |
| Activity: Steering Committee Project Joint programme to support the National Observatory of Human Development in Morocco | ONDH, MoFA, UN WOMEN, UNPD, UNFPA, UNICEF, local authorities, universities, | December | NA |  |
| Activity Project monitoring Committee Project : Joint programme to support the National Observatory of Human Development in Morocco | ONDH, UN WOMEN, UNPD, UNFPA, UNICEF | March, June, September, December | NA |  |
| Activity Steering Committee Project : Joint programme- MDGs monitoring in Morocco | HCP, MoFA, UN WOMEN, UNPD, UNFPA, UNICEF, UNAIDS, ECA, WHO, local authorities, universities, | December | NA |  |
| Activity: Monitoring Committee Project : Joint programme- MDGs monitoring in Morocco | HCP, UN WOMEN, UNPD, UNFPA, UNICEF, UNAIDS, ECA, WHO, | March, June, September, December | NA |  |
| Activity : Monitoring Committee Project : Joint programme- MDGs monitoring in Morocco | MEF (Department of Budget, Department of Studies & Financial Forecasts, Department of General Affairs), UNW | March, June, September, December | Non core | $1000 |
| Activity : Steering Committee Project : GRB Excellence Center in Morocco | Ministry of Economy and Finance, UNW | June and December | Non core | $2,400 |
| Activity Steering Committee # Project :Women's elections Watch in Morocco, beyond the numbers | ADFM, AMVEF, YTTO, Tanmia.ma, Ennakhil, Government of Netherlands, UNW | October or November | Non Core | $1 500 |
| Activity: Steering Committee Project: Support women political participation and gender mainstreaming at the local planning, in Morocco | Ministry of Interior-DGCL, UNW | June and December | N/A | N/A |
| Activity: Technical Committee Project: Support women political participation and gender mainstreaming at the local planning | Ministry of Interior-DGCL, UNW | Monthly basis | N/A | N/A |
| Activity: Report on the status of single mothers in Morocco # Project: Training, Personnel Development and Socio-Professional Integration of Single Mothers, in Morocco | NGO INSAF, UNW | August 2015 | GEF | $2,600 |
| Activity Steering Committee # Project : Improve the access to judicial services for women and children victims of human trafficking, in Morocco | Ministry of Justice and Liberties , UNW | January/February 2015 | N |  |
| Activity Steering Committee Project : Promote and strengthen the institutionalization of equality in the public policies, in Morocco | Ministry of Solidarity, Women, Family and Social Development and UNW | Quarterly | NA | NA |
| Activity Technical Committee Project : Promote and strengthen the institutionalization of equality in the public policies, Morocco | Ministry of Solidarity, Women, Family and Social Development and UNW | Monthly |  |  |
| RESEARCH |  |  |  |  |
| Study on women and children victims of human trafficking in Morocco | Ministry of Justice and Liberties , UNW | February 2015 | Non-Core | 26 000 USD |
| Analytical assessment on women’s political participation in Algeria | Ministry of Interior in Algeria | June 2015 | Non-Core | 65235 USD |
| Study on perception of the concept of Qiwamah.in Morocco | Center of Studies and Research on Women in Islam/Rabita of Oulama | September 2015 | Non-Core | 50000 USD |
| Analytical assessment on the implementation of the family code during the last ten years in Morocco | Ministry of Solidarity, Women, Family and Social Development and UNW | February 2015 | Non-Core | 68239 USD |
| Analytical assessment of gender equality mechanisms in the different departments of the machinery of women and other ministries at the central and regional levels in Morocco | Ministry of Solidarity, Women, Family and Social Development and UNW | October 2015 | Non-Core | 23810 USD |
| Gender diagnosis on the local services that targets women, girls and elderly in Morocco | Ministry of Solidarity, Women, Family and Social Development and UNW | December 2015 | Non-Core | 14881 USD |
| Communication strategy to market the products of women cooperatives in Morocco | Ministry of Solidarity, Women, Family and Social Development and UNW | October 2015 | Non-Core | 18072 USD |
| Gender sensitive diagnosis on elderly people, Morocco | Ministry of Solidarity, Women, Family and Social Development and UNW | November 2015 | Non-Core | 24090 USD |
| Annual report 2015 on the situation of single mothers and their children in the region of Casablanca. | NGO INSAF | December 2015 | Non Core | 35000 |

Evaluation Plan 2015

| Evaluation name | Mandatory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ MCO/ RO AWP Output | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |
| Final evaluation of the programme Women’s Elections Watch (Morocco) | Y | UNDAF Outcome 4: SP Goal 1, Outcome 1.3: | Output 1.3.1 | Morocco | MCO Maghreb | N | ADFM, AMVEF, YTTO, Tanmia.ma, Ennakhil, ALCI, AMDH, FLDDF, ARMCDH, Government of Netherlands, UNW | June-November 2015 | $51,000 non core |  |  |
| Final evaluation of the Project “Improve the access to judicial services for women and children victims of human trafficking” (Morocco) | Y | UNDAF Outcome 4: SPOutcome 3: | Output 3.2.1 | Morocco | MCO Maghreb | Y | Ministry of Justice, UNW, | tbd | $16,909 non core |  |  |
| Final evaluation of the projet “Support women political participation and gender mainstreaming at the local planning” (Morocco) | Y | UNDAF Outcome 4 | Outcome 1.1/1.2/5.1 | Morocco | MCO Maghreb | N | Ministry of Interior-DGCL and UNWOMEN | Oct/Dec | $ 17,709 Non core |  |  |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |
| Final evaluation Project:Training, Personnel Development and Socio-Professional Integration of Single Mothers (Morocco) | Y | UNDAF Outcome 3 SP Goal 2, Outcome 2.2 & 2.3 | Output 2.2.1 &2.3.1 | Morocco | MCOMaghreb | NGO Insaf, UNW | NGO Insaf, UNW | November December 2015 | $20.500 Project budget (FGE) |  |  |

# Evaluation Justification Matrix 2015

| List of selected evaluation | Criteria used for the selection | Potential evaluability | Intended use of evaluation findings |
| --- | --- | --- | --- |
| Final evaluation of the programme Women’s Elections watch | -Required by the donor -The strategic characteristic of the programme regarding the role of NGOs in monitoring public policies -The size of the programme USD 1.7K | All conditions are here to conduct the evaluation | -To evaluate the efficiency and effectiveness of the program; -Accountability to the donor -Possibility to mobilize resources for a programme extension |
| Evaluation of the ProjectImprove the access to judicial services for women and children victims of human trafficking | Required by the donor The evaluation will serve for the development of a second phase of the programme | All conditions are here to conduct the evaluation | -To evaluate the efficiency and effectiveness of the program; -Accountability to the donor -Possibility to mobilize resources for a programme extension or development of a second phase |
| Final evaluation of the projet “Support women political participation and gender mainstreaming at the local planning” | Relevance of the subject | All conditions are here to conduct the evaluation | -To evaluate the efficiency and effectiveness of the program; -Accountability to the donor -Possibility to mobilize resources for a programme extension |